## Slide 1: Status of Harmonized Schedule
Antonella Chiuchiolo Work-package Leader Super-FRS magnet testing at CERN
CERN-GSI Collaboration Steering Board Meeting - 17 Nov 2022

## Slide 2: Outline
Work Package
Magnets overview
Status testing at CERN
Test schedule
Summary

## Slide 3: Work Package

## Slide 4: Magnets overview

## Slide 5: Status testing at CERN
FoS SM | 2.2019 | 2 magnets – 4 thermal cycles | 03.2022 GSI
FoS LM | 11.202 | 9 magnets – 2 thermal cycles | 09.2022 Elytt
FoS D3 | 2.2021 |  | 01.2022 GSI
SM08 | 12.2021 | 2 magnets - 1 thermal cycle | 
FoS D2 | 1.2022 | 1 magnet - 2 thermal cycles | 
SM01 | 3.2022 | 2 magnets – 2 thermal cycles | 
LM09 | 10.2022 | 3 magnets- tests 2022/2023 | 
LM11 | 12.2022 | 3 magnets- tests Q1 2023 | 
SM06 | 12.2022 | 3 magnets- tests Q1 2023 | 
MODULES
INCOMING
TESTING
OUTGOING
2022-11-17

## Slide 6: Test schedule
Original assumption before 2018
  6 weeks testing during series phase for each of the 3 test benches
Analysis 2022 after FoS experience
  Preparation of the modules for connection on the test benches is not negligible (mechanical intervention, welding, vacuum pumping)
  Cooldown, warmup and magnetic measurements depends on the size of the module and the number of magnets
  Parallel operations are defined on the base of facility and resources constraints (no parallel powering, cryo consumption, crane operation, 2 cryo shut - down per year…)

## Slide 7: Test schedule
Original assumption before 2018
Analysis 2022 after FoS experience
Calendar days
Working days (calendar days)
TB1
TB2
TB3
Example of test benches parallel activities flow
Series Dipole magnet (29 days on Test Bench)
Series Long Multiplet (54 days on Test Bench)

## Slide 8: Test schedule
Modules for the early science tested until Q3-2025
Prevision beyond 2025 will be updated after further analysis
Energy buncher to be tested in 2027 not in the present agreement
2023
2024
2025
2026
2027
Energy Buncher
Magnets for early science
3 benches: (blue, green, white)

## Slide 9: Mitigations
Courtesy of A. Kosmicki
    How do we handle possible unwanted delays?
    Quality control at manufacturer for cleanness of magnets cryo pipes improving and validation at CERN
    Cryo test facility consolidation for reducing cross talk perturbations during operation of 3 benches and clogging issues during cooldown
    Mechanical quality improvement (on going)
    Flexibility on the test plan and work flow
    Availability of “ready” modules on a bigger preparation area at CERN
LM09 cryo pipe endoscopy (edms no. 2796747)

## Slide 10: Summary
First of Series dipole and long multiplet and 2 series multiplets tested in 2022 (14 magnets in total )
Two FoS multiplets shipped to GSI for pre-assembly preparation
Magnets non-conformities analysis helped improvement of quality control and production process at the manufacturers
Test schedule updated after the experience of FoS tests and facility commissioning

## Slide 11
  Thank you for your attention