## Slide 1: Beam time(s) during FAIR Phase-0: Engineering run 2023 and Beam time 2024
D. Severin, S. Reimann

## Slide 2: Outline
Engineering Run 2023
Beam time schedule 2024/25
strategic beam time schedule

## Slide 3: Engineering-Run 2023
S. Reimann

## Slide 4: Boundary Conditions – Engineering-Run 2023
Main Goal:
Recommissioning after long shutdown (incl. LA16 renewal) to ensure full performance operation for 2024 physics run!
44 days of operation (24h 3-shift rotation and full on-call support)
energy consumption limit for 2023 (max. 43,7 GWh)
4 new persons in shift team (from Jülich via TransFAIR)
all machines fully operational (except there is a risk that ESR will have a late start)
campus
46 GWh*
* ca. 5% error bar

## Slide 5: Pre-defined Topics – from general operation request
Xenon high current measurement campaign
Uranium 73+ high current campaign
operator training and Trans FAIR integration
dual isotope beam development for medical physics
pion production evaluation run for HADES
test operation for FAIR in-kind contributions
measurement of standard beam parameters behind SIS18
open slots for prioritized machine experiments
parallel beam for Cryring experiments with local source
parallel beam for cw-demonstrator operation
user driven
acc driven

## Slide 6: preliminary schedule, only using pre-defined topics
Apparently
6 weeks are
not much time
HITRAP? commissioning: makes only sense if ESR and 7 days are available

## Slide 7: Opportunities
start of Cryring beam operation 2 weeks earlier, if shutdown work is fast and cooler commissioning can be done early
parasitic users @UNILAC and maybe @SIS18 (limited / feasibility needs to be checked)
prolongation of beam time by single days, if energy consumption over the year is low enough and re-commissioning is fast
What I need from you
A reasonable prioritized list of topics / experiments to be flexibly included if possible
Statement whether pre-defined topics are still the hot topics
  HADES evaluation run
  dual isotope beam development for medical physics
  Xenon high current measurement campaign

## Slide 8: Beam time 2024/25
D. Severin

## Slide 9: Beam time scheduling // first ideas

## Slide 10: Beam time scheduling // first ideas

## Slide 11: Challenges and Opportunities
Beam time scheduling: inhomogeneous beam request SIS/ESR
Less dense schedule -> only one beam at SIS
HLI restriction in 2024: 48-Ca operation only in 2025
HITRAP commissioning (Au block)
Machine performance and benchmarking
What we need to discuss
How to deal with open blocks (fill it up with A- vs. new PAC for 2025/26)
Schedule density
Possible restrictions in 2025 due to FAIR hardware commissioning

## Slide 12: Strategic Beam Time Schedule
S. Reimann / D. Severin

## Slide 13: FAIR/GSI strategic operation scenario
beam time
2022
2023
FAIR Phase 0
FAIR Early Science
134
120
120
120
180
180
13
Project phases
FAIR Installation of Accelerator Components
FAIR Hardware Commissioning
FAIR Beam Commissioning
2024
2025
2026
2027
2028
2029
2030
UNILAC  EH, SIS18  TH, EX, FRS, ESR  HITRAP, Cryring
Facility availability
SIS18  SFRS
SIS18  APPA-Cave
SIS100  CBM Cave (+ SFRS + APPA Cave)
HESR
p-Linac
CR
FAIR Intermediate Objective
200
FAIR MSV
240
240
Acc. Operation total / days
beam time
107
100
100
100*
150*
150*
175*
200
Physics beam time/ days
200
* Special mode of “physics beam time” only as 2nd priority in parallel to FAIR beam com.
Status Jan. 2022

## Slide 14: Assumptions
new project baseline
funding of FAIR commissioning and operation budget will be available
Remarks:
UNILAC post-stripper (Alvarez) replacement not yet included  Decision on time window for installation and commissioning will be made at an appropriate time
no performance upgrades in existing facilities are financed (exception: pulsed gas stripper)  no major change in performance to be expected for early science
50Hz high duty cycle UNILAC operation is a risk for UNILAC hardware  recommendation is, to remove it from ACC portfolio as soon as reasonable

## Slide 15: FAIR/GSI strategic operation scenario towards FS+
beam time
2022
2023
FAIR Phase 0
Early Science
134
44
140
140
90
90
15
Project phases (ES, FS, FS+)
FAIR Installation of Accelerator Components
FAIR Hardware Commissioning
FAIR Beam Commissioning
2024
2025
2026
2027
2028
2029
2030
UNILAC  EH, SIS18  TH, EX, FRS, ESR  HITRAP, Cryring
Facility availability
SIS18  SFRS  NUSTAR
SIS100 –> CBM
SIS100  SFRS  NUSTAR
200
240
240
Acc. Operation total / days
beam time
107
0
100
min 30*
min 100*
180
Physics beam time/ days
180
*number of days to be announced for PAC call
(share is reduced due to FAIR commissioning)
Update 2023 (proposal ACC)
100
FCC needed
90
min 30*
Early Science & First Science+
60
PCP reached
restricted shutdown
early science (ES) 
first science (FS) 
first science + (FS+) 

## Slide 16: FAIR/GSI strategic operation scenario towards FS+
beam time
2022
2023
FAIR Phase 0
Early Science
134
44
140
140
90
90
16
Project phases (ES, FS, FS+)
FAIR Installation of Accelerator Components
FAIR Hardware Commissioning
FAIR Beam Commissioning
2024
2025
2026
2027
2028
2029
2030
UNILAC  EH, SIS18  TH, EX, FRS, ESR  HITRAP, Cryring
Facility availability
SIS18  SFRS  NUSTAR
SIS100 –> CBM
SIS100  SFRS  NUSTAR
200
240
240
Acc. Operation total / days
beam time
107
0
100
min 30*
min 100*
180
Physics beam time/ days
180
*number of days to be announced for PAC call
(share is reduced due to FAIR commissioning)
Update 2023 (proposal ACC vs. RED)
100
FCC needed
90
min 30*
Early Science & First Science+
60
PCP reached
restricted shutdown

## Slide 17: FAIR/GSI strategic operation scenario towards FS+
2022
2023
FAIR Phase 0
Early Science
134
44
140
140
XX
90
17
Project phases
FAIR Installation of Accelerator Components
FAIR Hardware Commissioning
FAIR Beam Commissioning
2024
2025
2026
2027
2028
2029
2030
UNILAC  EH, SIS18  TH, EX, FRS, ESR  HITRAP, Cryring
Facility availability
SIS18  SFRS  NUSTAR
SIS100 –> CBM
SIS100  SFRS  NUSTAR
200
240
240
Acc. Operation total / days
107
0
100
180
Main physics beam time/ days
180
Update 2023 (proposal RED)
100
FCC needed
90
Early Science & First Science+
XX
PCP reached
restricted shutdown
m
107
XX
XX
Parasitic physics beam time/ days
XX
XX
XX
XX
Draft!
Tbd…

## Slide 18: Challenges and Opportunities
Parallel operation during FAIR commissioning (commissioning beam, physics FAIR targets, physics actual targets)
Define technical and resource dependent boundary conditions for parallel operation
What we need to discuss
Priority during transition phase: ratio of main and parasitic physics beam time
  - Clearly, we all want FAIR asap BUT we also want as much as possible beam time
Priority
FAIR commissioning and installation
Physics beam time