## Slide 1
Project Description |  | Subprojects / Tasks | 
Development of a digital potentiometer board control for FCC - Focus: UNILAC operation - But also generally as an option for other linear accelerators or any parameters, where a rotating controller makes sense. The project includes the incremental encoder hardware and the software application. |  | procurement of incremental encoders -> different encoder variants have been tested, decision still open preparation of control system communication stack -> in evaluation (LSA) UI -> open FCC console integration -> open serial production -> open | 
Project Goals |  | Ressource Profile | 
Replace the outdated UNILAC Potiboard control with a digital version that is compatible with new control room environment (FCC) ca. 100ms turnaround time (from: knob rotation  to: set values are active) FAIR control system integration Ready on time for the move to FCC Production of relevant spare parts |  |  | 
Major Milestones |  | Risks, Boundary Conditions and Comments | 
Q4/2022  Q1/2023 | technology decision – incremental encoder hardware and communication protocol | Major Risks: turnaround time too slow for adequate UNILAC control | Concerned departments: ACO (FE, AP, IN) OPE (APS)
Q4/2022  Q1/2023 | decision regarding use of control system stack (FESA or LSA or else) to be able to ensure the required performance |  | 
Q3/2023 | Hardware prototype and control system stack ready for test (e.g. for HEST magnet) |  | 
Q4/2023 | UI prototype ready | Boundary Condition: must be functional before move from HKR to FCC existing potiboard must kept functional until move to FCC is complete | Comments: to be clarified: Responsible group for hardware maintenance
Q1-2/2024 | Live test in HKR (first acceptance test of full system) |  | 
Q1/2025 | Final Acceptance Test |  | 
Year | Estimated costs [k€] | Personnel [person months]
2022 | 1 | 2
2023 | 4 | 12
2024 | 15 (inital equipment) | 3
2025 | 10 (spare parts) | 3
2026 | 0 | 0
Sum | 30.000 Euro | 20 person months
Project | FCC Digital Potiboard
Project Lead | S. Reimann
Status Date | 09.02.2022