## Slide 1
MAPS23

## Slide 2
Project Description |  | Subprojects / Tasks | 
Goal is to replace the outdated MAPS system (x86 CPU on MS-Dos, Borland C) and to install a new MAPS-System in LSB (data acquisition and software), use commercial hardware, full FESA integration, digitize all signals in parallel, allow future upgrades and enhancements of the system. Separate the fast beam loss monitor part (SVÜ, to be realized by ACO in the future). Strategy: during start phase of the upgrade signals will be splitted for parallel usage of old and new MAPS (only beam signals, not pre-amp power or I/O), first replace single transformers to allow for parallel testing with old MAPS. Then partially increase the number of transformers in the new MAPS23 up to full amount of devices and full I/O control by MAPS23. Looking for a new name. |  | Specify the system ✔ Purchase commercial electronics (2U MTCA system AM G64 CPU, TAMC532 32 channel ADC with RTM, 2xSIS8864 I/O modules, FTRN) ✔ plus spare parts -> open Manufacture adaptor box -> in progress, approx. 20k€ Find solution for MAPS oscilloscope -> 10MSPS under evaluation, higher very expensive Installation (LSB) -> open Write FESA and GUI software ✔ Perform beam tests with single transformer -> open (first tests took place) Commissioning of the full system -> open | 
Project Goals |  | Ressource Profile | 
Replace the outdated MAPS system with a modern version MAPS23 State of the art hardware components Full FESA / control system integration Be prepared for the move to FCC Separation of the beam-loss monitor part from intensity monitoring „MAPS-Oscilloscope“ function at 10 MHz sampling rate Procurement of relevant spare parts (DAQ main system plus ADC, ~25k€) (Done) |  |  | 
Major Milestones |  | Risks, Boundary Conditions and Comments | 
Q1/2021 | Start procurement | Major Risks: Complex adaptor box not ready MAPS Oscilloscope Lack of manpower LSA not yet ready at Unilac WR Timing model/domains not ready Long delivery times | Concerned departments: BEA ACO (for SVÜ) OPE (user requirements)
Q4/2022 | Procurement of hardware completed (not spares) |  | 
Q2/2023 | Further purchase of components |  | 
2023-2025 | CE Conformity for adaptor boxes (if required) | Boundary Condition: Must be prepared before move of HKR to FCC (should be easy) | Comments: - Extra costs for MAPS Oszi possible -LSA essential for ranges setting. intensity calculation and PG Schutz - CE required?
Q3/2023 or when applicable | Commissioning with beam |  | 
Year | Estimated costs [k€] | Personnel [person months]
2022 | 40 | 2.5
2023 | 20 | 2.5
2024 | 10 | 1
2025 |  | 
2026 |  | 
Sum | 30 kEuro | 3.5
Project | HKR-Injector-Upgrade / MAPS23
Project Lead | T. Hoffmann
Status Date | 10.02.2023

## Slide 3
MAPS - Macro Pulse Selector @ UNILAC 2023
Efforts (estimated):
Task Duration Costs (open)
Preparation of adaptor box: 3 - 6 months 20k€
Installation (step-by-step): 4 weeks 1k€ (cables, adaptors etc)
Programming FESA and GUI: 3 months
Implementation additional features: 6 months
SVÜ (preparation U/f converter boxes): 2 months unclear
MAPS Oscilloscope if, 12 months unclear

## Slide 4
UNIMON

## Slide 5
Project Description |  | Subprojects / Tasks | 
Goal is to replace the outdated Unimon system, i.e. display of chopper, buncher, RFQ, IH, Alv, ER etc., with an updated version using state-of-the art electronic components. The new Unimon shall be fully integrated into the accelerator control system. The complete DAQ system and the signal cables need to be moved from HKR into LSB. There, all data is digitized in preparation of usage at FCC. |  | Specify the system ✔ Purchase commercial electronics (MTCA system) ✔ plus spare parts ✔ Design and produce adaptor box ✔ Use White Rabbit timing -> in progress (final model not available) Write FESA and GUI software (Rocky 9) -> in progress Switch cables from old to new hardware -> in progress Move hardware from HKR to LSB (new rack required) -> open Perform beam tests -> in progress Commissioning of the full system -> open | 
Project Goals |  | Ressource Profile | 
Replace the outdated Unimon system with a modern version State of the art hardware components Full FESA / control system integration Be prepared for the move to FCC Move of DAQ hardware and cables from HKR to LSB Procurement of relevant spare parts (done) |  |  | 
Major Milestones |  | Risks, Boundary Conditions and Comments | 
Q1/2021 | Start procurement | Major Risks: Low priority (compared to FAIR activities), delay No clear WR timing status “cable salad” in false floor (->LSB) and damages | Concerned departments: BEA LRF (move to LSB) OPE (user requirements)
Q2/2022 | Procurement of hardware completed |  | 
Q3/2023 or when applicable | Commissioning with beam |  | 
 |  | Boundary Condition: Must be prepared before move of HKR to FCC Decision on date for HKR move | Comments: Installation space in LSB required -> who decides? Responsible persons for move??
Year | Estimated costs [k€] | Personnel [person months]
2022 | 5 | 2.75
2023 | 5 | 2
2024 |  | 
2025 |  | 
2026 |  | 
Sum | 5 | 2 person months
Project | HKR-Injector-Upgrade / Unimon-Upgrade
Project Lead | T. Hoffmann
Status Date | 10.02.2023

## Slide 7
Efforts (estimated):
Task Duration Costs
Movement to LSB: 3 months 5k€ (rack, cables, adaptors etc)
Programming FESA and GUI: 1 months
Plus programming Timing adaption: 3 months
Procurement Spare Parts 0 months done, 90000208 in 2022

## Slide 8
BPM Unilac

## Slide 9: Blockschaltbild

## Slide 10: DPX DAQ Unilac (replace Lichtorgel)
3 dedicated locations for DAQ
LSB2 (Prestripper): 4 x DPX, 16 x ADC
LSB4 (Poststripper): 11 x DPX, 1 x DP, 44 x ADC
EH-Keller (TK): 10 x DPX, 40 x ADC
Status:
3 DAQ systems incl. ADCs ordered -> long delivery times
-> Realisation in 2024 possible
nothing more done yet
Next steps:
Readout like Unimon
Preparation of DAQ rack in EH-Keller
Preparation of specification / GUI layout (Kajetan-Version)