## Slide 1: Accelerator operation and beam time 2023 – 2028…
S. Reimann, D. Severin

## Slide 2
2023 Shutdown and engineering run
Next physics beam time blocks 2024+25
Operation perspectives
Outlook

## Slide 3: Shutdown Status
LA16 Air Cooling System finished and commissioning is ongoing
Roots pumps stand (UNILAC stripper area)
Unilac super lens rods are exchanged
SIS18 µ-Spill Cavity is installed and ready for first test in Eng.-Run
SIS18 e-Septum is repaired
Cryring will be ready for operation by end of October
ESR will be ready for operation by Dec. 18th
this is our main risk, so the process is closely controlled by operations
management

## Slide 4: Engineering Run 2023
framework plan coordinated
machine studies proposals evaluated and prioritized
detailed planning is ongoing

## Slide 5: RED input for Engineering run 2023
Er-beam verification
208-Pb high rate (1Hz)
SHE: 54-Cr beam verification
High current campaign ( incl. extraction)
Dual isotope beam development for medical physics
Pion production evaluation run for HADES incl. µ-spill
Spill structure
HEST beam transport HTA, HHT (transmission, stability, focus)
FRS re-commissioning
ESR – HTA beam transport
FRS-ESR beam transport
SIS-ESR beam transport for 2nd beams
ESR deceleration and isochronous mode
SIS-ESR-CRY optimization aiming for CRY int. increase
HITRAP commissioning
DESPEC: detector tests
parallel beam for Cryring experiments with local source
ACC Topics
operator training and Trans FAIR integration
FAIR booster mode
test operation for FAIR in-kind contributions
measurement of standard beam parameters behind SIS18
open slots for prioritized machine experiments
parallel beam for cw-demonstrator operation
Last RED retreat

## Slide 6
2023 Shutdown and engineering run
Next physics beam time blocks 2024+25
Operation perspectives
Outlook

## Slide 7: Beam time schedule 2024 v5

## Slide 8: Beam time schedule 2025 v2

## Slide 9
2023 Shutdown and engineering run
Next physics beam time blocks 2024+25
Operation perspectives
Outlook

## Slide 10: FAIR/GSI strategic operation scenario towards FS+
2022
2023
FAIR Phase 0
Early Science
134
44
140
140
100
90
10
Project phases
FAIR Installation of Accelerator Components
FAIR Hardware Commissioning
FAIR Beam Commissioning
2024
2025
2026
2027
2028
2029
2030
UNILAC  EH, SIS18  TH, EX, FRS, ESR  HITRAP, Cryring
Facility availability
SIS18  SFRS  NUSTAR
SIS100 –> CBM
SIS100  SFRS  NUSTAR
200
240
240
Acc. Operation total / days
107
0
100
180
Main physics beam time/ days
180
Update 2023 (proposal RED)
100
FCC needed
90
Early Science & First Science+
80
PCP reached
restricted shutdown
m
107
30
40
Parasitic physics beam time/ days
30
30
30
100
Draft!
Last RED retreat

## Slide 11: FAIR/GSI strategic operation scenario towards FS+
beam time
2022
2023
FAIR Phase 0
Early Science
134
44
140
140
100
90
11
Project phases (ES, FS, FS+)
FAIR Installation of Accelerator Components
FAIR Hardware Commissioning
FAIR Beam Commissioning
2024
2025
2026
2027
2028
2029
2030
UNILAC  EH, SIS18  TH, EX, FRS, ESR  HITRAP, Cryring
Facility availability
SIS18  SFRS  NUSTAR
SIS100 –> CBM
SIS100  SFRS  NUSTAR
200
240
240
Acc. Operation total / days
beam time
107
0
100
180
Physics beam time/ days
180
*includes shared blocks with parallel FAIR com.
Update 2023 (proposal RED)
100
FCC needed
90
Early Science & First Science+
80
PCP reached
restricted shutdown
early science (ES) 
first science (FS) 
first science + (FS+) 
120*
140*
Last RED retreat

## Slide 12: FAIR/GSI strategic operation scenario towards FS+
beam time
2022
2023
FAIR Phase 0
Early Science
134
44
140
140
90
90
12
Project phases (ES, FS, FS+)
FAIR Installation of Accelerator Components
FAIR Hardware Commissioning
FAIR Beam Commissioning
2024
2025
2026
2027
2028
2029
2030
UNILAC  EH, SIS18  TH, EX, FRS, ESR  HITRAP, Cryring
Facility availability
SIS18  SFRS  NUSTAR
SIS100 –> CBM
SIS100  SFRS  NUSTAR
200
240
240
Acc. Operation total / days
beam time
107
0
100
min 30*
min 100*
180
Physics beam time/ days
180
*number of days to be announced for PAC call
(share is reduced due to FAIR commissioning)
2023 (ACC proposal from last research retreat)
100
FCC needed
90
min 30*
Early Science & First Science+
60
PCP reached
restricted shutdown
early science (ES) 
first science (FS) 
first science + (FS+) 
Last RED retreat

## Slide 13: ACC/FAIR Developments in schedule since last research retreat
FAIR project Re-baselining lead to changes in commissioning timeline
FCC is planned to be ready for operation Q1 2026
In 2026 new UNILAC control system will be in operation for the first time in a production run
adoptions 

## Slide 14: FAIR/GSI strategic operation scenario towards FS+
beam time
2022
2023
FAIR Phase 0
Early Science
134
44
140
140
90
90
14
Project phases (ES, FS, FS+)
FAIR Installation of Accelerator Components
FAIR Hardware Commissioning
FAIR Beam Commissioning
2024
2025
2026
2027
2028
2029
2030
UNILAC  EH, SIS18  TH, EX, FRS, ESR  HITRAP, Cryring
Facility availability
SIS18  SFRS  NUSTAR
SIS100 –> CBM
SIS100  SFRS  NUSTAR
200
240
240
Acc. Operation total / days
beam time
107
0
100
min 30*
min 100*
180
Physics beam time/ days
180
*number of days to be announced for PAC call
(share is reduced due to FAIR commissioning)
2023 (FAIR Re-Baselining update)
100
FCC OP ready
UNILAC CS ready
90
min 30*
Early Science & First Science+
60
PCP reached
restricted shutdown
early science (ES) 
first science (FS) 
first science + (FS+) 

## Slide 15: FAIR/GSI strategic operation scenario towards FS+
beam time
2022
2023
FAIR Phase 0
Early Science
134
44
140
140
90
100
15
Project phases (ES, FS, FS+)
FAIR Installation of Accelerator Components
FAIR Hardware Commissioning
FAIR Beam Commissioning
2024
2025
2026
2027
2028
2029
2030
UNILAC  EH, SIS18  TH, EX, FRS, ESR  HITRAP, Cryring
Facility availability
SIS18  SFRS  NUSTAR
SIS100 –> CBM
SIS100  SFRS  NUSTAR
200
240
240
Acc. Operation total / days
beam time
107
0
100
min 120*
180
Physics beam time/ days
180
*number of days to be announced for PAC call
(share is reduced due to FAIR commissioning)
DRAFT (opportunity for more physics)
100
FCC OP ready
UNILAC CS ready
90
min 30*
Early Science & First Science+
60
PCP reached
restricted shutdown
early science (ES) 
first science (FS) 
first science + (FS+) 
70
run to fail
DR

## Slide 16: FAIR/GSI strategic operation scenario towards FS+
beam time
2022
2023
FAIR Phase 0
Early Science
134
44
140
140
100
16
Project phases (ES, FS, FS+)
FAIR Installation of Accelerator Components
FAIR Hardware Commissioning
FAIR Beam Commissioning
2024
2025
2026
2027
2028
2029
2030
UNILAC  EH, SIS18  TH, EX, FRS, ESR  HITRAP, Cryring
Facility availability
SIS18  SFRS  NUSTAR
SIS100 –> CBM
SIS100  SFRS  NUSTAR
200
240
240
Acc. Operation total / days
beam time
107
0
100
min 120*
180
Physics beam time/ days
180
DRAFT (ACC proposal for engineering run in 2026)
100
FCC OP ready
UNILAC CS ready
90
min 30*
Early Science & First Science+
PCP reached
restricted shutdown
early science (ES) 
first science (FS) 
first science + (FS+) 
70
engineering-runs
*number of days to be announced for PAC call
(share is reduced due to FAIR commissioning)
run to fail
DR
90
0

## Slide 17: FAIR/GSI strategic operation scenario towards FS+
beam time
2022
2023
FAIR Phase 0
Early Science
134
44
140
100
17
Project phases (ES, FS, FS+)
FAIR Installation of Accelerator Components
FAIR Hardware Commissioning
FAIR Beam Commissioning
2024
2025
2026
2027
2028
2029
2030
UNILAC  EH, SIS18  TH, EX, FRS, ESR  HITRAP, Cryring
Facility availability
SIS18  SFRS  NUSTAR
SIS100 –> CBM
SIS100  SFRS  NUSTAR
200
240
240
Acc. Operation total / days
beam time
107
0
100
min 120*
180
Physics beam time/ days
180
DRAFT (possible compensation)
FCC OP ready
UNILAC CS ready
90
min 30*
Early Science & First Science+
PCP reached
early science (ES) 
first science (FS) 
first science + (FS+) 
70
engineering-runs
*number of days to be announced for PAC call
(share is reduced due to FAIR commissioning)
run to fail
DR
90
0
90
50
140+30
100+30

## Slide 18: FAIR/GSI strategic operation scenario towards FS+
beam time
2022
2023
FAIR Phase 0
Early Science
134
44
140
140+30
90
100
18
Project phases (ES, FS, FS+)
FAIR Installation of Accelerator Components
FAIR Hardware Commissioning
FAIR Beam Commissioning
2024
2025
2026
2027
2028
2029
2030
UNILAC  EH, SIS18  TH, EX, FRS, ESR  HITRAP, Cryring
Facility availability
SIS18  SFRS  NUSTAR
SIS100 –> CBM
SIS100  SFRS  NUSTAR
200
240
240
Acc. Operation total / days
beam time
107
0
100
min 120*
180
Physics beam time/ days
180
DRAFT (fire protection renovation EH)
100+30
FCC OP ready
UNILAC CS ready
90
min 30*
Early Science & First Science+
0
PCP reached
early science (ES) 
first science (FS) 
first science + (FS+) 
70
engineering-runs
*number of days to be announced for PAC call
(share is reduced due to FAIR commissioning)
run to fail
DR
90
50
8 months
fire protection renovation
EH
now
included
still
missing