## Slide 1
FAIR Status
Thomas Nilsson,
GSI/FAIR Scientific Managing Director
KHuK Jahrestagung,11-13 December 2025

## Slide 2: FAIR steps towards succesful start!
FAIR 2028

## Slide 3: FAIR & GSI Integrated Schedule
2024
2025
2026
2027
2028
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
2024 2025 2026 2027 2028
Commissioning
Injector Controls Upgrade: 1st version of new production system
Injector Controls Upgrade: finalization
ACC operation from new FCC
FCC Construction & Procurement of Interior equipment
SFRS Cooldown
SIS100 Cooldown
Controls & BI Digitization UNILAC, SIS18, ESR, Cryring, HEBT
HEBT & SIS100-FS Hardware-Commissioning
FS Beam Commissioning
Equipment
Installation
FAIR Tech. Buildings Infrastructure
FAIR Buildings Testing & Commissioning
FAIR Accelerator / Experiments Procurement & Manufacturing
SIS100-FS
SFRS-ES
FAIR Accelerator / Experiments Installation
SIS100-FS
HEBT/SFRS-ES
HBO
Regular Operation of Tech. Buildings Infrastructure
Version Q4.2 2025
Start of ES
science program
Start of FS science program
Level 2 Plan
Beam Time
Beam Time
Beam Time
Beam Time
FAIR
Beam
Comm.
EH refurbishment
SIS-18 Hematite bar replacement
Civil Construction
HEBT-ES Hardware-Commissioning
Cryo 2 Commissioning
Dry-Runs
SFRS Hardware-Commissioning
ES Beam Commissioning
Dry-
Runs
FAIR First beam (T1S1-I)
FAIR
Beam
Comm.
Beam Time
GSI-Beam Time
FBE Installation - T1S1-I
Teil 2
FBE-local comm.
Beam Time
.
Remote-integ.
Dry run-beam comm.

## Slide 4
Precision tests of QED
Cosmic ray simulator for irradiation studies
Materials under high pressure
QCD matter at high baryon densities
Phase transition and critical point
Particles in dense medium
temperature
density
Nucleosynthesis of heavy elements
Structure of exotic nuclei (e.g. hypernuclei)
Neutron matter equation of state
Gluonic excitations: Hybrids, glueballs
Precision spectroscopy of charmonium states
Time-like form factors, nucleon structure

## Slide 5: Our vision for the future: FAIR 2028
FAIR in 2028 will feature the most valuable science program which can be hosted in the FS(+) infrastructure.
The ”FAIR 2028“ science program will include:
  APPA experiments at the low-energy rings, at SIS100, at the caves at SIS18 and UNILAC with and at PHELIX and a limited set of experiments which could be hosted at all the caves served by SIS100
  NUSTAR at the Super FRS with SIS100 beams, plus SHE and MATS experiments at UNILAC and ILIMA at the low-energy rings
  CBM at the new cave with SIS100 beams, and HADES at SIS18
  PANDA is developing a hadron physics program to be carried as bridge towards the program with antiprotons, when possible using the caves and beams available at GSI/FAIR and synergies with other experiments.
→Research Strategy for the integrated FAIR/GSI campus
Thomas Nilsson | MAC-28

## Slide 6: Research Strategy Meeting for the integrated FAIR/GSI campus, July 2025:
Priority 0:
  overarching priority is the scheduled completion of the facilities for
    Early Science,
    First Science
    and First Science +
    → FAIR 2028
    permitting world-unique Research
  200 days of physics beam time annually from 2029
FAIR2028
Early Science (ES)
First Science/+ (FS/FS+)
200 days/y
>5 y SIS100
UNILAC/Rings

## Slide 7: Research Strategy Meeting for the integrated FAIR/GSI campus, July 2025:
Priority 1:
  Research at the installations of First Science ++
    Commissioning of the Low Energy Branch and APPA Caves
  Realisation of HELIAC for Material Research, and Superheavy Elements

## Slide 8: Research Strategy Meeting for the integrated FAIR/GSI campus, July 2025:
Further goals: Research with
Uranium intensity increased by a factor of 5 PHELIX successor for laser physics AGATA in the NUSTAR Low Energy Building from 2032 Thorium beam
At least five years of operation with SIS100 before installing the Alvarez 2.0

## Slide 9: Long-term goals
First Science +
MSV completion
Next steps
SIS18
SIS100
Super-FRS
ESR
CRYRING
UNILAC
CBM
NUSTAR HEB
HITRAP
APPA Laser
after 2028
NUSTAR LEB
APPA Cave
CR
HESR
PANDA
ILIMA
SPARC
First priority: Make use of available buildings

## Slide 10: FAIR Phase-0 Scientific Programme
Harvesting rich results of data taking
Beam time 2025
  Extremely successful data taking for experiments and machine studies
  Record number of physics days
  Minimal downtimes
Started in 2019, annual runs of ~110 days until FAIR operation
Supported by FAIR partners, so far:
  Finland, France, Germany, (Romania*), Sweden and the UK
8 % - 15 % speed of light
linear accelerator
UNILAC
Fragment Separator
storage ring ESR
up to 90 % speed of light
heavy-ion synchrotron
SIS 18
Ion species: H+,..., U92+
PHELIX
HADES
CRYRING
Z6
HHT
Cave A
HITRAP
Ion
sources
R3B
SHE
miniCBM
X0
M-branch
*Romania contributed 2019-22

## Slide 11: Beam Time 2025 – publicity figures

## Slide 12: Major Experiment Highlights
CBM Magnet:
  FAT of magnet support
  first dipole coil impregnated
Laser-Building planned
  next to APPA Cave within EU- financed project THRILL
APPA/NUSTAR
  Nature publication for Biophysics (ERC grant)
NUSTAR
  Discovery of new isotope 20Al – 3-proton emitter – Isospin breaking
RICH Conference in Mainz in Sept 2025
  strong participation/leadership of the PANDA collaboration

## Slide 13
“Au+Au BES completed with anticipated statistics despite shorter run time”
New SOS system enabled event rates about a factor two larger than without! (duty factor and micro spill improved)
5.9 Billion events in 11 days (33.5 shifts)
Four different beam energies investigated
Successful repair of broken cold box in time for run
FEE replaced with newly designed boards for the two inner tracking planes (MDC I & II)
Coloured bands: 800, 600, 400 200 A MeV (from red to light green)
Hatched area: weekend before scheduled beam time
Green wedge (anticipated statistics): lower boundary rate assumed in proposal (w/o SOS and FEE upgrade), upper boundary includes maximum expected gain after upgrade of FEE (w/o SOS).
Beamtime highlight
HADES run successfully completed

## Slide 14: Beamtime highlight D+D reaction cross section at the Gamov Window
3H
3He
1H
All reaction products of interest observed
Statistics of 1-2% for the majority of energies, including those within the Big Bang Nucleosynthesis energy range down to 90 keV/u
Initial luminosity calculations suggest a factor 1000 increase compared to measurements in 2024!
Analysis ongoing to understand systematics and calculate luminosity with required precision

## Slide 15: HITRAP: First Experiment with Decelerated Bare Ions at High-Z
Beamtime 2025: Nanostructuring of monolayer graphene using slow heavy ions at high charge states (G-22-00057)

## Slide 16
Scientific highlight First image-guided treatment in vivo with radioactive ion beams
Boscolo et al., Nat. Phys. 19.8.2025

## Slide 17: Some highlights … New island of asymmetric fission
Map of evolution of asymmetric fission
First Science at R3B
(p,2p) induced fission enables measurement of excitation energy (-> fission barriers)
Charge- and mass-distributions + fission barriers towards r-process nuclei
P. Morfouace, Nature doi:10.1038/s41586-025-08882-7 (2025)
Fission of exotic nuclei
Important in r-process nucleosynthesis: fragment distributions + fission barriers
Experiment: Charge distributions for for 100 neutron-deficient isotopes produced in Coulomb fission
New asymmetric fission island in the sub-lead region discovered

## Slide 18: Constraints on the equation-of-state (EoS) of nuclear matter
EoS dependence of v1, v2 of protons and clusters at SIS: PHQMD vs HADES
Strong EoS dependence of v1(y), v2(y) and v2(pT) of clusters
HADES data favor a soft momentum dependent potential
V. Kireyeu et al., arXiv:2411.04969
EoS:
S – soft
H – hard
SM - soft momentum dependent potential

## Slide 19: Installation und Start der Inbetriebnahme
HEBT
S-FRS
SIS100
HEBT
Sector 4
Pre Target Area
Mega-Science-Projekt FAIR: Installation and Start of Commisioning
© J. Hosan, GSI/FAIR

## Slide 20: FAIR-Projektstatus: Beschleunigerinstallation im SIS100-Tunnel
© GSI/FAIR, Zeitrausch
© J. Hosan, GSI/FAIR
Heavy-ion Synchrotron “SIS100”
Notes: Bild neu

## Slide 21: Installation Super-FRS
© J. Hosan, GSI/FAIR
Super-FRS components

## Slide 22: CBM-Experiment
© GSI/FAIR; Zeitrausch
Commisioning Cryoplant
© J. Hosan, GSI/FAIR
Notes: Zukunft raus

## Slide 23
NUSTAR-R3B@FAIR

## Slide 24
CBM – Compressed Baryonic Matter
Final setup in cave including HADES
© GSI/FAIR, Zeitrausch
Notes: Welche zukünftigen Möglichkeiten bietet FAIR im Bereich CBM?
Bild: Visualisierung CBM-Experiment an FAIR

## Slide 25: Pion- and proton-induced QCD studies at GSI/FAIR Hadron physics
Roadmap
Versatile program during the various phases of FAIR
FAIR Phase0: pions/protons at HADES@SIS18
      FS+: protons at CBM@SIS100
          …towards antiprotons at HESR
Hadron Physics at GSI and FAIR: Prospects for the Next Decade

## Slide 26: GSI in Helmholtz – PoF V (2028-2034)
Deutsches Elektronen-Synchrotron DESY, Hamburg and Zeuthen
Forschungszentrum Jülich FZJ, Jülich
Helmholtzzentrum für Schwerionenforschung GSI, Darmstadt HI Jena: Helmholtz-Institut Jena, HIM: Helmholtz-Institut Mainz
Helmholtz-Zentrum Berlin für Materialien und Energie HZB, Berlin
Helmholtz-Zentrum Dresden-Rossendorf HZDR, Dresden
Helmholtz-Zentrum Hereon Hereon, Geesthacht
Karlsruhe Institute of Technology KIT, Karlsruhe
A powerful alliance of world-class laboratories
Centre Evaluation of GSI Science in 2025 very successful
Next step: Strategic Evaluation of the field Matter in Q2 2026
Thomas Nilsson | MAC-28

## Slide 27: German Hightech Agenda
BMFTR has produced a document (in German only)
  https://www.bmftr.bund.de/EN/Research/HightechAgenda/HightechAgenda_node.html
Focus on six key technologies
  Artificial intelligence (AI)
  Quantum technologies
  Microelectronics
  Biotechnology
  Fusion and climate-neutral energy generation
  Technologies for climate-neutral mobility
    in addition:
  Strategic research fields
Notes: Distributed detector lab, Fusion research

## Slide 28: FAIR Council met on 9-10 Dec 2025
At a very constructive meeting, the impressive progress of the project was acknowledged with delegations of all shareholders on site.
An extraordinary Council meeting in April is expected to decide on FS+, provided India confirms its announced additional commitment.
Meanwhile the Management is authorised to do further preparatory steps towards FS+.

## Slide 29: ErUM-Pro in GSI-FAIR
German university groups play a leading role in research at GSI-FAIR
  Authorship (often leading) in scientific publications
  High international visibility
Crucial contributions to
  Experimental set-ups at FAIR
  Detector and accelerator developments
  Education and attraction of young talents
Continued support essential for the scientific success of FAIR (and GSI)
Highlights and progress in tomorrow´s FSP-talks!

## Slide 30
Thank you for your attention

## Slide 31: Backup?

## Slide 32: FAIR Experiment Status Overview
Collaborations work on maximising the science output
  Under the FAIR2028 goal
Experimental preparations progress
  Construction progress is slowly increasing towards completion
  Test/Commissioning progress also is increasing