## Slide 1: Beam Time 2024 – Report from Strahlzeitkoordinator
Daniel Severin

## Slide 2: Beamtime 2024
Many thanks for the successful beamtime!!!

## Slide 3: Summary BT2024
Ti/Ar + C/O block
  SHE/MAT (UNILAC): many adaptions due to failures
  R3B: pre-run and commissioning + very flexible phys. run (E091)
  BIO + BARB: OK, some failures
Au block
  MAT: as usual, stabile and successful
  HADES: spill feedback
  SPARC ESR-CRY: fast beam setup, good intensity
  mCBM: commissioning fast beam setup
  R3B (ASY-EOS): good pre-run

## Slide 4: Summary BT2024
Ar + Fe/Er block
  MAT: 5Hz Fe beam and Ar µ-probe
  ESA: successful
  BIO: failed (1 day)
  Hi/Despec: new Er-beam successful
Cr + Ni/Mo block
  SHE-C: 52-Cr (PIG) high intensity
  mCBM production test successful
  ILIMA/SPARC: sec. beam without FRS at ESR
  Hi/Despec: intensive test program

## Slide 5: Summary BT2024
U block
  MAT/BIO (UNILAC): successful parasitic program
  SEC+Hi/Despec: various program at FRS (E181: 2 days failed)
  Radnext: failed (3 days)
  mCBM: failed (3 days)
  PP: HiHex very successful (high pulse intensity)
  MAT (SIS): adapted to fast ext. so, successful
  SPARC: E095 OK / E052 failed / E028 successful
Cryring intern
  very flexible and successful program with 7 experiments

## Slide 6: Lessons learned concerning operation & machine
Beam setup
  Faster setup times
  Initial settings often with support of machine experts
  UNILAC/SIS matching
  Stable control system
  HEST settings reproduceable
Feedback system
  Spill structure
  Increased stability for parallel operation
Radiation safety
  TVS
  New challenges at SIS (ESR production target)
Machine stability
  Uranium operation at the limit

## Slide 7: Lessons learned concerning scheduling
Uranium block as single beam block
  No gain (?)
  Comparable intensity as parallel operation
Parallel operation
Beam settings for the entire block
  Gain during the block
  Increased stability
Machine beam block integrated
  Physics view: pro: time for setup changes // con: increased failure risk
SIS single user operation (Hades block)
  High risk if main experiment fails

## Slide 8: Lessons learned summary
It was a successful beamtime!
  Even if we had painful failures and lost some experiments (HADES, BIO, Radnext, ESR Th, FRS)
  Adaptions as solution still works
    UNILAC water leak
    Fast extraction for MAT
  Focus on avoidable failures

## Slide 9: BT 2025

## Slide 10: Upcoming challenges
2025 beamtime
  Longest block since more than 10 years (130 days physics)
  HITRAP strategy: commissioning vs. open for experiments
  48-Ca operation from HLI (3 blocks)
  Pion run (short)
  Fully packed FRS program
2026/27 PAC call
  Expectation management

## Slide 11: Physics beamtime modes
Mode A
Mode B
Mode C
Physics beamtime
Best effort operation (BEO)
Second priority
- highest priority on physics
- full parallel operation
- full on-call service at any time
- priority on physics
- limited parallel operation
- on-call service by arrangement
- priority on FAIR commissioning
- limited parallel operation
- on-call service by arrangement

## Slide 12: FAIR/GSI strategic operation scenario towards FS+
beam time
2022
2023
FAIR Phase 0
Early Science
134
44
140
140+30
140
12
Project phases (ES, FS, FS+)
FAIR Installation of Accelerator Components
FAIR Hardware Commissioning
FAIR Beam Commissioning
2024
2025
2026
2027
2028
2029
2030
UNILAC  EH, SIS18  TH, EX, FRS, ESR  HITRAP, Cryring
Facility availability
SIS18  SFRS  NUSTAR
SIS100 –> CBM
SIS100  SFRS  NUSTAR
200
240
240
Acc. Operation total / days
beam time
107
0
100
min. 120*
180
Physics beam time/ days
180
100+30
FCC OP ready
UNILAC CS ready
140
Early Science & First Science+
PCP reached
early science (ES) 
first science (FS) 
first science + (FS+) 
engineering-runs
DR
50
renovation
EH
now
included
still
missing
Pre-paration works
EH
renovation
EH
70

## Slide 13: FAIR/GSI strategic operation scenario towards FAIR
beam time
FAIR Phase 0
Early Science
140
140+30
140
13
Project phases (ES, FS, FS+)
2024
2025
2026
2027
2028
2029
2030
Facility availability
200
240
240
Acc. Operation total / days
beam time
100
min. 120*
215
Physics beam time/ days
215
100+30
140
Early Science & First Science+
FAIR Installation of Accelerator Components
FAIR Hardware Commissioning
FAIR Beam Commissioning
UNILAC  EH, SIS18  TH, EX, FRS, ESR  HITRAP, Cryring
SIS18  SFRS  NUSTAR
SIS100 –> CBM
SIS100  SFRS  NUSTAR
FCC OP ready
UNILAC CS ready
PCP reached
early science (ES) 
first science (FS) 
first science + (FS+) 
DR
50
renovation
EH
now
included
still
missing
Pre-paration works
EH
renovation
EH
70
2031
2032
Science
240
240
215
215

## Slide 14: FAIR/GSI strategic operation scenario towards FAIR
beam time
FAIR Phase 0
Early Science
140
140+30
140
14
Project phases (ES, FS, FS+)
2024
2025
2026
2027
2028
2029
2030
Facility availability
200
240
240
Acc. Operation total / days
beam time
100
min. 120*
215
Physics beam time/ days
215
100+30
140
Early Science & First Science+
FAIR Installation of Accelerator Components
FAIR Hardware Commissioning
FAIR Beam Commissioning
UNILAC  EH, SIS18  TH, EX, FRS, ESR  HITRAP, Cryring
SIS18  SFRS  NUSTAR
SIS100 –> CBM
SIS100  SFRS  NUSTAR
FCC OP ready
UNILAC CS ready
PCP reached
early science (ES) 
first science (FS) 
first science + (FS+) 
DR
50
renovation
EH
now
included
still
missing
Pre-paration works
EH
renovation
EH
70
2031
2032
Science
240
240
215
215

## Slide 15: Remarks
Mid-term
  EH renovation
  Parallel FAIR commissioning and physics run
  Performance upgrades
    Pulsed gas stripper
    Spill feedback / µ-spill cavity
    Control system (eg. archiving)
    etc.
Long-term
  UNILAC
    HLI vs. Heliac: perspectives for SHE & MAT
    HSI (RFQ, super lens, IH): action needed?
  FAIR commissioning after PCP

## Slide 16: Thanks for you attention