## Slide 1: Strategic beam time schedule
Stephan Reimann, M. Vossberg
Beam Time Retreat 2024 – Do. 16:30-16:50

## Slide 2: 2025

## Slide 3
Strategic Schedule – Status Jun. 2024
100
140
0
44

## Slide 4: Strategic schedule – FAIR-commissioning perspective
Injector Controls Upgrade: finalization
2024 2025 2026 2027 2028
HEBT-ES HW-Commissioning
Beam Time
Eng. Run
Beam Time
Beam Time
SIS100 HW-Commissioning
HEBT-FS HW-Commissioning
SFRS HW-Commissioning
FCC - MCR commissioning
Injector Controls Upgrade: 1st version of new production system
ES Beam Commissioning
FS Beam Commissioning
operation from FCC
UNILAC operation with new CS
FCC Construction & Procurement of Interior equipment
Cryo 2 Commissioning
SFRS Cooldown
SIS100 Cooldown
Controls & BI Digitization UNILAC, SIS18, ESR, Cryring, HEBT
Dry-Runs
Dry-Runs
Dry-Runs
Dry-Runs