## Slide 1: 7th Beam Time Retreat Shutdown Planning 2024
M. Klich, M. Müller, Y. Valdau – Shutdown Coordination
11th and 12th July 2024
@ Hotel Jagdschloss Kranichstein
BEAM TIME RETREAT 2024

## Slide 2
Planning process
Overview Shutdown
Shutdown’s Framework
Shutdown activities
Content
BEAM TIME RETREAT 2024

## Slide 3
Collecting activities from Machine Coordinators
Creating Shutdown Activity List
Meetings with Commons departments
  Effort estimation
Review of the list taking into account available resources
Distribution of reviewed list with prioritization in Machine Meeting
Resource loaded first draft of shutdown plan
Planning Process
BEAM TIME RETREAT 2024

## Slide 4
From Microsoft Project to Planisware Establish new structure | Great support from Project Management Office
Switch to Planisware
BEAM TIME RETREAT 2024

## Slide 5
Shutdown plan resource loaded
List of activities per division
Effort FTE per week
Evaluation of Resources
BEAM TIME RETREAT 2024

## Slide 6
Overview Shutdown
BEAM TIME RETREAT 2024

## Slide 7
Shutdown’s Framework
Installation FAIR in parallel
Lack of time
Injector Controls Upgrade Project
BEAM TIME RETREAT 2024

## Slide 8
Shutdown Activities - Across GSI
Preparations for renovation of Experimental Hall (EH)
Rebuilding control system KS02
Maintenance of medium voltage switch gear =AE
Exchange/refurbishment fire protection dampers
Survey & Alignment
§88 Test
OPEN: TVS (Tür-Verriegelungs-System)
BEAM TIME RETREAT 2024

## Slide 9
Shutdown Activities - UNILAC
Water leakage GUH3QT3 (IH1) & repair steerer GUH2MS3
Alvarez A4
  Modification of RF loop A4
  Replacement leaking pump valve
Alvarez A3
  Vacuum leaks in tank cap
  Drift tube DR31 fore-vacuum
Alvarez A2
  Drift tube DR105
  Vacuum leak check BB5
BEAM TIME RETREAT 2024
UNILAC Radio Frequency
Pulsed gas stripper
Source: GSI / M. Vossberg

## Slide 10
Shutdown Activities - SIS18
Exchange of GS06DFV scintillator screen window
Maintenance of SIS12/SIS18 mode power switch
NEW: Repair of connector electrostatic extraction septum
If resources are available or with external resources:
Installation of prototype cryo inserts
Open SIS18 electrostatic extraction septum and repair of clearing electrode
BEAM TIME RETREAT 2024
Source: GSI / B. Walasek-Höhne

## Slide 11
Shutdown Activities - HEST
Cupid Upgrade
Exchange of GHTTDF2V screen
Power Converters GTE1QD11/QD12/KY1 refurbishment
NEW: Repair TE-Stripper
BEAM TIME RETREAT 2024
GHADDF2
GHADDF3
GHTTDF2

## Slide 12
Shutdown Activities - Other Machines
BEAM TIME RETREAT 2024
CRYRING@ESR Installation 14.5 GHz ion source E-cooler Experiment preparations | ESR Preparation target area FRS Installation stepper motors control hardware Upgrade quadrupole PC HITRAP Extension control system Investigations IH cavity

## Slide 13
Thank you for your attention!
Source: GSI/FAIR, D. Fehrenz

## Slide 14
Back Up
BEAM TIME RETREAT 2024

## Slide 15
Maintenance of MV switch gear =AE (1/3)
BEAM TIME RETREAT 2024

## Slide 16
Maintenance of MV switch gear =AE (2/3)
BEAM TIME RETREAT 2024

## Slide 17
Maintenance of MV switch gear =AE (3/3)
BEAM TIME RETREAT 2024

## Slide 18
Exchange/refurbishment fire protection dampers
BEAM TIME RETREAT 2024
(1/7)

## Slide 19
Exchange/refurbishment fire protection dampers
BEAM TIME RETREAT 2024
(2/7)

## Slide 20
Exchange/refurbishment fire protection dampers
BEAM TIME RETREAT 2024
(3/7)

## Slide 21
Exchange/refurbishment fire protection dampers
BEAM TIME RETREAT 2024
(4/7)

## Slide 22
Exchange/refurbishment fire protection dampers
BEAM TIME RETREAT 2024
(5/7)

## Slide 23
Exchange/refurbishment fire protection dampers
BEAM TIME RETREAT 2024
(6/7)

## Slide 24
Exchange/refurbishment fire protection dampers
BEAM TIME RETREAT 2024
(7/7)

## Slide 25
Renovation roof BG, TR & EX
BEAM TIME RETREAT 2024