## Slide 1: Report from the Controls Review
R. Aßmann
BTR 2024, 12.7.2024

## Slide 2: Review Committee
Chair
Jörg Wenninger (CERN), MAC member
Members
Enrique Blanco Vinuela (CERN)
Michael Costanzo (BNL)
Grzegorz Kruk (CERN)
Rüdiger Schmidt (CERN), MAC member
Scientific Secretary
Sabrina Appel (GSI)

## Slide 3: Background of Review
For FAIR a new control system is being developed, widely based on CERN controls architecture components.
The FAIR controls project includes upgrading the existing GSI accelerator systems to the new system.
The controls work is centered in the accelerator controls (ACO) department but also involves the beam diagnostics (BEA) department, the operations (OPE) department, the FAIR SIS-100 sub-project (SYS) and various additional persons in other departments, e.g. DEC.
Work spans over the FAIR project and the GSI accelerator division.
A Controls Steering Group had reviewed and ranked the various controls tasks in 2022, ranking about 200 tasks in priority.

## Slide 4: Review Mandate
Review the planned controls tasks, the assigned priorities and the degree of completion.
Review the control system features to be provided versus the control room needs.
Review the use of underlying software packages and approaches, especially focusing on the middleware solutions planned.
Review the organization of work, the status of collaboration between different departments and the decision process and control of subsequent execution.

## Slide 5: Program I

## Slide 6: Program II

## Slide 7: Preliminary Outcome – General Remarks
The Committee would like to thank the FAIR management team and staff for the excellent organization, clear presentations and open discussions at this control system review. The work of the review committee was eased significantly by the fact that the presenters adhered to the prepared layout and guidelines for the review.
The Committee observed that collecting all the information on the state of controls and bringing together staff across groups to discuss the status of the control system may be one of the main achievements of this review.
The Committee would also like to congratulate the GSI-FAIR team for the excellent overall advancement of the control system in view of Early Science (ES) and First Science (FS) that was presented during the review.

## Slide 8: Preliminary Outcome Recommendations I
Consider re-starting a body with an emphasis on focussing and prioritizing the controls activities across GSI/FAIR towards ES/FS goals.
The committee recommends ensuring adequate resources for managing the ORACLE database. As more rings and transfer lines are added and automated feedback systems are introduced, existing performance issues with parameter trims are likely to become more pronounced.
Prioritize the collection of the requirements for SFRS to start the needed development (of industrial controls) and be ready for ES.
Discuss between the teams how data from the technical network can be accessed from NUSTAR (and the reverse).

## Slide 9: Preliminary Outcome Recommendations II
Evaluating how this system (OpenDigitizer, OpenCMW, GNU Radio) integrates into the control infrastructure, considering all implications such as long-term maintenance, or exploring alternative approaches, necessitates discussions among the responsible team members, guided by management. These discussions should aim to reach a consensus on the preferred course of action, with a clear division of responsibilities, as this decision will have significant long-term impacts on the entire control system and its users.
The committee considers that the resources allocated to data archiving are not sufficient given the importance of archived data to fully exploit and understand modern machines. The committee considers that this system needs attention, the need for data storage and the list of data sources and performance limitations may be underestimated.

## Slide 10: Preliminary Outcome Answers to Questions I
Are there any control system features missing in your opinion? In case yes, what is missing?
  The committee does not see that any major feature is missing. The committee observed however that the development of an important system like post-mortem for magnet protection has not yet started.
Are there any control system features obsolete or not important in your opinion? In case yes, what is obsolete and can be removed from the work list?
  The committee acknowledges that an important effort is ongoing to eliminate legacy systems, largely driven by the commissioning of the new FCC control room in 2026. The ICU renovation project is well structured, seems to receive the adequate level of attention and has well defined and understood milestones.

## Slide 11: Preliminary Outcome Answers to Questions II
Are there any planned features inefficient in your opinion, in the sense that simpler solutions could be adopted, or already existing solutions can be adapted? In case yes, where and how could efficiency be gained?
  The readout of the digitizer HW with the FESA class implemented by COSYLAB does not apparently meet the specifications. For this reason, a new implementation (OpenDigitizer) relying on OpenCMW as a communication protocol was launched in collaboration with an external company. This represents a vertical control system slice which does not build on ACO standards. The committee did not receive sufficient information to judge on the justification for a separate standard.

## Slide 12: Preliminary Outcome Answers to Questions III
Is there a need to adjust the priority for some controls work packages in your opinion? In case yes, what should be lowered or raised in priority?
  A priority list was established by the CSG a few years ago. The committee recommends updating those priorities to match the targets of ES/FS. The advancement of key components should be tracked regularly to ensure the success of ES/FS. This may become particularly important with the beginning of the intense commissioning periods between 2026 and 2028 when many resources may be bound by support and operation of the new facilities.
Can the planned FAIR controls milestones be reached in your opinion? In case you see delays, where are those and do you have suggestions for improvement?
  The committee considers that the ES/FS milestones can be met, even if some control system components may not be completed at the beginning. In case of delays the priority of the task should be optimized, see also the recommendation from the previous point.

## Slide 13: Preliminary Outcome Answers to Questions IV
Is the planned controls system well maintainable (within the available resources at GSI/FAIR) in your opinion, both in terms of software updates and in complexity? In case not, where should we take actions?
The committee encourages the GSI FAIR teams involved in the development of the control system components to adhere to standards and avoid parallel developments that are not strongly justified. This will minimize the long-term maintenance effort. The large majority of teams involved in the development use ACO standards (CMW, FESA, LSA). Using the OpenCMW middleware in a vertical slice (FEC to control room application) beyond the use case of beam-based feedback for which it was designed, introduces a redundant communication protocol requiring maintenance.
The fact that standard FECs and BEA FECs operate with different boot configurations increases the overall maintenance effort. The committee encourages ACO to search for a unique boot configuration for all FECs.
The LSA trim performance may present an issue in the future with more machines and more settings. The issue seems mainly due to ORACLE DB access performances. The committee recommends training or hiring a staff with expertise in ORACLE DB design and optimization.
The committee observed that in many areas specific developments are performed by one or two individuals, creating a large risk of knowledge loss in case of absence, illness etc. It is also clear that there are no simple solutions to this problem as long as the number of staff is limited.

## Slide 14: Preliminary Outcome Answers to Questions IV
Is the work well organized and efficient towards our goals in your opinion? In case you see room for improvement, please comment on possible measures to be taken.
  The committee got the impression that communication between the different teams involved in control system component development could be improved. In that respect the review had probably an important role as a forum for information exchange. The organization of meetings devoted to controls may deserve to be re-analysed. Monitoring the progress on the control system advancement and prioritizing tasks during heavy commissioning periods may be important: to this end a steering body should be set up. This body must closely follow the progress of the commissioning of the machines to be able to take the appropriate decision or formula pertinent recommendations concerning priorities.

## Slide 15: Conclusion and Outlook
Very useful FAIR MAC review of our controls work.
Many thanks to all the speakers for really excellent presentations and the many useful discussions.
Feedback from the committee is very encouraging for us – we are on a good track.
The committee’s recommendations will help us to focus on the most important aspects, to address some shortcomings and to optimize our work flow.
To be followed up on…