## Slide 1: FAIR Commissioning general strategy, definitions, organisation, roles
Stephan Reimann
1st FAIR Commissioning Workshop 07.11.-08.11. 2024

## Slide 2: Outline
FAIR 2028 & Project Stages
Strategic Schedule
Commissioning Phases
Chains, Sections, Systems
Planning Status
Organisation of the Subproject
Preparatory Activities
Roles in Execution Phase
appendix: buildings & NE-areas
NUSTAR - visualisation - zeitenrausch

## Slide 3: FAIR 2028
until 2028
after 2028

## Slide 4: FAIR Stages – Intermediate Objectives
FAIR Early Science (ES)
FAIR First Science (FS)
+ CBM
HEBT (ES)
SFRS
HEBT (ES)
HEBT (FS+)
SFRS
SIS100

## Slide 5: FAIR – HEBT Tunnel 30.10.2024

## Slide 6: FAIR – HEBT Tunnel 30.10.2024

## Slide 7: FAIR commissioning – strategic schedule
Injector Controls Upgrade: finalization
2024 2025 2026 2027 2028
HEBT-ES HW-Commissioning
Beam Time
Beam Time
Beam Time
SIS100 HW-Commissioning
HEBT-FS HW-Commissioning
SFRS HW-Commissioning
move to MCR & commissioning
Injector Controls Upgrade: 1st version of new production system
ES Beam Commissioning
FS Beam Commissioning
operation from FCC
UNILAC operation with new CS
FCC Construction & Procurement of Interior equipment
Cryo 2 Commissioning
SFRS Cooldown
SIS100 Cooldown
Controls & BI Digitization UNILAC, SIS18, ESR, Cryring, HEBT
Dry-Runs
Dry-Runs
Dry-Runs
Dry-Runs
Beam Time
equipment
Installation

## Slide 8: Commissioning phases for accelerators and detectors
# | commissioning phase | accelerators & transfer lines | detectors
1 D1 M103 | local HW- commissioning | local system tests in tunnel and supply areas Control system not needed (only in limited aspects) TBI not needed, site power is sufficient | single detector tests tests of individual components install. service & controls
2 D2 M104 | remote & system commissioning | single system test (vertical system integration test) remote testing from MCR (sequences, checklists) TBI (phase 5 and 6), control system integration and timing is needed, access control & STVs needed | system tests (with HV, gas, ...) pre-test of DAQ system local control
3 D3 M105M11 | integration | (3.1) multi system tests & (3.2) full Dry-Runs control system and accelerator models for pilot beam scenarios fully available, PAS commissioning done | full detector test and DAQ using cosmics
4 E M12 | pilot beam commissioning | pilot beam commissioning (completion parameters) operation permit | commissioning with pilot beam
inst.
Commissioning without Beam
Beam Commissioning
 | beam commission & operation | operation with PCP-beam respectively status quo beam commissioning of advanced systems and complex operation modes / intensity ramp-up accelerator development towards FAIR design parameters
handover to operations
color-codes aligned with responsibility matrices

## Slide 9: Chains  Sections  Systems
(UNILAC  SIS18 ) HEBT  SFRS  HEB  NUSTAR
T1S1
T1S2
TSX1
FTF1
FPF0-4
FMF1-3
FHF1-2
TSF1
T1F2
NUSTAR
Chain
Sections
T1S1
Section
DIP
DIP
VAC
DIAG
QUAD
VAC
DIP
DIAG
QUAD
Systems
(tunnel area part)
PS
PS
PS
DAC
PS
SPEC
TBI
Systems
(supply area part)

## Slide 10
HEBT
hardware commissioning
SFRS
hardware commissioning
Early Science
beam commissioning
Cryo-Link
Site & Installation
Controls & Access System
SIS100
detailed section-wise planning for ES-HEBT and SFRS is available for all commissioning phases
installation planning is linked
TBI commissioning milestones, are updated, linked

## Slide 11: Ongoing preparatory Activities
Commissioning Workshop for each System Type
development of a commissioning procedure
collect prerequisites and boundary conditions for each commissioning step
review resources & impact on baseline schedule
write a commissioning instruction document
define a test sequence for acceptance of M11 (ready for beam)
implement test sequence in sequencer service software

## Slide 12
Commissioning Organisation
FC-SPL
HEBT
commissioning responsible
SFRS
commissioning responsible
SIS100
commissioning responsible
Cryo
commissioning responsible
Controls
commissioning responsible
NUSTAR
commissioning responsible
F. Hagenbuck S. Pietri P. Spiller H. Kollmus R. Bär H. Albers
S. Reimann
(deputy V. Kamerdzhiev)
Commissioning responsible:
participation in bi-weekly commissioning meeting
responsible for planning (Planisware & commissioning workshops), preparation, execution of commissioning
coordinates work package leaders
Machine-SPL/SSPL:
declares/ signs readiness for beam commissioning (or operation in case of Cryo and Controls)
safety &
beyond FS

## Slide 13: Main Roles during Commissioning (execution phase)
Commissioning Coordinator (CC)
is rotated weekly
general coordination, weekly planning
host of daily coordination meetings / briefings
on-call over nights & weekends
Commissioner in Charge per Machine (CiC)
is rotated weekly
day to day coordination with WPLs / tech. dep. on site
on-call over nights & weekends
Definition of daily tasks for tech. groups & shift team
Safety Responsible Persons (STVs)
for tunnels and supply areas
working permits
definition of safety measures (e.g. Freischaltung)
room access control
Steering is done in weekly Commissioning Meeting hosted by FC-SPL or deputy
work schedule is determined by CC
all commissioning activity must be registered in the commissioning meeting
all work in tunnels and supply rooms must be registered in the commissioning meeting
working permits are only granted by STVs
central coordination via FAIR Control Centre

## Slide 14: First 3 major Commissioning Milestones
June 1st 2025 Cryogenic Plant “Cryo2” (building K0720A) & parts of main supply building H0719A
Q1/2026 FAIR Control Centre and new Main Control Room Q3 first beam in GSI from FCC
Q4/2026 First Beam Event T1S1

## Slide 15: E.o.P.

## Slide 16: Sections of HEBT (ES)

## Slide 17: Sections of SuperFRS

## Slide 18
Buildings

## Slide 19
NE Areas