## Slide 1: HEBT Hardware Commissioning
Frank Hagenbuck
1st FAIR Commissioning Workshop
November 7-8, 2024

## Slide 2: Outline
Introduction – HEBT Overview
HEBT Early Science
Commissioning Planning
Schedule
Roles
Summary

## Slide 3: HEBT Overview – MSV (Module 0-3)
29 sections (13 connections/beam lines)
total length (HEBT) ca. 1.5km
all beam lines normal conducting
nominal magnetic rigidity 100Tm, 18Tm, 13Tm
parallel operation
full version had to be taken into account for building planning of the MSV

## Slide 4: HEBT Overview – Staging
(*to be added to complete the scenario)
dotted lines are not part of HEBT

## Slide 5: Buildings – MSV
H0719A
L0516A
G0418A
G0418A
with HEBT Supply
K0410A
K0923A
with HEBT Beamline
K0406A
09A
H02
321A
K0
G0702A
K0617A
H0307A
K0619A
K0503A
G0704A
GAP HEBT
H0705A

## Slide 6: Buildings – Early Science
H0719A
with HEBT Supply
G0702A
K0617A
G0704A
H0705A
with HEBT Beamline
GAP HEBT

## Slide 7: HEBT Early Science (ES)
T1S1
T1S2
TSX1
TSF1
TFF1
T1F2
G0702A
TR
H0705A
K0617A
SIS100
SIS18
 | TR/G0702A | G0702A/H0705A | H0705A/K0617A | K0617A |  |  | 
 | T1S1 | T1S2 | TSX1 | TSF1 | T1F2 | TFF1 | Sum
Length [m] | 102,0 | 55,2 | 88,7 | 17,2 | 14,3 | 11,6 | 289,1
VAC Sections | 3 | 1 | 2 | 1 | 1 | 1 | 9

## Slide 8: HEBT ES Vacuum Sections
T1S1
T1S2
1
2
3
T1S1 – VAC section 1
T1S1 – VAC section 2
T1S1 – VAC section 3
T1S2

## Slide 9: HEBT ES Vacuum sections
TSX1
TSF1
T1F2
H0705A
K0617A
1
2
TFF1
TSX1 – VAC section 1
TSX1 – VAC section 2

## Slide 10: HEBT ES Components
E20.010
E20.021
T1S1
T1S2
G0704A.E20.010
G0704A.E20.021
yellow – racks for ES

## Slide 11: HEBT ES Components
TSX1
TSF1
T1F2
TFF1
E30.130
E30.120
H0719A.E30.130
yellow – racks for ES
H0719A.E30.120
yellow – racks for ES

## Slide 12: HEBT ES Components
 |  | Beamline | Supply
 |  | all ES sections | G0704A + H0719A
Dept (WP) | System Type |  | 
NCM, EPS | Dipole Magnet | 16 | 10 HB.Dx
 | Quadrupole Magnet | 43 | 42 HB.Qx
 | Steering Magnet | 23 | 23 HB.Cx
BEA | Diagnostic Chamber | 18 | 31 Racks + Gas Mixing Station
 | Multiwire Proportional Chamber (MWPC) | 12 | 
 | Particle Detector Combination (PDC) | 6 | 
 | SEM-Grid | 12 | 
 | Scintillation Screen (SCR) | 5 | 
 | Beam Position Monitor (BPM) | 9 | 
 | Transformer (RT & FCT) | 8 | 
 | Cryogenic Current Comparator (CCC) | 2 | 
VAC | Ion Getter Pump | 31 | 6 Racks
 | Penning Gauge | 17 | 
 | Pirani Gauge | 10 | 
 | Fast Valve Sensor | 2 | 
 | Fast Valve | 2 | 
 | Roughing Valve | 11 | 
 | Gate Valve | 10 | 
 | Venting Valve | 11 | 
VAC (SI) | Safety Beam Plug | 3 | in Rack PAS
 | Foil Stripper | 1 | 1 Rack SI
 | Collimator | 3 | in Rack BEA
ACO |  |  | 40 Racks*

## Slide 13: Commissioning Planning
Status
Procedures and prerequisites for commissionig of system types defined in LCM workshops
Almost all system types of ES covered
Visualization of processes in LCM started by FCO
Estimation of time and ressources provided by WPLs/Departments and discussed with SSPL
Commissioning plan has been reorganised with PPL and a new timeline has been set up for ES
Next steps
Set up new timeline for First Science
Include ressources in Planisware
HEBT commissioning workshop in Q1/2025
  discuss commissioning steps and status preparation in detail with WPLs/Departments
  coordinate/optimize order of activities between WPLs/Departments (order defined in 2016)
  establish roles
BEA
EPS
VAC

## Slide 14: Commissioning Planning - Progress dashboard
Dept. | System Type | 1st. workshop done | procedure developed | prerequisites collected | review resources | review schedule | work instruction doc. | sequence procedure | sequence implementation | Status
NCM, EPS | NC-magnet & power supply (dipole, quad, steerer) | 100% | 100% | 100% | 100%* | 50%* | 0% | 100% | 30% | 73%
BEA | Beam transformer | 100% | 100% | 100% | 100% | 50%* | 50% | 0% | 0% | 63%
BEA | BPM beam position monitors | 100% | 100% | 100% | 100% | 50%* | 50% | 0% | 0% | 63%
BEA | SEM grid | 100% | 100% | 100% | 100% | 50%* | 50% | 0% | 0% | 63%
BEA | SCR luminous screen | 100% | 100% | 100% | 100% | 50%* | 50% | 0% | 0% | 63%
VAC | Vacuum sector (valves, pumps, gauges, controller, ...) | 100% | 50% | 50% | 100% | 50%* | 0% | 100% | 50% | 63%
VAC (SI) | Safety beam plug | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 38%
BEA | MWPC multi wire proportional chambers | 100% | 100% | 100% | 100% | 50%* | 0% | 0% | 0% | 56%
BEA | BLM beam loss monitors | 100% | 100% | 100% | 100% | 50%* | 0% | 0% | 0% | 56%
BEA | Pneumatic drive controls | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
BEA | CCC cryogenic current comparator | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
VAC (SI) | Foil stripper | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
VAC (SI) | Collimator | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
VAC | Bakeout system | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
 | HEBT overall preparation status | 49% |  |  |  |  |  |  |  | 
maintained by FCO-Team (*estimate by F. Hagenbuck)
not in ES
(02.2024 29%)
LCM workshop yesterday

## Slide 15: HEBT ES Installation Schedule

## Slide 16: HEBT ES Commissioning Schedule

## Slide 17: HEBT Installation (ES, FS) & Commissioning (ES) Schedule
2025
2026
2027
2028
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
ES HEBT Commissioning - Phase 1
ES HEBT Commissioning Phase 2-3.1
T1S1
T1S2
TSX1
TSF1
T1F2
TFF1
T1S1
T1S2
TSX1
TSF1
T1F2
TFF1
ES HEBT - Commissioning Phase 3.2-4
ES HEBT ready for beam (M11)
ES HEBT ready for operation (M12)

## Slide 18: ‘Staged’ Commissioning of TBI - HEBT
T1S1, T1S2 „need“ G0702A and G0704A
Start local HW Commissioning with T1S2 in 09/2025
Media supply (Stage V) in G0702A and G0702A available in 12/2025
TSX1, TSF1, T1F2, TFF1 „need“ H0705A, K0617A, H0719A
Start local HW Commissioning TSF1 in 08/2026
Power and Media supply (Stage V) available

## Slide 19: HEBT Commissioning Roles
HEBT Commissioning Management (1 FTE, 2 heads – by HEB)
Overall coordination of activities
Reporting to SPL FAIR Commissioning and SPL Commons (level1)
Overall time planning
Coordination with the building activities in neighbouring areas
Authorisation to stop construction activities if needed
Define access restrictions together with STV(p) and Commissioners
HEBT Commissioners (1 FTE, 2 heads – no ressources in HEB)
Weekly coordination of activities together with STV(p) and WPLs
Weekly reporting
Daily coordination of activities on site
Activity primarily on the construction site
HEBT WPLs (+ staff from related department)
Execute Commissioning
Reporting to Commissioner
STV(p) (up to 1 FTE, 2 heads – by HEB + ?)
Preparation of safety instructions GBU, ASR …
Define access restrictions together with Commissioning Management and Commissioners
Revision of the instructions if needed
Monitoring of compliance with the safety rules

## Slide 20: Summary
T1S1
T1S2
TSX1
LCM workshops for almost all system types done
Estimation of time and ressources provided by WPLs/Departments
New timeline has been set up for Commissioning HEBT Early Science
Commissioning HEBT Early Science Phase1-3.1 parallel to installation HEBT First Science
Planned start of local HW commissioning in 09/2025 with section T1S2
Close coordination with installation required – transportation along T1S2

## Slide 21
Thank you
for your attention
Special thanks to the HEBT Planungsgruppe and all colleagues contributing to HEBT and this presentation.

## Slide 22: HEBT beam commissioning
First step
favourable before first beam is directed to FAIR – measurement of beam parameters in HEST close to TS1MU1
start with nominal ion optic setting of beamline SIS18-SFRS
start with pilot beam, e.g. Ar, medium energy (12-18Tm), low intensity
use fast extracted beam for first commissioning of beamline
switch off/on HEBT branching dipoles to avoid uncontrolled beam loss in superconducting SFRS magnets
beam steering element by element (+ check functionality of beam diagnostics during this step)
beam will be dumped on SFRS beam catcher
Secon step (beam reaches SFRS beam catcher)
kick response measurement
aperture scan
measurement of dispersion
beam optimization to ensure hand over parameters for SFRS

## Slide 23: Tunnel G0702A

## Slide 24: Tunnel K0617A

## Slide 25
Montageplanung HEBT Tunnel
Stand: 01.11.2016
2.14.12
Installations/
Assembly
CSTI
M. Bevcic
2.14.9.8
Alignment
ENMA
I. Pschorn
2.3.3
Power Converter
LOEP
H. Welker
2.3.6
Beam Instru-
mentation(BI)
CSBI
B. Walasek-H.
3
Building
infrastructure
FSB
A. Fischer
2.3.11
Special
Installations
SIS18/SIS100(SI)
L. Bozyk
Arbeitspakete / Zuständigkeiten
2.3.2.
Magnets
ENMA
C. Mühle
2.3.7
Vacuumsystems
CSVS
L. Urban
Inbetriebnahme
Komponenten
Anschluss
Komponenten
4.
Dipol auf blaue Linie
stellen
CSTI
12.
Komponenten
vorjustieren
CSTI
5.
Quadrupol auf blaue
Linie stellen
CSTI
16.
Maschinennahe
Trassen mont. und
Kleinsignalka. aufl.
LOEP
36.
Brandschutzwände
montieren
FSB
1.
Blaue Linien
anbringen
ENMA
37.
BLM‘smontieren +
verkabeln
CSBI
6.
Sammelgestelle (mit
Komponenten) auf
blaue Linie stellen
CSTI
3.
Einbringung Beam
Dump
SI
2.
Einbau Transport-
vorrichtungschiefe
Ebene
CSTI
35.
Mobile
Abschirmwände
stellen
FSB
7.
Steererauf blaue
Linie stellen
CSTI
8.
BI Komponenten
auf blaue Linie
stellen
CSTI
9.
SI Komponenten
auf blaue Linie
stellen
CSTI
10.
Vakuumkomponen-
tenauf blaue Linie
stellen
CSTI
26.
Wasserkreisläufe:
Dichtigkeit prüfen,
Inbetriebnahme
CSTI
21.
Magnetkabel
konfektionieren und
anschließen
LOEP
20.
Magnete Polarität
prüfen
ENMA
3.1
BI Komponenten
auf blaue Linie
stellen
CSTI
3.3
BI Komponenten
vorjustieren
ENMA
3.2
Vakuumkomponen-
tenauf blaue Linie
stellen
CSTI
3.4
Vakuumkompo-
nentenvorjustieren
ENMA
3.5
Mobile
Abschirmwände
stellen
FSB
3.6
DumpGrube
verschließen
(Brammen auflegen)
FSB
11.
Sonstige
Komponenten auf
blaue Linie stellen
CSTI
13.
Vorschließen
Vakuumsystem
CSTI
24.
Vakuum Anpumpen/
Lecktest
CSVS
22.
BI-Kabel
konfektionieren und
anschließen
CSBI
23.
Vakuum-Kabel
konfektionieren und
anschließen
CSVS
25.
SI-Kabel
konfektionieren und
anschließen
SI
19.
Wassergekühlte
Geräte: Schläuche
anschließen
CSTI
27.
Pressluft:
Anschluss,
Inbetriebnahme
CSTI
28.
Detektorgasvers.für
BI; Anschluss,
Inbetrieb.
CSBI
29.
Inbetriebnahme
Power Converter &
Magnete
ENMA & LOEP
30.
Inbetriebnahme
Beam
Instrumentation
CSBI
31.
Inbetriebnahme
Vakuum
CSVS
32.
Inbetriebnahme
Special Installations
SI
Montage der
Beschleunigerkomponenten
zusätzlichfürG004
14.
Komponenten
feinjustieren
ENMA
18.
Mediennahe
Wasserverso. und
Wasservert. setzen
CSTI
33.
Inbetriebnahme
Kontrollsystem
CSCO
Abschluß
arbeiten
2.14.10
Controls
CSCO
R. Bär
34.
Komponenten
feinjustieren
ENMA
15.
Endgültiges
Schließen
Vakuumsystem
CSTI
2.3.0.3.
DMU
ENMI
L. Heyl
17.
As buildin DMU
Model übernehmen
ENMA

## Slide 26
Montageplanung HEBT
Versorgungsgebäude
Stand: 01.11.2016
2.14.12
Installations/
Assembly
CSTI
M. Bevcic
2.14.9.8
Alignment
ENMA
I. Pschorn
2.3.3
Power Converter
LOEP
H. Welker
2.3.6
Beam Instru-
mentation(BI)
CSBI
B. Walasek-H.
3
Building
infrastructure
FSB
A. Fischer
2.3.11
Special
Installations
SIS18/SIS100(SI)
L. Bozyk
Arbeitspakete / Zuständigkeiten
2.3.2.
Magnets
ENMA
C. Mühle
2.3.7
Vacuumsystems
CSVS
L. Urban
Anschluss
Komponenten
4.
Power Converter
und Netzgeräte
aufstellen
LOEP
7.
SI Racks
aufstellen und
bestücken
SI
8.
Vakuum Racks
aufstellen und
bestücken
CSVS
17.
Primärkabel an
Racks anschließen
FSB
Aufstell-
ung
Abschluß
arbeiten
2.14.10
Controls
CSCO
R. Bär
1.
Doppelboden mit
provisorischen
Platten schließen
FSB
2.
Unterverteilung
NSHV aufstellen
und anschließen
FSB
3.
Montage
Umluftkühlgerätefür
Druckbelüftung
FSB
5.
Control Racks
aufstellen und
bestücken
CSCO
9.
Sonstige
Komponenten
aufstellen
NN
6.
BI Racks
aufstellen und
bestücken
CSBI
10.
Power Converter
Kabelkonfektionieru
ng und Kabeltests
LOEP
11.
Controls-Kabel
konfektionieren
und Kabeltests
CSCO
12.
BI Kabel
konfektionieren
und Kabeltests
CSBI
13.
SI Kabel
konfektionieren
und Kabeltests
SI
14.
Vakuum-Kabel
konfektionieren
und Kabeltests
CSVS
15.
Sonstige Kabel
konfektionieren
und Kabeltests
NN
16.
Potentialausgleichs-
schienen für alle
Racks anschl.
LOEP
19.
Kühlwasser an
Racks anschließen,
füllen, entlü., spülen
LOEP
21.
Interlock-und
Controls-Kabel
anschließen
LOEP+CSCO
22.
BI Kabel
anschließen
CSBI
23.
SI Kabel
anschließen
SI
24.
Vakuum-Racks
anschließen
CSVS
25.
Brandmelder im
Doppelboden
montieren
FSB
26.
Brandschotts
schließen
FSB
27.
Doppelbodenplatten
durch endgültige
Platten tauschen
FSB
18.
Nutzertrafos
anschließen
LOEP
20.
Kühlwasser an H2O-
Kabel anschließen
LOEP
28.
Inbetriebnahme
Control
CSCO
29.
Inbetriebnahme
Power Converter
LOEP
30.
Inbetriebnahme
BI
CSBI
31.
Inbetriebnahme
SI
SI
32.
Inbetriebnahme
Vakuum
CSVS
33.
Inbetriebnahme
restliche
Komponenten
NN
Inbetrieb-
nahme