## Slide 1: Super-FRS hardware commissioning
Preparation, Status, Schedule and Resources
Stephane Pietri, SFS

## Slide 2: Super-FRS Commissioning
Some introduction
Sectioning
Systems
Status of planning
Next steps
Thoughts for the next phases

## Slide 3: Super-FRS – general overview
FHF2, HEB cave,
R3B NUSTAR
Main separator
Pre-separator
Target area
Pre-target
Focusing system
Supply building,
lab, control room
Ring branch, not ES
Super-FRS stands for
Super FRagment Separator
Super for super conducting
Low Energy Branch
not ES

## Slide 4: Objective of Super-FRS commissioning
Main goal of Super-FRS: select and identify ions produced in nuclear reactions at the target.
Final goal of the Super-FRS commissioning: show we can select and identify ions with it.
Confirm something like
this 
Z of particle
AoQ of particle
Data from
FRS

## Slide 5: Super-FRS: Super FRagment Separator
238U from SIS18 on target to produce 212Pb, 238U+12C@1 GeV.A  212Pb
This is what is produced
at the target (yield)
3000+ isotopes
we need to select
the one we want

## Slide 6: Super-FRS: Super FRagment Separator
238U from SIS18 on target to produce 212Pb, 238U+12C@1 GeV.A  212Pb
50 most produced ones
 red is 212Pb

## Slide 7: Super-FRS: Super FRagment Separator
238U from SIS18 on target to produce 212Pb, 238U+12C@1 GeV.A  212Pb
At HEB after selection

## Slide 8: Magnets – size and constrain
Need large magnets to accept as much in momentum (40 cm openings)
This means the inductance is quite high (good for machine protection…)

## Slide 9: Magnets – size and constrain
Need large magnets to accept as much in momentum (40 cm openings)
This means inductance quite high (good for machine protection…)
This means need more order correction – quite a variety of multiplet

## Slide 10: Complexity due to target
high radiation, target complexity
all elements encased in a
steel “sarcophagi”
limit access, only one vacuum
section
this is special for
commissioning and installation

## Slide 11: Complexity due to cryogenics
Cryogenics distribution not based on functional sections
Local cryogenics: depends on general cryogenics and deliveries
Phase 2 commissioning Super Conducting Magnets after local cryogenics commissioning
Dependency:
Magnet commissioning
phase 2 after cool down
per section
but P/M/H cooled
down at once

## Slide 12: Complexity due to detectors
Main goal of detectors in the spectrometer: identification particle per particle for the experiments (detectors part of experiment)
Detectors needed also for:
  beam steering
  characterization of ion optics
  intensity monitoring
Constrain: size of focal planes
 heterogeneity of focal planes
Note: detectors in yellow are read
out with experimental acquisition,
separate network

## Slide 13: Scope (elements) of commissioning
Goal commissioning: reach FHF2 (commission the full HEB line)

## Slide 14: FHF2

## Slide 15: Commissioning include last multiplet at FHF2
FHF2 is in HEB, in front of the R3B experiments
SFRS multiplet
beam reach here during SFRS beam commissioning

## Slide 16: Commissioning phases, sections goal
Need sectioning to breakdown the work
Allows to plan parallel installation work and/or commissioning work
First idea: functional sections, Magnets then diagnostics
Goal commissioning: reach FHF2 (commission the full HEB line)

## Slide 17: System list
SCM: Super Conducting Magnets
NCM: Normal Conducting Magnets (target area)

## Slide 18: Commissioning phases, sections for phases 1/2 and 3/4
Phase 1 sections different

## Slide 19: Phase of commisining
Phase 1: hardware commissioning (after mechanical completion)
Phase 2: remote commissioning
Phase 3.1: integration test
Phase 3.2: dry run (SAT Ba/M11)
Phase 4: beam commissioning (SAT Bb/M12)
          (note, beam can be reasonably high intensity at the end)

## Slide 20: Commissioning phases, sections
for phase 1 (local) and 2 (remote):
  component in sections following assembly unit
  vacuum and cryo own section
  special treatment for target area (more on this later)
for phase 3.1 (integration), 3.2 (dry run) and 4 (beam)
  sections are based on functional sectioning (or focal planes)

## Slide 21: Status of planning - LCM
LCM approach for phase 1 and 2 status (co-organized by M. Cabioch)
clear dependency and requirements
reduced number of people in meetings
goal resource loaded schedule by early spring 2025

## Slide 22: Status of planning,Target area
Example target area

## Slide 23: Status of planning, Target area
Example target area

## Slide 24: Status of planning, Target area
Example target area

## Slide 25: Status of planning, Target area
Example target area
Close steel roof: is a fixed time from
installation planning (many other dependencies)

## Slide 26: Status of planning, Target area
Example target area

## Slide 27: Status of planning, Target area
Example target area

## Slide 28: Status of planning, Beam diagnostic chambers
suppose VAC phase 2 done
pressured air, power for motor drive
and patch panel connection
pressured air, power for motor drive
and patch panel connection

## Slide 29: Learn from LCM – effect of dependencies on planning
Beam diagnostic need Vacuum commissioning to phase 2 to start phase 1
Super Conducting Magnets needs phase 2 of Local Cryo (and cool down) to do to phase 2
Target area has a long “installation” activity in the middle of its phase 1 commissioning (affects Target area and Normal Conducting Magnets)

## Slide 30: General planning, top to bottom
first planning from installation plan
2024 start installation, 2025 ramp up installation, 2026 finish installation
2025 start commissioning, 2026 ramp up commissioning, 2027 beam commissioning

## Slide 31: First simulations – toy model
Current planning resource estimate (not fully LCM but taking results into account)

## Slide 32: Section, element, complexity of elements
SaTBb is end dryrun

## Slide 33: Full .xls document

## Slide 34: First simulations – toy model

## Slide 35: Results in Planisware
Consolidate Planisware, cooling? hypothesis Mar 27?

## Slide 36: Example of detail

## Slide 37: Example of details – vacuum installation
Thanks to Marina Gorda for implementing all the complexity!

## Slide 38: First test of commissioning
Installation started this year, commissioning starts next year
first commissioning: Vacuum pre target area

## Slide 39: Future plan, phase 1 and 2
finish the LCM workshop and resource collection
consolidate sequencer operation for commissioning
organize teams for commissioning, hardware (phase 1 and phase 2)
objective : having 2 teams for VAC, SCM and BeamDiagnostic + pool of experts we can pull if needed (eg, collaborators, ext. partners) which can go along the beam line
Target and Normal Conducting Magnets are more localized
Cryogenics organization: under discussion

## Slide 40: From phase 3.1 to 4
higher level expertise will be needed (harder to plan with general ressources):
  SFRS EXP DAQ coupling of detectors to experiment, very few people can do it (6 people at GSI+ 2 outside)
  integration to higher level control system  need support from ACO
phases ran from NUSTAR control room (SFRS room):
  closer access
  close to our labs
  modern solutions we can
  easily interact with FAIR
  control room
E20.008
NUSTAR
E20.009
SFRS control
L0321A ( G006a)
13 m

## Slide 41: Beam commissioning
goal of beam commissioning (coarse):
  test beam instrumentation
  check, measure ion optic parameters
   for defining details we are establishing a “commissioning working group” to discuss exchange ideas on the topic (SFS/SFC)
beam requirement:
  SIS18 slow extraction, 1 to 5 s
  12 to 18 Tm
  light to medium and then heavy  example Ar, Sn and Pb/U
  1e4 particle per spill to 1e8 particle per spill (end of commissioning highest intensity possible)
  we could (low probability) have to go back to lighter
  for final beam commissioning: 238U (or agreement with NUSTAR)
  if sharing, and everything works, block mode
  beam emittance requirement on the final beam instrumentation tests and for ion optic

## Slide 42: End of beam commissioning
Check identification from Spectrometer with Isomer Tagging
request to NUSTAR to provide a setup for this
 follows return of experience from FRIB (USA) and BigRiPS (JP) commissioning

## Slide 43: Phase 3.1, 3.2 and 4 commission, some thoughts
Risk/opportunities (organization)
  presently all high end single particle tracking detector read in experimental network and all magnet control in accelerator network:
    Super-FRS EXP DAQ (PSP 2.4.6.3.1.2), data source different format/network from ACC/BEA
    we need a solution to permit automatic/advanced beam tunning for ease and speed of operation
    until solution not present man power can not be engaged in development
    from 2026 man power will be occupied in commissioning
    ….. Ralph is aware… but still something we really need soon

## Slide 44: Super-FRS and NUSTAR
Link NUSTAR
  need support for isomer tagging at FHF2 from NUSTAR
  clear channel of communication, through Helena Albers for NUSTAR requests
  final setting of our commissioning should open the first experiment done together with NUSTAR
   then Early Science can start

## Slide 45: Idea learnt from CERN visit
Picket vs “on call”
  on-call: waits for a call
  picket has an active role  monitors the system
Request would be picket for critical system during beam commissioning
  CRY, VAC, Controls…
rotating coordinators, option for long beam time
  same goal, same objectives
  goal of the week given/designed clearly

## Slide 46: Commissioning organization, ideas (to be discussed)
Phase 1, 2
  system responsible, responsible for commissioning
    up to two team working in parallel per system
  coordination from commissioning teams
Phase 3, 4
  commissioning more centrally managed
  use of sequencer where possible
  for beam operation (plan several months), rotating coordinator, daily report
    weekly objective
    team/operation in shifts (with shift leader)
    we expect people have the same goal at hand

## Slide 47: Last thought
Super-FRS commissioning will be a interesting culture mix:
  Nuclear Experimental Physics (SFS)
  Support from operation/machine oriented physicists (SFC/ commissioning team)
  some reporting (QUA.. PMO)
…. let’s try to learn from each others!

## Slide 48
My thanks to:
Seva Kamerdzhiev, Marie Cabioch, Marina Gorda, Stephan Reimann,
Heike Marcocelli, Valentina Ricciardi.

## Slide 49: plans
plan your work and work you plan!!!
Installation Readiness Release (Desy)
Components detail (ESS)

## Slide 50
Local Cryogenics Branches

## Slide 51
Commissioning need to be done in parallel to installation (as much as possible)
Integration test could be done “per installation block”  main question: Cryo commissioning (no info possible)!

## Slide 52
Assembly Units
Installation: Super-FRS
Installation: NUSTAR
LM_01
LM_02
DC_01
LM_03
TA
NC_QQ
NC_QS
NC_D1
NC_D2
NC_D3
BC1
BC2
BC3
SM_01
SM_03
SM_02
DC_02
SM_04
SM_05
SM_06
SM_07
FTF1
FPF0
FPF1
FPF2
FPF3
FPF4
FMF1
FMF2
FMF3
FRF1
DC_18
FRF2
FRF3
DC_19
DC_20
FHF1
FLF1
DC_10
DC_11
DC_12
DC_13
DC_14 (maybe)
FLF2
FLF3
FLF4
DC_15
FLF5
DC_16
FLF6
DC_17
DC_09
DC_07
DC_03
DC_04
DC_05
DC_08
DC_06
SCD_01
SCD_02
SCD_03
LM_04
LM_05
SCD_04
SCD_05
SCD_06
LM_06
SCD_07
SCD_08
SCD_09
LM_07
LM_08
LM_09
SCD_10
SCD_11 (branch)
SCD_12
LM_10
LM_11
FHF2
FHF3
LM_12
LM_13
GLAD
SCD_13
LM_14
LM_15
LM_16
LM_17
LM_18
LM_19
LM_20
LM_21
LM_22
LM_23
SCD_14 (branch)
SCD_15
SCD_16
SCD_17
SCD_18
SCD_19
SCD_21
SCD_20
SCD_22
SCD_23 (branch)
SCD_24
EBM_01
EBM_02
EBM_03
EBM_04
EBM_05
EBD_01
EBD_02
EBD_03
VAC_02
VAC_07
VAC_08
VAC_10
VAC_11
VAC_03
VAC_04
VAC_ NUSTAR
VAC_01
VAC_09
BDN
VAC_05
VAC_06
NC_S
Last modified: Super-FRS Workshop, 15-17 Nov. 2021
SM sc short multiplet
LM sc long multiplet
SCD sc dipole
DC diagnostic chamber
VAC beam-line vacuum
EBD EB dipole
EBM EB multiplet
Installation: Super-FRS
Installation: NUSTAR
beam
Assembly Units along the beamline
early science locations
Fxxx notation defines “focal planes”
TA target
NC_QQ nc quadr. 1a + quadr. 1b
NC_QS nc quadr. 2 + sextupole
NC_D nc dipole
BC beam catcher
NC_S nc sextupole
7 sc short multiplets
13 sc long multiplets
15 sc dipoles
10 diagnostic chambers (DC_01 not includable)
4 long/special beam pipes
Number of pieces for Early Science
(Target Area excluded)
4 sc long multiplets
3 sc dipoles
2-3 diagnostic chambers
1 long/special beam pipes
Additional number of pieces for LEB (up to FLF3)
6 sc long multiplets
6 sc dipoles
6 diagnostic chambers
6 long/special beam pipes
5 sc Energy Buncher multiplets
3 sc Energy Buncher dipoles
Additional number of pieces for completion
Power converter Racks (total) 77
Control Racks (total) 336
not ATB

## Slide 53
G018
T103
G006A
FTF1
Commissioning sections along the beamline v1
T103
G006B
G006
beam
sections for commissioning
blocks for machine installation
FPF0
FPF1
FPF2
FPF3
FPF4
FMF1
FMF2
FMF3
FRF1
FRF2
FRF3
FLF1
FHF1
FHF2
FLF2
FLF3
FLF4
FLF5
FLF6
All this is LEB
commissioned together

## Slide 55: Local Cryogenics branches M, H, G (B optional)
Procurement and installation branch M
Procurement and installation branches H, G
Planned FAIR contracts: December 2024
Planned delivery to FAIR: October 2025 – July 2026
Planned installation: October 2025 – August 2026
shielded target area
T
P1
P2
M1
M2
M3
H
G
11.25
11.25
04.26
09.26
04.26
08.25
batch M3 07.26
batch M2 02.26
batch M1 10.25
batch W2 09.25
batch W1 06.25
batch H 02.26
batch G 05.26
05.26
last batch W0 Dec-24
Delivery dates of local cryogenics boxes
Local cryogenics sectors: installation completed
03.25
Tender running
Deadline for offers: 23/10/2024
Offers from 4 bidders (3 companies + 1 consortium)
All qualified and well-known companies
Requested schedule confirmed
Negotiations starting
Risk of FAIR internal competition with cryo tenders
Overview tenders LC branches
CE
Still to be tendered: jumpers of branches M, H, G

## Slide 57: Super-FRS – NUSTAR : no coupling hypothesis
SFRS runs “isomer tagger” at FHF2 during its commissioning
last setting is an “isomer tagger” for NUSTAR experiment
remove isomer tagger
install NUSTAR setup
☺ | ☹
Clear separation of goals | not nice in spirit of cooperation
Low man power need from NUSTAR side (short period) | Still need to tune implantation after Super-FRS commissioning
Limited risk to damage NUSTAR unique equipment | Still need to do the NUSTAR in beam commissioning (only one region or full rescalling)
SFRS
NUSTAR

## Slide 58: Super-FRS – NUSTAR: high coupling hypothesis
if several beams, to better characterize detector, several small experiments(?)
as soon as we are “safe” in beam handling, we could move in NUSTAR setup
perform small measurement along the different beams while going up in Z (supposing we start light and end up heavy)
☺ | ☹
Much more NUSTAR-SFRS integration | Could generate conflicts on goal
NUSTAR setup properly commissioned in beam during SFRS commissioning | Higher risk to damage unique equipment (but can be mitigated easily)
 | Long NUSTAR beam period, with idle times where SFRS does pure SFRS stuff
 | Not all beams with NUSTAR will yield interesting results?
SFRS
NUSTAR

## Slide 59: Super-FRS NUSTAR – mid coupling hypothesis
Super-FRS perform its commissioning
when confident we remove isomer tagger and start NUSTAR beam commissioning hand in hand with Super-FRS last points of commissioning
Super-FRS commissioning end at the last setting for Super-FRS/first setting for NUSTAR, then NUSTAR experiment begings (in beam commis. already done)
SFRS
NUSTAR
☺ | ☹
Much more NUSTAR-SFRS integration | 
NUSTAR setup properly commissioned in beam during SFRS commissioning | (minor): need some agreement on process at the end of Super-FRS commissioning
Lower man power impact for NUSTAR than strong coupling | 
Reduced risk for NUSTAR experiment compared to other options | 

## Slide 60: Open points
Would define “we finished beam commissioning of SFRS and NUSTAR here we do first experiment” be good? Or is “the first NUSTAR experiment is the end of the Super-FRS commissioning?” (first case was my assumption)
I would suggest to check feasibility of first NUSTAR experiment with Super-FRS expert, to avoid a too risky experiment
Once NUSTAR setup is better defined the discussion can start of how we couple the two commissioning (from which moment we rely on the NUSTAR setup and remove our small isomer tagger, if some light beam for tracking detectors need to be tested etc…) and what shall be done for the NUSTAR in beam commissioning
For information: we just started the discussions on the Super-FRS “no-beam” commissioning in the project side (so no urgency!)

## Slide 61
End slide

## Slide 62: Why isomer tagging is preferred for SFRS com.1
5 options: counting, beta, alpha, mass, isomer tagging
  counting: (step by step from Primary beam), not efficient if long jump, always a backup
  beta: life time with error not unique finger print, end point measurement can be confusing if several decays (isomer/gs) and need a lot of statistics
  alpha: quite rare in the chart, energy and life time are unique fingerprint, but fast alpha decay make spectra confusing if spectrometer tuned far away of where it is believed
  mass: unique finger print, main issue implantation in a very thin matter, extraction, then mass measurement, when all works fine it is perfect, but many steps that can go wrong, and if the setting is not the one though, the implantation will not work, nice to confirm on an establish setup, maybe not for shooting in the dark…
  isomer: quite unique finger print, more open the setting better (contrary to 2/3/4), implantation can be done quite surely (thick plate), direct correlation between ion and gamma, not a multi step process, best when shooting in the dark
1: This of course does not constrain in anyway the options for NUSTAR first science