## Slide 1: Super-FRS requirement to controls for commissioning

## Slide 2: Objective of Super-FRS commissioning
Main goal of Super-FRS: select and identify ions produced in nuclear reactions at the target.
Final goal of the Super-FRS commissioning: show we can select and identify ions with it.
Confirm something like
this Nov 2027 
Z of particle
AoQ of particle
Data from
FRS

## Slide 3: Scope (elements) of commissioning
Goal commissioning: reach FHF2 (commission the full HEB line)

## Slide 4: FHF2

## Slide 5: General planning, top to bottom
first planning from installation plan
2024 start installation, 2025 ramp up installation, 2026 finish installation
2025 start commissioning, 2026 ramp up commissioning, 2027 beam commissioning

## Slide 6: Phase of commisining
Phase 1: hardware commissioning (after mechanical completion)
Phase 2: remote commissioning
Phase 3.1: integration test
Phase 3.2: dry run (SAT Ba/M11)
Phase 4: beam commissioning (SAT Bb/M12)
          (note, beam can be reasonably high intensity at the end)

## Slide 7: Commissioning phases, sections goal
Need sectioning to breakdown the work
Allows to plan parallel installation work and/or commissioning work
Goal commissioning: reach FHF2 (commission the full HEB line)

## Slide 8: System list
SCM: Super Conducting Magnets
NCM: Normal Conducting Magnets (target area)

## Slide 9: Status of planning, Beam diagnostic chambers
suppose VAC phase 2 done
pressured air, power for motor drive
and patch panel connection
pressured air, power for motor drive
and patch panel connection

## Slide 10: Full .xls document

## Slide 11: First simulations – toy model

## Slide 12: Requirement
From phase 2 of commissioning:
  Network infrastructure
  FESA control
From phase 3.1
  higher tier applications
  LSA
As soon as possible
  DAQ coupling so we can prepare commissioning applications
  posiblity to have simple interface (python) for “ad hock” implementation

## Slide 13: Requirement per system
Target area
  for phase 2
     IND, VAC control
     Phytron controller
  for phase 3
    implementation of higher level control for beam catcher, target and magners
Normal Conducting magnets
  for phase 2
    network
    timing
    FESA

## Slide 14: Requirement per system
Beam line vaccum
  Phase 2: VAC control system
Cryogenics (LCM in progress)
  phase 2: CRY control system
Super Conducting Magnets
  phase 2:
    Quench Detection subnet ready
    FESA class present
    timing
    network

## Slide 15: Requirement per system
Beam diagnostic
  phase 2:
    network
    timing
    FESA server
Super-FRS machine model needed for phase 3.1
Super-FRS ACO DAQ coupling will be tested for phase 3.1
  BUT: need way to develop based on the protocol BEFORE

## Slide 16: System list
Need some custom applications ready for 2027,
Learning curve for ACO application development, 4 to 6 months
No man power before 6 months at best
 start to be short!

## Slide 17: Super-FRS requirements, color scheme
safe, will happen or mitigating actions existing
normal
mission critical request or high concern about this being present in time (based on my current knowledge)

## Slide 18: Super-FRS Machine model– link to D. Ondreka
FRS machine model ready and running, includes matter
Need to be ported at Super-FRS
  two operation modes (ready)
    user sets Brho per section (like FRS)
    machine model takes care of matter calculation (need proper matter database and matter calibration) – drives moved from Paramodi
  Goal, PhD student joining late 2025, so time to implement in 2026 and person is present for commissioning/ES operation in 2027

## Slide 19: Super-FRS requirement – to ACO
Vacuum and cryogenic control possible from NUSTAR control room
Vacuum controls allowing experiment installation
PARAMODI
  save and load settings
  save part of beam line/load part of beam line
  save all information, no hidden trim not saved
Ist/soll comparison application
Different classes of users (Expert/operators/physicists)
Machine Protection that allows us to have drives in during beam time
Integration interlock from experiments (lines) and across systems

## Slide 20: Super-FRS specific application (I) – CSG prio 1
FESA class for Phytron motors (5 drives)
 development done, test next week
Open point: integration to higher tier of the control system (Device control etc..)
Super-FRS integration of Stray filed handling in trajectory control
 use of Benno to be checked with Super-FRS magnets and beam dynamics experts
Super-FRS MAGSTAT/DRIVESTAT
  need to be ported from FRS to Super-FRS, (0.5 FTE),
  need to shows easily longer beam line for easier monitoring

## Slide 21: Super-FRS specific application (II) – CSG prio 1
Super-FRS CS-DAQ coupling
 concept ready since 2014
 needed for any sequencer/automatic calibration during commissioning
 we understand “general one solution for all FAIR pillars” would be nice but we can not wait everybody aligns. Our requirement are written since 2015!
 alternative, ssh tunneling?
Super-FRS MGSKAL:
based on sequencer, used to cycle the magnet through hysteresis, long for FRS (2 min), Super long (~15 min) for Super-FRS
Facility control: Gas system control

## Slide 22: Super-FRS specific application (IV) – CSG, prio 2
Setting Validation System
  current FRS operation LISE simulation, set Brho per section, check dangerous setting from simulation
  Super-FRS, more focal planes, 2 hours for each simulation
  Goal: intercept request from operator, check danger, allow/warming/forbhid change
  then sends information to Paramodi (.txt file or different)
  2 tasks:
    nuclear physics task optimize speed of simulation
    interface from application to Paramodi
Software Interlock System
  based on simulation (see point above) check if rate is what is expected at focal plane
  need interface CS-DAQ, could be developed

## Slide 23: Super-FRS specific application (non CSG)
Field control from NMR probes (to avoid long cycling magnet procedure)
  need discussion on implementation
  man power needed in Super-FRS group (< 1 FTE)
LISE setting to Paramodi conversion (small application)
General view/monitoring of spectrometer
  question is how to simply monitor 150+ magnets and 60 beam device, Device control need several screens
Sequencer APP coupled with CS-DAQ coupling for automatic mater calibration (and detector calibration)

## Slide 24: Conclusion - outlook
need quite a lot of integration between ACO and SFRS for commissioning
currently every two weeks meeting with Ralph, Ralf, Frederic, Christine and me
for commissioning having a “ACO contract” for SFRS who follows the issues will be welcome

## Slide 25: First test of commissioning
Installation started this year, commissioning starts next year
first commissioning: Vacuum pre target area

## Slide 26: Future plan, phase 1 and 2
finish the LCM workshop and resource collection
consolidate sequencer operation for commissioning
organize teams for commissioning, hardware (phase 1 and phase 2)
objective : having 2 teams for VAC, SCM and BeamDiagnostic + pool of experts we can pull if needed (eg, collaborators, ext. partners) which can go along the beam line
Target and Normal Conducting Magnets are more localized
Cryogenics organization: under discussion

## Slide 27: From phase 3.1 to 4
higher level expertise will be needed (harder to plan with general ressources):
  SFRS EXP DAQ coupling of detectors to experiment, very few people can do it (6 people at GSI+ 2 outside)
  integration to higher level control system  need support from ACO
phases ran from NUSTAR control room (SFRS room):
  closer access
  close to our labs
  modern solutions we can
  easily interact with FAIR
  control room
E20.008
NUSTAR
E20.009
SFRS control
L0321A ( G006a)
13 m

## Slide 28: Beam commissioning
goal of beam commissioning (coarse):
  test beam instrumentation
  check, measure ion optic parameters
   for defining details we are establishing a “commissioning working group” to discuss exchange ideas on the topic (SFS/SFC)
beam requirement:
  SIS18 slow extraction, 1 to 5 s
  12 to 18 Tm
  light to medium and then heavy  example Ar, Sn and Pb/U
  1e4 particle per spill to 1e8 particle per spill (end of commissioning highest intensity possible)
  we could (low probability) have to go back to lighter
  for final beam commissioning: 238U (or agreement with NUSTAR)
  if sharing, and everything works, block mode
  beam emittance requirement on the final beam instrumentation tests and for ion optic

## Slide 29: End of beam commissioning
Check identification from Spectrometer with Isomer Tagging
request to NUSTAR to provide a setup for this
 follows return of experience from FRIB (USA) and BigRiPS (JP) commissioning

## Slide 30: Phase 3.1, 3.2 and 4 commission, some thoughts
Risk/opportunities (organization)
  presently all high end single particle tracking detector read in experimental network and all magnet control in accelerator network:
    Super-FRS EXP DAQ (PSP 2.4.6.3.1.2), data source different format/network from ACC/BEA
    we need a solution to permit automatic/advanced beam tunning for ease and speed of operation
    until solution not present man power can not be engaged in development
    from 2026 man power will be occupied in commissioning
    ….. Ralph is aware… but still something we really need soon

## Slide 31: Super-FRS and NUSTAR
Link NUSTAR
  need support for isomer tagging at FHF2 from NUSTAR
  clear channel of communication, through Helena Albers for NUSTAR requests
  final setting of our commissioning should open the first experiment done together with NUSTAR
   then Early Science can start

## Slide 32: Idea learnt from CERN visit
Picket vs “on call”
  on-call: waits for a call
  picket has an active role  monitors the system
Request would be picket for critical system during beam commissioning
  CRY, VAC, Controls…
rotating coordinators, option for long beam time
  same goal, same objectives
  goal of the week given/designed clearly

## Slide 33: Commissioning organization, ideas (to be discussed)
Phase 1, 2
  system responsible, responsible for commissioning
    up to two team working in parallel per system
  coordination from commissioning teams
Phase 3, 4
  commissioning more centrally managed
  use of sequencer where possible
  for beam operation (plan several months), rotating coordinator, daily report
    weekly objective
    team/operation in shifts (with shift leader)
    we expect people have the same goal at hand

## Slide 34: Last thought
Super-FRS commissioning will be a interesting culture mix:
  Nuclear Experimental Physics (SFS)
  Support from operation/machine oriented physicists (SFC/ commissioning team)
  some reporting (QUA.. PMO)
…. let’s try to learn from each others!

## Slide 35
My thanks to:
Seva Kamerdzhiev, Marie Cabioch, Marina Gorda, Stephan Reimann,
Heike Marcocelli, Valentina Ricciardi.

## Slide 36: plans
plan your work and work you plan!!!
Installation Readiness Release (Desy)
Components detail (ESS)

## Slide 37
Local Cryogenics Branches

## Slide 38
Commissioning need to be done in parallel to installation (as much as possible)
Integration test could be done “per installation block”  main question: Cryo commissioning (no info possible)!

## Slide 39
Assembly Units
Installation: Super-FRS
Installation: NUSTAR
LM_01
LM_02
DC_01
LM_03
TA
NC_QQ
NC_QS
NC_D1
NC_D2
NC_D3
BC1
BC2
BC3
SM_01
SM_03
SM_02
DC_02
SM_04
SM_05
SM_06
SM_07
FTF1
FPF0
FPF1
FPF2
FPF3
FPF4
FMF1
FMF2
FMF3
FRF1
DC_18
FRF2
FRF3
DC_19
DC_20
FHF1
FLF1
DC_10
DC_11
DC_12
DC_13
DC_14 (maybe)
FLF2
FLF3
FLF4
DC_15
FLF5
DC_16
FLF6
DC_17
DC_09
DC_07
DC_03
DC_04
DC_05
DC_08
DC_06
SCD_01
SCD_02
SCD_03
LM_04
LM_05
SCD_04
SCD_05
SCD_06
LM_06
SCD_07
SCD_08
SCD_09
LM_07
LM_08
LM_09
SCD_10
SCD_11 (branch)
SCD_12
LM_10
LM_11
FHF2
FHF3
LM_12
LM_13
GLAD
SCD_13
LM_14
LM_15
LM_16
LM_17
LM_18
LM_19
LM_20
LM_21
LM_22
LM_23
SCD_14 (branch)
SCD_15
SCD_16
SCD_17
SCD_18
SCD_19
SCD_21
SCD_20
SCD_22
SCD_23 (branch)
SCD_24
EBM_01
EBM_02
EBM_03
EBM_04
EBM_05
EBD_01
EBD_02
EBD_03
VAC_02
VAC_07
VAC_08
VAC_10
VAC_11
VAC_03
VAC_04
VAC_ NUSTAR
VAC_01
VAC_09
BDN
VAC_05
VAC_06
NC_S
Last modified: Super-FRS Workshop, 15-17 Nov. 2021
SM sc short multiplet
LM sc long multiplet
SCD sc dipole
DC diagnostic chamber
VAC beam-line vacuum
EBD EB dipole
EBM EB multiplet
Installation: Super-FRS
Installation: NUSTAR
beam
Assembly Units along the beamline
early science locations
Fxxx notation defines “focal planes”
TA target
NC_QQ nc quadr. 1a + quadr. 1b
NC_QS nc quadr. 2 + sextupole
NC_D nc dipole
BC beam catcher
NC_S nc sextupole
7 sc short multiplets
13 sc long multiplets
15 sc dipoles
10 diagnostic chambers (DC_01 not includable)
4 long/special beam pipes
Number of pieces for Early Science
(Target Area excluded)
4 sc long multiplets
3 sc dipoles
2-3 diagnostic chambers
1 long/special beam pipes
Additional number of pieces for LEB (up to FLF3)
6 sc long multiplets
6 sc dipoles
6 diagnostic chambers
6 long/special beam pipes
5 sc Energy Buncher multiplets
3 sc Energy Buncher dipoles
Additional number of pieces for completion
Power converter Racks (total) 77
Control Racks (total) 336
not ATB

## Slide 40
G018
T103
G006A
FTF1
Commissioning sections along the beamline v1
T103
G006B
G006
beam
sections for commissioning
blocks for machine installation
FPF0
FPF1
FPF2
FPF3
FPF4
FMF1
FMF2
FMF3
FRF1
FRF2
FRF3
FLF1
FHF1
FHF2
FLF2
FLF3
FLF4
FLF5
FLF6
All this is LEB
commissioned together

## Slide 42: Local Cryogenics branches M, H, G (B optional)
Procurement and installation branch M
Procurement and installation branches H, G
Planned FAIR contracts: December 2024
Planned delivery to FAIR: October 2025 – July 2026
Planned installation: October 2025 – August 2026
shielded target area
T
P1
P2
M1
M2
M3
H
G
11.25
11.25
04.26
09.26
04.26
08.25
batch M3 07.26
batch M2 02.26
batch M1 10.25
batch W2 09.25
batch W1 06.25
batch H 02.26
batch G 05.26
05.26
last batch W0 Dec-24
Delivery dates of local cryogenics boxes
Local cryogenics sectors: installation completed
03.25
Tender running
Deadline for offers: 23/10/2024
Offers from 4 bidders (3 companies + 1 consortium)
All qualified and well-known companies
Requested schedule confirmed
Negotiations starting
Risk of FAIR internal competition with cryo tenders
Overview tenders LC branches
CE
Still to be tendered: jumpers of branches M, H, G

## Slide 44: Super-FRS – NUSTAR : no coupling hypothesis
SFRS runs “isomer tagger” at FHF2 during its commissioning
last setting is an “isomer tagger” for NUSTAR experiment
remove isomer tagger
install NUSTAR setup
☺ | ☹
Clear separation of goals | not nice in spirit of cooperation
Low man power need from NUSTAR side (short period) | Still need to tune implantation after Super-FRS commissioning
Limited risk to damage NUSTAR unique equipment | Still need to do the NUSTAR in beam commissioning (only one region or full rescalling)
SFRS
NUSTAR

## Slide 45: Super-FRS – NUSTAR: high coupling hypothesis
if several beams, to better characterize detector, several small experiments(?)
as soon as we are “safe” in beam handling, we could move in NUSTAR setup
perform small measurement along the different beams while going up in Z (supposing we start light and end up heavy)
☺ | ☹
Much more NUSTAR-SFRS integration | Could generate conflicts on goal
NUSTAR setup properly commissioned in beam during SFRS commissioning | Higher risk to damage unique equipment (but can be mitigated easily)
 | Long NUSTAR beam period, with idle times where SFRS does pure SFRS stuff
 | Not all beams with NUSTAR will yield interesting results?
SFRS
NUSTAR

## Slide 46: Super-FRS NUSTAR – mid coupling hypothesis
Super-FRS perform its commissioning
when confident we remove isomer tagger and start NUSTAR beam commissioning hand in hand with Super-FRS last points of commissioning
Super-FRS commissioning end at the last setting for Super-FRS/first setting for NUSTAR, then NUSTAR experiment begings (in beam commis. already done)
SFRS
NUSTAR
☺ | ☹
Much more NUSTAR-SFRS integration | 
NUSTAR setup properly commissioned in beam during SFRS commissioning | (minor): need some agreement on process at the end of Super-FRS commissioning
Lower man power impact for NUSTAR than strong coupling | 
Reduced risk for NUSTAR experiment compared to other options | 

## Slide 47: Open points
Would define “we finished beam commissioning of SFRS and NUSTAR here we do first experiment” be good? Or is “the first NUSTAR experiment is the end of the Super-FRS commissioning?” (first case was my assumption)
I would suggest to check feasibility of first NUSTAR experiment with Super-FRS expert, to avoid a too risky experiment
Once NUSTAR setup is better defined the discussion can start of how we couple the two commissioning (from which moment we rely on the NUSTAR setup and remove our small isomer tagger, if some light beam for tracking detectors need to be tested etc…) and what shall be done for the NUSTAR in beam commissioning
For information: we just started the discussions on the Super-FRS “no-beam” commissioning in the project side (so no urgency!)

## Slide 48
End slide

## Slide 49: Why isomer tagging is preferred for SFRS com.1
5 options: counting, beta, alpha, mass, isomer tagging
  counting: (step by step from Primary beam), not efficient if long jump, always a backup
  beta: life time with error not unique finger print, end point measurement can be confusing if several decays (isomer/gs) and need a lot of statistics
  alpha: quite rare in the chart, energy and life time are unique fingerprint, but fast alpha decay make spectra confusing if spectrometer tuned far away of where it is believed
  mass: unique finger print, main issue implantation in a very thin matter, extraction, then mass measurement, when all works fine it is perfect, but many steps that can go wrong, and if the setting is not the one though, the implantation will not work, nice to confirm on an establish setup, maybe not for shooting in the dark…
  isomer: quite unique finger print, more open the setting better (contrary to 2/3/4), implantation can be done quite surely (thick plate), direct correlation between ion and gamma, not a multi step process, best when shooting in the dark
1: This of course does not constrain in anyway the options for NUSTAR first science