## Slide 1: Planning status – strategic schedule
Injector Controls Upgrade: finalization
2024 2025 2026* 2027 2028
HEBT-ES HW-Commissioning
Beam Time
Beam Time
Beam Time
SIS100 HW-Commissioning
HEBT-FS HW-Commissioning
SFRS HW-Commissioning
move to MCR & commissioning
Injector Controls Upgrade: 1st version of new production system
ES Beam Commissioning
FS Beam Commissioning
operation from FCC
UNILAC operation with new CS
FCC Construction & Procurement of Interior equipment
Cryo 2 Commissioning
SFRS Cooldown
SIS100 Cooldown
Controls & BI Digitization UNILAC, SIS18, ESR, Cryring, HEBT
Dry-Runs
Dry-Runs
Dry-Runs
Dry-Runs
Beam Time
equipment
Installation
* 2026 beam time schedule, to be confirmed

## Slide 2: Vorschlag
Trennung der Entscheidung Strahlzeitverschiebung 2026 von der Entscheidung zum Testbetrieb mit SIS18 im Februar 2026 ohne Dach.
Die Strahlzeitverschiebung in die 2. Jahreshälfte soll zügig beschlossen werden, um Missverständnisse, Doppelplanungen und Verzögerungen zu vermeiden.
Der Testbetrieb Injektor-Upgrade soll ebenfalls fix auf den Februar 2026 festgelegt werden
Der einzige offene Punkt bleibt, wie dieser Testbetrieb im Detail aussieht. Es gibt 3 Optionen:
Betrieb mit Dach, da die erste Lage zeitgerecht installiert werden kann
Betrieb ohne Dach, falls die Genehmigung der Behörde rechtzeitig vorliegt
Betrieb nur bis TK
(absteigende Präferenz)