## Slide 1: SFRS Installation
NUSTAR Annual Meeting 2025
K. Knie

## Slide 2
SFRS Early Science
Pretarget
area (sc)
Target
area (nc)
Separator (sc)
....

## Slide 3: A) Local Cryogenics Installation: 1) „TGA“ (Technical Infrastructure)
beam
beam
tunnel width: 8 m
tunnel height:7 m
Cable trays, cables in trays, cooling water, compressed air, cranes …
Courtesy Felix Wamers

## Slide 4: A) Local Cryogenics Installation: 2) Tunnel Measuring and Marking
Measure tunnel, calculate accelerator grid
 markings (± 1 mm).
beam
beam
F
F
M
M
Courtesy Felix Wamers

## Slide 5: A) Local Cryogenics Installation: 3) Multipurpose & Warm Gas Lines
F
F
M
M
W
W
Install branch-wise auxiliary cryo lines to tunnel walls: WGS, CLR, MPL
Courtesy Felix Wamers

## Slide 6: A) Local Cryogenics Installation: 4.a) Placing Feed Boxes
F
F
M
M
W
F
F
F
W
Drill holes, place feed boxes to marking
Set feed box nominal height (shims ?)
Courtesy Felix Wamers

## Slide 7: A) Local Cryogenics Installation: 4.b) Install Transfer Lines
F
F
M
M
T
T
T
W
F
F
F
W
(Drill holes for supports), positioning and
welding transfer line pieces between FBs
T
Courtesy Felix Wamers

## Slide 8: A) Local Cryogenics Installation: 4.c) Jumpers with their Endcaps
F
F
M
M
W
F
F
W
J
J
J
F
T
T
T
Weld jumpers on FBs: Adjust (FB &) jumper to magnet interface (fids). Mockup?
T
Courtesy Felix Wamers

## Slide 9: A) Local Cryogenics Installation: 5) Connect Feed Boxes to Warm Gas
F
F
M
M
W
F
F
W
J
J
J
F
T
T
T
Connect FBs to auxiliary/warm piping:
Weld / cut pieces of MPL, WGS
T
Courtesy Felix Wamers

## Slide 10: Local Cryogenics Installation: 6) X-ray, CPL, Close Vacuum Jackets
F
F
M
M
W
F
F
W
J
J
J
F
T
T
T
Branch-wise x-ray all pp-welds, CPL, MLI, close shields and vacuum jackets.
T
Courtesy Felix Wamers

## Slide 11: Local Cryogenics Installation: 7) Cabling Connections, Controls
F
F
M
M
W
F
F
W
J
J
J
F
T
T
T
Connect cables / air to FBs.
Bring cryogenics controls into operation.
T
Courtesy Felix Wamers

## Slide 12: Local Cryogenics Installation: 8) Commissioning without Magnets
F
F
M
M
W
F
F
W
J
J
J
F
T
T
T
Branch-wise vacuum check, p&p, cooldown  cryogenic performance
T
Courtesy Felix Wamers

## Slide 13: Local Cryogenics Installation: 9) Cutting off Jumper Endcaps
F
F
M
M
W
F
F
W
J
J
J
F
T
T
T
Cutting off the jumper endcaps, prepare for connection to magnets (before cabling?)
T
Courtesy Felix Wamers

## Slide 14: Local Cryogenics Installation: 10) Bring Magnets into Tunnel
F
F
M
M
W
F
F
J
F
M
J
W
M
M
J
T
T
T
Place magnets to their nominal positions (precision +/- 1mm)
T
Courtesy Felix Wamers

## Slide 15: A) Local Cryogenics Installation: 11) Aligning Magnets to Beam (IOL)
F
F
M
M
W
F
F
M
W
M
J
J
J
F
M
M
T
T
T
Align the magnets (to the IOL) (~ 1 mm, ~ 1°)
T
Courtesy Felix Wamers

## Slide 16: A) Local Cryogenics Installation: 12) Welding of Magnets to Jumpers
F
F
M
M
W
F
F
M
W
J
J
J
M
M
F
T
T
T
Weld jumpers to magnets. Remove supports.
X-ray. CPL? MLI. Close shield/vacuum jacket
T
Courtesy Felix Wamers

## Slide 17: A) Local Cryogenics Installation: 13) Connect Current Leads Return
F
F
M
M
W
F
F
M
W
J
J
J
M
M
F
T
T
T
Connect current leads to warm gas return line
T
Courtesy Felix Wamers

## Slide 18: A) Local Cryogenics Installation: 14) Finish all other Installation Work
F
F
M
M
W
F
F
M
W
J
J
J
F
M
M
T
T
T
Vacuum pumps, magnet cabling, bring magnet controls into operation?
T
Courtesy Felix Wamers

## Slide 19: A) Local Cryogenics Installation: 15) Commissioning with Magnets
F
F
M
M
W
F
F
M
W
J
J
J
F
M
M
T
T
T
(Branch-wise): insulation vacuum, CPL?, pump&purge, cooldown...
T
Courtesy Felix Wamers

## Slide 20
Pretarget Area

## Slide 21
Pretarget Area: Possible Installation Sequence
Position Local Cryo in tunnel

## Slide 22
Pretarget Area: Possible Installation Sequence
Position Local Cryo in tunnel
Bring Multiplet 1 and 3 in parking position

## Slide 23
Pretarget Area: Possible Installation Sequence
Position Local Cryo in tunnel
Bring Multiplet 1 and 3 in parking position
Install and test Local Cryo

## Slide 24
Pretarget Area: Possible Installation Sequence
Position Local Cryo in tunnel
Bring Multiplets 1 and 3 in parking position
Install and test Local Cryo
Connect Multiplets 1 and 3

## Slide 25
Pretarget Area: Possible Installation Sequence
Position Local Cryo in tunnel
Bring Multiplets 1 and 3 in parking position
Install and test Local Cryo
Connect Multiplets 1 and 3
When crane available (Sep 25): Install Multiplet 2

## Slide 26
Target Area
Crane test with 50 t, final test with 100 t, April 2024
Target Building Feb.2024

## Slide 27
Installation of shielding blocks,
May-July 2024
Target Area
Sep. 2024

## Slide 28
Target Area
80 t shielding flask has been installed in Dec. 2024

## Slide 29
Target Area
Dec 2024, Jan 2025
Shielding blocks entrance and exit target area

## Slide 30
Target Area: Possible Installation Sequence
https://www.youtube.com/watch?v=P8qhiqWR0Tw

## Slide 31
0:Targetchamber and shielding
(to be installed by GSI)

## Slide 32
1. Multipol Magnets 1

## Slide 33
2 Multipol Magnets 2 (installation not along the beamline!)

## Slide 34
3, 5, 7: Dipole magnet:
Heaviest assembly unit (95 t)
Will be installed in two parts

## Slide 35
4, 6: Beamcatcher
7.5 t
3.6m
Beamcatcher Plug

## Slide 36
8: Beamcatcher 3+Sextupol e
9: Shielding

## Slide 37
Preliminary Schedule

## Slide 38
Installation above target area (Q3/4 2026)

## Slide 39
Installation Branchbox, Mar. 2025

## Slide 40
Pre installation of sc magnets in LE cave

## Slide 41: Preliminary overall installation schedule
Chart: 
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Magnet rfi 2/2025 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Section rfi | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Local cryo subbranch ready | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
TA exit ready | 3.5
Magnet inst. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35

## Slide 42
Thank you for your attention!