## Slide 1: FAIR operation concept from the new Control Center
Stephan Reimann
subproject leader FAIR commissioning,
head of GSI operations department
CERN-GSI Collaboration Steering Board Meeting, May 2025

## Slide 2: Outline
FAIR Commissioning
FAIR Operation Concept (FCC 2028)

## Slide 3: GSI & FAIR – Integrated Campus Schedule
2024 2025 2026 2027 2028
Beam Time
Beam Time
Beam Time
Commissioning
Injector Controls Upgrade: 1st version of new production system
Injector Controls Upgrade: finalization
ACC operation
from new FCC
FCC Construction & Procurement of Interior equipment
SFRS Cooldown
SIS100 Cooldown
Controls & BI Digitization UNILAC, SIS18, ESR, Cryring, HEBT
SFRS Hardware-Commissioning
ES Beam Commissioning
Dry-Runs
HEBT-ES Hardware-Commissioning
Cryo 2 Commissioning
Dry-Runs
HEBT & SIS100 -FS Hardware-Commissioning
Dry-Runs
FS Beam Commissioning
Beam Time
Equipment
Installation
Civil Construction
FAIR Tech. Buildings Infrastructure
FAIR Buildings Testing & Commissioning
FAIR Accelerator / Experiments Procurement & Manufacturing
SIS100-FS
SFRS-ES
FAIR Accelerator / Experiments Installation
SIS100-FS
HEBT/SFRS-ES
HBO
Regular Operation of Tech. Buildings Infrastructure
Start of ES
science program
start of first
science program
& first science+ program
First beam in T1S1
today

## Slide 4: First 3 major Commissioning Milestones
Q2/2025  Q4/2025: cryogenic plant “Cryo2” (building K0720A & parts of main supply building H0719A) (see coloured area right)
Q4/2025: start of first commissioning activities in Transfer Lines T1S2 and subsequently T1S1
(both ready for beam in Q4/2026)
Q1/2026 commissioning of FAIR Control Centre and new Main Control Room
 Early Science commissioning schedule on section level
Cryo2 Commissioning
FSB – ES Commissioning

## Slide 5: Organisation of Commissioning
Commissioning is organized as a subproject within FAIR project
fully integrated in FAIR management lead team with other sub project leaders and in GSI accelerator organisation (ACC)
fully integrated into FAIR reporting structures (planning, risk management, controlling) and committees
Subproject Commissioning is divided in 12 work packages with dedicated work package leaders (commissioning responsible)
Full integration of experiment groups and facility management (technical building infrastructure) in the commissioning process
first science
and beyond
FAIR Project Lead
J. Blaurock
Head Accelerator Operation & Development
R. Assmann
Technical Director
J. Blaurock
Line management S. Reimann to operations department OPE
Note: handover to operation organisation after delivering beam with project completion parameters (PCP) on target:
Early Science: 238U73+, 1 GeV/u, 2E9 ions/second
First Science: 238U28+, 1.4 GeV/u (60Tm), 2.5E10 ions/cycle
First Science+: 197Au79+, 11 GeV/u, 1E7 ions/second
associated GSI-group (FAIR Commissioning and Operation) in ACC-OPE
line management
project organisation (matrix)
FAIR Commissioning Subproject Leader & GSI Operation Manager
S. Reimann
HEBT
commissioning responsible
Cryogenic
commissioning responsible
FAIR Control Center
commissioning responsible
Safety
commissioning responsible
technical building infrastructure responsible
NUSTAR
commissioning responsible
Radiation Safety
commissioning responsible
SFRS
commissioning responsible
Controls commissioning responsible

## Slide 6: 1st Major Milestone: Commissioning of cryogenic plant
Cryo2 work package organization has been developed (as pilot for all further commissioning activities e.g. HEBT commissioning)
Organisation, processes and responsibilities including safety are clarified and documented
Lessons Learned from Cryo2 Commissioning are important for the next commissioning phases
Cryo2 Commissioning - work package organization with external companies
Detailed commissioning schedule of cryo system

## Slide 7: Commissioning of cryogenic system
Cryo2 commissioning starts June 2025 with distribution box DB3
involves cryoplant, compressor station, and the helium storage
an media from construction site
requires special safety measures due to surrounding construction site
following steps: Super-FRS and SIS100 cryo distribution systems

## Slide 8: HEBT-Commissioning & First Beam Event in Q4 2026
Target: T1S1DF6 (Scintillator screen)
GSI/FAIR
border
NE1 NE22
beam from
SIS18
Wall
Boundary of the safety
zones NE1 and NE22

## Slide 9: Preparation of Gate Reviews for phase transitions
gate review concept under development
different readiness needs, depending on commissioning phase / concept
includes acceptance checklists and inspection walk-through
2. remote & single system
M104
M104-s
3.2 Integration (Dry Runs)
M11
M105
4. Pilot beam comm.
M12-A
M12-s
1. Pre-comm. & Local HW
M103-s
M103
3.1 Integration (multi system)
FSB: TBI & Media Ready
Safety / radiation safety
Commissioning: previous phase are completed
Readiness Review (Gate): release for the next phase
Mechanical Completion
M12
3. Integration

## Slide 10: II. FAIR Control Center

## Slide 11: FAIR Control Center – Move and Commissioning
Bi-weekly FCC commissioning meeting with all stakeholders established
planning & steering of construction, procurement, installation and commissioning
final acceptance of injector controls upgrade with beam
Extended dry test phase for data supply, control and readout
10.11.2025 : new main control room will be ready for interieur installation
consoles: the call for tenders is closed, the order will be placed next week
procurement process for other equipment (displays etc.) hast also started

## Slide 12: FAIR Control Center – basic facts
25 workstations
fully digital
access control
water-cooled consoles
height-adjustable tables
open space, no columns/pillars
holistic floor design with meeting rooms, visitor's gallery, showers, changing rooms, kitchen

## Slide 13: Interieur
Console specification has benefited from CERN experience (screen size, accessibility, cryo and TI area)

## Slide 14: Main Control Room – start configuration
25 workstations a 6 monitors
Ion Sources & UNILAC: 5
SIS18: 2
HEBT: 1
SIS100: 3
Technical Infrastructure: 2
Access Systems (TVS, ZKS, PAS): 1
Cryogenic-system: 2
FRS & SFRS: 3
ESR: 2
HITRAP: 1
Cryring: 2
Testing: 1
1 wall with overview displays (LED-matrix)
Src
UNI
UNI
S18
S18
S100
S100
FRS
SFRS
UNI
PAS
display wall
ESR
ESR
HITRAP
CRY
CRY
HEBT
SFRS
Cryo
Cryo
TI
TI
S100
UNI
TEST

## Slide 15: FCC: Staff deployment during commissioning phase
Assumptions
  Beam commissioning always runs parallel to GSI beam time
  Hardware commissioning mainly (but not always) takes place during GSI shutdown
Staff on site
  2-3 or 4 operators permanently present in 16/7 or 24/7 shift work
  Commissioning team (composition, depending on commissioning phase)
  1 cryo operator permanently (new)
  1 TI operator permanently (new)
  Machine experts on demand (UNILAC, SIS18, ESR, Cryring, FRS, HEBT, SFRS, SIS100)
staff on call
  Technical on-call services (accelerator, TI, IT)
  On-call services for safety and radiation protection
  On-call services for coordination

## Slide 16: II FAIR Operation Concept (FCC 2028)

## Slide 17: FCC 2028 - FAIR operation concept
Goal:
consistent operating concept for an effective and efficient GSI/FAIR operation from FCC for optimal science output
Scenario:
9 months full operation and 3 months shutdown
Deliverables:
highest availability for experimental operation and high beam quality to achieve optimal physics outcome
processes, roles & responsibilities
staff deployment (number, qualification)
Minimization of downtimes automated fault tracking, fast fault analysis (archiving system, post-mortem system), preventive or even predictive maintenance
Minimization of setup time optimized user interfaces for operation, fast trim times, automation of repetitive tasks, automatic tuning & beam-based feedback (e. g. spill optimization), maximized reproducibility
Optimization of parallel operation capabilities reduction of unwanted interaction between patterns running in parallel, flexible scheduling, backup user
Optimization of beam scheduling to reduce setup periods (strategic long-term beam scheduling, e. g. long blocks with the same element)

## Slide 18: Optimal staff deployment Example: Operations Department OPE
the demands on operation have increased over the recent years
  increased parallel operation, new operation modes, a new storage ring and the new control system, new UI to the accelerators – and now FAIR
not all old operators could keep up with the increased demand
  experiences with engineers (and physicists) are increasingly better
  operators should also be able to develop tools (software, instrumentation)
this is reflected in the most recent hirings
  balance is important
  presently: 1/3 physicist, 1/3 engineers, 1/3 technicians, (Status 2015 ca.: 20%, 20%, 60%)
to be considered:
  impact of automatization, improving user interfaces and maturing control system are likely to shift the balance and personnel demand
  the domain knowledge of the machine departments must be preserved

## Slide 19: Conclusion
With the start of commissioning, we are now entering a very intensive phase for FAIR
We have already been working together very well for years.
consulting on various commissioning topics (cryo-system, control room, cryo-magnet commissioning, general commissioning strategies and concepts, ...)
FAIR Commissioning Workshop, Safety Advisory Committee, ...
the GSI/FAIR control system landscape was partly taken over from CERN (e.g. LSA) and is now further developed in collaboration with CERN
  basic controls concepts are the same (patterns, chains, model-driven data supply, accelerator- and beam modes, RBAC, etc.)
  higher-level concepts can be developed jointly since we work on the same base
  commissioning tools and automation will benefit both operation teams
  a joint further development of the software creates synergies, as experts for these systems work at both institutes
The collaboration on FAIR Commissioning topics is to be intensified

## Slide 20: 2 Work Packages defined in ADDENDUM No. 16
Collaboration on Beam instrumentation &
FAIR accelerator commissioning
WP 1.1: Cryogenic Current Comparators (CCC)
WP 1.2: Luminescence Monitor for LHC e-lens
WP 1.3: Ionisation profile collaboration
WP 1.4: FESA integration of beam diagnostics: Present focus on BSM and CCC
WP 1.5: SEM-Grid Monitor for high-intensity beams
WP 1.6: BPM Hardware development, analysis methods and signal simulation
WP 1.7: Beam Instrumentation design and usage for slowly extracted beam
WP 2.1: Support for hardware and beam commissioning of FAIR accelerators and systems
WP 2.2: Support for software tools for commissioning and early beam operation

## Slide 21: Thank You

## Slide 22: Recent Beamtime Statistics

## Slide 23: GSI & FAIR parallel operation modes
UNILAC
UNILAC
UNILAC
Unilac-Chain
ESR
SIS18
SIS18
Cryring
HITRAP
HHT, HAD
X, Y, Z, M
A
 (2-3) of 4 parallel
 (1-2) of 5 parallel
 2 of 3 parallel
FRS
A, C, D, M
SIS18 Chain
Storage Rings & HITRAP
FRS
SIS18
UNILAC
SIS100
NUSTAR
CBM
 1-2 of 2 parallel
pf = 6 - 9
SRFS
FAIR FS+
local