## Slide 1: Current status of Super-FRS Commissioning planning, LCM and open points
S. Pietri

## Slide 2: Super-FRS – general overview
FHF2, HEB cave,
R3B NUSTAR
Main separator
Pre-separator
Target area
Pre-target
Focusing system
Supply building,
lab, control room
Ring branch, not ES
Super-FRS stands for
Super FRagment Separator
Super for super conducting
Low Energy Branch
not ES

## Slide 3: Objective of Super-FRS commissioning
Main goal of Super-FRS: select and identify ions produced in nuclear reactions at the target to deliver to NUSTAR experiments.
Final goal of the Super-FRS commissioning: assure Super-FRS can select and identify ions.
Confirm something like
this 
Z of particle
AoQ of particle
Data from
FRS

## Slide 4: Super-FRS: Super FRagment Separator
238U from SIS18 on target to produce 212Pb, 238U+12C@1 GeV.A  212Pb
This is what is produced
at the target (yield)
3000+ isotopes
we need to select
the one we want

## Slide 5: Super-FRS: Super FRagment Separator
238U from SIS18 on target to produce 212Pb, 238U+12C@1 GeV.A  212Pb
50 most produced ones
 red is 212Pb

## Slide 6: Super-FRS: Super FRagment Separator
238U from SIS18 on target to produce 212Pb, 238U+12C@1 GeV.A  212Pb
At FHF2 after selection

## Slide 7: Super-FRS – assembly unit view, ES scope
Installation already started  see Klaus Knie presentation

## Slide 8: Scope (elements) of commissioning
Goal commissioning: reach FHF2 (commission the full HEB line)

## Slide 9: Commissioning include last multiplet at FHF2
FHF2 is in HEB, in front of the R3B experiments
SFRS multiplet
beam reach here during SFRS beam commissioning

## Slide 10: Commissioning phases, sections goal
Need sectioning to breakdown the work
Allows to plan parallel installation work and/or commissioning work
First idea: functional sections, Magnets then diagnostics
Goal commissioning: reach FHF2 (commission the full HEB line)

## Slide 11: System list
SCM: Super Conducting Magnets
NCM: Normal Conducting Magnets (target area)

## Slide 12: Phase of commissioning
Mechanical Completion (end of Installation) M102
Phase 1: hardware commissioning (after mechanical completion) (end M103)
Phase 2: remote commissioning (end M104)
Phase 3.1: integration test (end M105)
Phase 3.2: dry run (SAT Ba/M11)
Phase 4: beam commissioning (SAT Bb/M12)
          (note, beam can be reasonably high intensity at the end)

## Slide 13: Milestones commissioning
M102 Mechanical Completion/ ready for hardware commissioning
  STV named, temp. safety present, local power and media supply ready, component inst.
M103: hardware commissioning done, ready for remote commissioning
  TGA installed, commissioned, working, media supply assured, safety implement,
  control system and expert tools present
M104: remote commissioning done, ready for integration test
  TGA, power, cryo, and media supply fully commissioning available
  higher tier control system deployed, sequencer test done
M105 integration test done, ready for dry run
  PAS and Safety installation commissioned
M11/SAT Ba, dry run done ready for beam
M12 beam commissioning done, SAT Bb done, ready for physics
          (note, beam can be reasonably high intensity at the end)

## Slide 14: Commissioning phases, sections
for phase 1 (local) and 2 (remote):
  component in sections following assembly unit, commissioning starts as soon as possible
  vacuum and cryo own sections
  special treatment for target area (more on this later)
for phase 3.1 (integration), 3.2 (dry run) and 4 (beam)
  sections are based on functional sectioning (or focal planes)

## Slide 15: Commissioning phases, sections for phases 1/2 and 3/4
Phase 1 sections different

## Slide 16: Status of planning - LCM
LCM approach for phase 1 and 2 status (co-organized with V. Kamerdzhiev)
link : FAIR - Commissio... – lcmd https://share.lcmdigital.com

## Slide 17: Status of planning,Target area
Example target area

## Slide 18: Status of planning, Target area
Example target area

## Slide 19: Status of planning, Beam diagnostic chambers
suppose VAC phase 2 done
pressured air, power for motor drive
and patch panel connection
pressured air, power for motor drive
and patch panel connection

## Slide 20: Planning - schedule
54 elements, 8 cryo branches, 18 vacuum sections
6 to 8 steps for phase 1 and phase 2
 500 steps for phase 1 and phase 2 in planning
Some elements are only once: Target area, so uncertainties are constrained
SCM 30+, BD chamber 10+, so here uncertainties shall be controlled

## Slide 21: System list – more details
Interlinked dependencies in phase 1 and 2:
  Target, Normal conducting magnets, vacuum (pillow seals)
  Super conducting magnets, cryogenics
  Beam vacuum and beam diagnostic chambers
Start of phase 1 per component strongly linked to installation

## Slide 22: System status and thought
Gas system : still no planning for it (risk for detector commissioning)
Cryogenics: detailed plan sent by Felix, many open options
Target area: sequence action ready, strongly linked to installation for phase1
NCM: linked to target area (roof closing)
SCM: phase 2 dependent on cryogenics, question on man power for COM.
Beam vacuum: sequences and resources plan available
Beam diagnostic: after beam vacuum, plan and resource needed available
General control, machine model, ion optical model commissioning in phase 3
Beam commissioning: IO commissioning with detector commissioning, then ID

## Slide 23: Section, element, heterogeneity of elements

## Slide 24: First simulations – toy model
Current planning resource estimate (not fully LCM but taking results into account)

## Slide 25: First simulations – toy model

## Slide 26: Full .xls document

## Slide 27: Results in Planisware
Consolidate Planisware, cooling? hypothesis Mar 27?

## Slide 28: Example of detail

## Slide 29: Example of details – vacuum installation
Thanks to Marina Gorda for implementing all the complexity!

## Slide 30: plans
plan your work and work you plan!
say what you do, do what you say!
open information exchange
clear dependencies and risk
in planning suggest reasonable estimate and buffer to deal with delays

## Slide 31: Goal for this workshop
Come with clear agreement on steps
Identify all dependencies
Start/estimate time for commissioning steps
Check what is missing in installation planning (ex: rack)

## Slide 32
My thanks to:
Seva Kamerdzhiev, Marie Cabioch, Marina Gorda, Stephan Reimann,
Heike Marcocelli, Valentina Ricciardi.

## Slide 33
Local Cryogenics Branches

## Slide 34
Commissioning need to be done in parallel to installation (as much as possible)
Integration test could be done “per installation block”  main question: Cryo commissioning (no info possible)!

## Slide 35
Assembly Units
Installation: Super-FRS
Installation: NUSTAR
LM_01
LM_02
DC_01
LM_03
TA
NC_QQ
NC_QS
NC_D1
NC_D2
NC_D3
BC1
BC2
BC3
SM_01
SM_03
SM_02
DC_02
SM_04
SM_05
SM_06
SM_07
FTF1
FPF0
FPF1
FPF2
FPF3
FPF4
FMF1
FMF2
FMF3
FRF1
DC_18
FRF2
FRF3
DC_19
DC_20
FHF1
FLF1
DC_10
DC_11
DC_12
DC_13
DC_14 (maybe)
FLF2
FLF3
FLF4
DC_15
FLF5
DC_16
FLF6
DC_17
DC_09
DC_07
DC_03
DC_04
DC_05
DC_08
DC_06
SCD_01
SCD_02
SCD_03
LM_04
LM_05
SCD_04
SCD_05
SCD_06
LM_06
SCD_07
SCD_08
SCD_09
LM_07
LM_08
LM_09
SCD_10
SCD_11 (branch)
SCD_12
LM_10
LM_11
FHF2
FHF3
LM_12
LM_13
GLAD
SCD_13
LM_14
LM_15
LM_16
LM_17
LM_18
LM_19
LM_20
LM_21
LM_22
LM_23
SCD_14 (branch)
SCD_15
SCD_16
SCD_17
SCD_18
SCD_19
SCD_21
SCD_20
SCD_22
SCD_23 (branch)
SCD_24
EBM_01
EBM_02
EBM_03
EBM_04
EBM_05
EBD_01
EBD_02
EBD_03
VAC_02
VAC_07
VAC_08
VAC_10
VAC_11
VAC_03
VAC_04
VAC_ NUSTAR
VAC_01
VAC_09
BDN
VAC_05
VAC_06
NC_S
Last modified: Super-FRS Workshop, 15-17 Nov. 2021
SM sc short multiplet
LM sc long multiplet
SCD sc dipole
DC diagnostic chamber
VAC beam-line vacuum
EBD EB dipole
EBM EB multiplet
Installation: Super-FRS
Installation: NUSTAR
beam
Assembly Units along the beamline
early science locations
Fxxx notation defines “focal planes”
TA target
NC_QQ nc quadr. 1a + quadr. 1b
NC_QS nc quadr. 2 + sextupole
NC_D nc dipole
BC beam catcher
NC_S nc sextupole
7 sc short multiplets
13 sc long multiplets
15 sc dipoles
10 diagnostic chambers (DC_01 not includable)
4 long/special beam pipes
Number of pieces for Early Science
(Target Area excluded)
4 sc long multiplets
3 sc dipoles
2-3 diagnostic chambers
1 long/special beam pipes
Additional number of pieces for LEB (up to FLF3)
6 sc long multiplets
6 sc dipoles
6 diagnostic chambers
6 long/special beam pipes
5 sc Energy Buncher multiplets
3 sc Energy Buncher dipoles
Additional number of pieces for completion
Power converter Racks (total) 77
Control Racks (total) 336
not ATB

## Slide 36
G018
T103
G006A
FTF1
Commissioning sections along the beamline v1
T103
G006B
G006
beam
sections for commissioning
blocks for machine installation
FPF0
FPF1
FPF2
FPF3
FPF4
FMF1
FMF2
FMF3
FRF1
FRF2
FRF3
FLF1
FHF1
FHF2
FLF2
FLF3
FLF4
FLF5
FLF6
All this is LEB
commissioned together

## Slide 38: Local Cryogenics branches M, H, G (B optional)
Procurement and installation branch M
Procurement and installation branches H, G
Planned FAIR contracts: December 2024
Planned delivery to FAIR: October 2025 – July 2026
Planned installation: October 2025 – August 2026
shielded target area
T
P1
P2
M1
M2
M3
H
G
11.25
11.25
04.26
09.26
04.26
08.25
batch M3 07.26
batch M2 02.26
batch M1 10.25
batch W2 09.25
batch W1 06.25
batch H 02.26
batch G 05.26
05.26
last batch W0 Dec-24
Delivery dates of local cryogenics boxes
Local cryogenics sectors: installation completed
03.25
Tender running
Deadline for offers: 23/10/2024
Offers from 4 bidders (3 companies + 1 consortium)
All qualified and well-known companies
Requested schedule confirmed
Negotiations starting
Risk of FAIR internal competition with cryo tenders
Overview tenders LC branches
CE
Still to be tendered: jumpers of branches M, H, G