## Slide 1: The Status of Superconducting Multiplets at Mechanical Completion
Melanie Cho
26.05.2025

## Slide 2: SC multiplets for Early Science 2027
Super-FRS SC Multiplet | M. Cho
target area
BB
branch T
branch P
branch M
branch H
branch T
pre-target area
SM2
SM3
SM1
SM4
SM5
SM8
LM11
LM09
LM10
LM16
LM18
LM20
LM21
LM22
LM23
LM25
LM13
LM15
LM29
Cold test completed at CERN or delivered to GSI
Cold test on-going at CERN
Waiting for cold test at CERN
Final FAT test passed at ASG
Production/Repair on-going at ASG
SM6
@ ASG FAT completed
SM05/LM22/LM23/LM21
@ ASG, under repair and production SM01/SM03/SM08/LM13/LM15/LM29
@ GSI : 6 multipets
LM09/10/11/16 and SM02/06
@ CERN : LM20/18/25 and SM04

## Slide 3: Working process for the multiplets
1.
2.
3.
4.
5.
6.
7.
8.
9.
10.
11.
12.
13.
14.
15.
16.
Working Processes Pre-assembly
1.
2.
3.
4.
5.
6.
7.
8.
9.
10.
11.
12.
13.
14.
15.
16.
Working Processes Installation
transport to LEB cave
Preparation transport
Documen-tation in PLM
mounting flexible power cables
mounting valve panel
quench detection box (only FOS)
mounting terminal boxes
mounting vacuum gauges
mounting vacuum valves
inspection report of works VAC
cleaning vacuum chamber
inspection report electr.
tests
electr.
tests (sensors)
incoming/ goods
tests
unpacking
Beam pipe Vacuum leak test
Isolation Vacuum leak test
purging + filling with nitrogen
documentation/ plans of DMU
assembly of support feet
air cushion transport
positioning on blue line
removal of transport rods
Bodenbefestigung
Mounting safety valve in tunnel installation
mounting vacuum pumps
Beam pipe
welding
mounting gate valve
Documen-tation in PLM
Jumper welding
Connecting signal cables
Current Lead Warm Gas (swagelock)
Grounding
Electrical tests
Insulation vauum tests
MC
Multiplet bereit für IBN
Magnet arrival at GSI
Transport to final position
(air cushion)
Closing open non-conformities before MC

## Slide 4: Storage conditions
Visual/Endoscopic inspection
Welding Jobs by ASG and
sub-contactors
  Lhe vessel
  TS shield
  Pipes
Conform ?
F-QB-SCM-en-MT-0009_Deviations_list_for_welding
_and_brazing_process
Used in production
Yes
No
Repairable?
Yes
Issue NCR
Repair
Assembly
No
Issue NCR
Assembly
Risk is
acceptable?
Yes
No exposure to humidity
and oxygen

## Slide 5: Management of Non-conformities
Evaluate and officially inform ASG
by WPL
Report findings by testing team
Non-conformity ?
Yes
Repairable at CERN?
Yes
Repair
Issue NCR
No
Repair at GSI after SAT Ab

## Slide 6: Open non-conformities
Modules | Non-conformities | Where/when
LM09 | Repair Leaky LEMO feedthroughs Leak on a flange on the cryo jumper's bolted flange Isolation T90 sensor on LQB Repair one damaged voltage tap cable | Pre-target after October, 2025
LM10 | Short circuit of BTX13 and BTX14 Leaky LEMO feedthroughs | 
LM11 | Leaky LEMO feedthroughs | 
SM06 | Low insulation between BTP 407 and BTP408 T90 temperature sensor swap between WD15 and WD16 Leaky LEMO feedthroughs | LE cave, the timeline to be decided
LM16 | Low insulation between Sensors BTX007 and BTX008 Leaky LEMO feedthroughs | 
SM02 | Repair damaged VT cable (Quad cold) | 

## Slide 7: Conclusion
There is no major issue with a delivery of Multiplet to CERN.
It is very important to keep the multiplets in non-oxidation environment.
Open non-conformities must be closed before the completion of the machine. ASG’s intervention will be scheduled in coordination with the GSI installation
working groups.