## Slide 1: Status of SIS100 installation – Progress and issues from machine perspective Niels Pyka

## Slide 2: Status of SIS100 installation
U10_U20_cryo-niches
  GE Vernova Main Power Supply installations
  Delayed start but on good track now
  End of installation 1/2026
  Commissioning planned Q1/2026 (with dummy load)
For details see talk of V. Plyusnin
U30 cryo-niches: local cryo installations
No installation yet, but first CLB delivered
For details see talk of M. Kauschke

## Slide 3: Status of SIS100 installation
U30 accelerator tunnel
Length of the ion target track: 1084 m, thereof 82% are cold
Installation started 3/2024
At present 29% of the total length is attached to the ground
Estimated completion: 3a
For details see talk of H.J. Löcker

## Slide 4: Status of SIS100 installation
U30 supply tunnel
A variety of racks, power supplies, power converter to be installed (additional racks from ACO etc. are not counted below)
In total 737 pc, 51% installed, some are still empty
Estimated completion: 2/2027 (basis: last 10 months)
For details see talk of M. Draisbach

## Slide 5: Status of SIS100 installation
U30 cable installation
Preconditions for cable laying:
  Cable routing, GSI check, correction, cable pull cards
Start in Q4/2023: laying of 128 cables (mostly koax pc)
Total number of cables to be layed: 20k pieces
Achieved until week 33 / 2025: 53%
Estimated completion: Q3/2026 (basis: last 9 months)
  Disabilities may lead to Q4/2026: different prioritization, issues with subcontractors, holidays etc.
For details see talk of H. Welker

## Slide 6: TBI installation to be continued
U30 Supply tunnel
Ground marking, fire protection walls, pump sumps, rework (existing list) etc.
U30 Accelerator tunnel
Ground marking, fire protection walls, exchange of fire extinguishing line, rework (existing list) etc.
Close coordination with TBI necessary
Planning of parallel work in same areas necessary

## Slide 7: Requirements to assure SIS100 installation in time
REMINDER
Follow-up work is much more time consuming than floor installation of ACC assemblies only
Cancel outdated paradigms
  Cable laying must not determine the ACC installation
  Install all available ACC assemblies as fast as possible: complete cells should be no precondition
  Keeping comfortable free moving space in the ACC tunnel must not be an argument to not install ACC assemblies
  Start to equip electronic racks or PSUs in the supply tunnel even under not perfect room conditions

## Slide 8: Requirements to assure SIS100 installation in time for commissioning
Immediate commissioning of a second, external welding team (frame contract) to keep the time schedule and as backup
Reinforcement of the SIS100 TRI team (6+1) for installation and immediate support of IFJ PAN
Dedicated bridges for cable pulling between all fire protection walls to reduce risc of damage for ACC
Resumption of the preparation of cable trays close to the ACC: without - no plugs; supply tunnel accordingly
LCM planning: allow for much more parallel work (ACC & TBI)
  Straights are 50m, arcs 130 m long! Definition of work by axis sections