## Slide 1: SIS100 Special Installations Status of procurement and findings
Lars Bozyk (Synchrtotron Special Installations)

## Slide 2: SIS100 Special Installations
2.8.11.1: Cryocatcher
  60 cryogenic ion catcher, integration into QDMs
2.8.11.2: Halo Collimation System
  Proton halo collimation system – two stage collimation system
  Ion halo collimation system – stripping and collimation
  Collimation system for systematic extraction losses
81 collimators / foils
SIS18: Development of Cryoinserts and further upgrade measures incl. laboratory administration
Simulation and machine experiments wrt Dynamic Vacuum in SIS18 and SIS100
Care & maintainance of 23 collimators in SIS18

## Slide 3: SIS100 Cryocatcher
60 cryocatcher in SIS100 will suppress dynamic vacuum effects
Located between quadrupoles in QDM
Production is finished
All components in store
  ready to delivery to integration
  or already integrated in Würzburg
Integration ongoing
Monitoring of distances
Still waiting for Einbauerklärung…

## Slide 4: Cryocatcher QDM-FAT
Verification of position measurement data
Verification of electrical integrity for current measurement
So far: 24 integrated

## Slide 5: Halo-Collimation in SIS100
Three different, non-independent collimation systems:
Proton halo collimation system
  Two stage collimation system
  Highly charged or fully stripped ions
Ion halo collimation system
  Stripping and collimation
  Medium charge states
Collimation system for systematic extraction losses
I.Strasik

## Slide 6: Proton Halo Collimation
Proton halo collimation system
  Collimation efficiency (multi-turn) close to 100%
  High collimation efficiency for light ions
  4x scattering foil (2x horizontal, 2x vertical)
  2x: 4x absorber block “protons”, 1x concrete shielded vacuum pipe

## Slide 7: Proton Scattering
Scattering foils:
  Tungsten sheet metal, 1mm width
  Four foils, 2 horizontal, 2 vertical
  Precision: +-0.5 mm
  fast movement (20 mm in 200 ms) required due to parallel operation

## Slide 8: 2x Proton Absorber Station
Absorber blocks, 2 horizontal, 2 vertical
  Material: Tungsten or Densimet, ca. 50 cm x 8 cm x 3 cm, ~25kg
  Movement: ~20 mm, speed: 5 mm in 200 ms desirable
  Precision: +- 0.2 mm
Shielding pipe:
  1m bakeable pipe
  surrouonded by concrete shielding
Option for vertical ionstripping foil

## Slide 9: Ion Halo Collimation in SIS100
Halo collimation of partially stripped ions:
  Stripping foil close to beam removes electrons
  Stripped ions are separated from circulating beam in magnets
  Collimator / absorber block removes these particles
Two positions:
  Sector 1 for vertical collimation (1 foil in foil chamber, 1 collimator)
  Sector 5 for horizontal collimation (1 foil at EE-kicker, 1 collimator between warm quads)
Stripping foil: Graphite, 0.5 mm – 1 mm
Collimator block: Copper with Ni/Au plating

## Slide 10: Extraction Collimation
During slow extraction some particles interact with the septum wires and get stripped
These particles will get lost
   collimators required, to catch these particles!
Two horizontal and one vertical pair in extraction straight
400 MeV, D.Onreka
2 between
warm Quads
2 behind EE-Kicker
2 in front of L-Septum

## Slide 11: Flowchart Halo-Collimation (2025)
Procurement:
15x slow drives, incl. 7x Cu-collimator
2.8.11.2.3
AID: 0002861
Procurement:
SIS100 Foil Chamber
2.8.11.2.3
AID: 0002866
Procurements:
6x fast drives
2.8.11.2.1
AID: 0002860
Collimator and Pump Module
AID: 0000783
Foil Chamber Assembly
AID: 0002865
vertical
I-Collimation Absorber Assembly
AID: 0002869
2 x P-Collimation Absorber-Assembly
AID: 0002863
Doble-Kicker-Assembly
AID: 0000568
Lambertson-Septum Assembly
AID: 0000764
Warm Quadrupole Doublet Assembly
AID: 0000762
2
2
2
1
5
1
Procurement:
SIS100 Warm Quad Collimation Chamber
2.8.11.2.3
AID: 0000784
Procurement:
SIS100 P-Collimation Shielding Pipe
production running
FAT in October 2025
SSI Assemblies
other assemblies
Vacuum chamber
drive incl. inside stuff
Procurement:
8x W-collimator
2.8.11.2 (<100 k€)
Procurement:
2x P-Absorber Chamber
2.8.11.2.2
AID:
1
1
2
2
8
+ Auxiliary Systems…
(almost) contracted
delivery 09/2026
Procurement:
1x vIon-Chamber
2.8.11.2.2
AID:
1
4
1
8
common procurement possible
Q2/2026
procurement start:
end of 2025

## Slide 12: Proc: Warm Quad Collimator Chamber
Manufacturer: TEES srl. in Italy
Production ongoing
Delivery expected in October 2025

## Slide 13: Proc: Slow drives
7 slow drives incl. copper collimators
  Slow extraction collimation
  Vertical ion collimation
8 slow drives for proton collimation
  Only drives, no support or collimator block
3 offers received, negotiation finished
Contract will be awarded soon to Omega Physics, France
  Manufacturing at Andesun, Nanjing, China
Delivery expected in stages
  First delivery in June 2026
  Last delivery in September 2026

## Slide 14: Proc: Fast Drives
6 components
  5 in foil chamber
  1 in kicker tank
Two different foils, simple mounting of foils
Electrical current measurement on foil
  HV sparkover from kicker has to be considered
Fast movement (20 mm in 200 ms) required due to parallel operation
Later installation possible (no large internal fixtures)
Own driver system required
  tbd: interface to accelerator control system
DS in work, 80%, coordination with ACO required
Start of procurement expected for end of 2025

## Slide 15: Proc: Vertical Ion Chamber
One single vacuum chamber
1 flange for drive with standard distance 300 mm
1 flanges for pump
Alignment & support

## Slide 16: Proc: Foil Chamber
One single vacuum chamber
5 flanges for drives with standard distance 300 mm
Several flanges for pumps (roughing chamber)
Viewport to observe foil damage
Detailing of chamber requirements and design required
Alignment & support
DS in work, 70%

## Slide 17: Proc: P-absorber Chamber
Two vacuum chambers
5 flanges for drives with standard distance 300 mm
Several flanges for pumps
Viewport to observe foil damage
Alignment & support
Detailing of chamber requirements and design required
Could be used to temporarily house collimators instead of EE-kicker

## Slide 18: Vacuum Chambers: common procurement?
2x
Protonabsorber-Chamber
Foil-Chamber
vertical Ion-Chamber
1x
1x
200-250 k€

## Slide 19: Many common parts
8x cover with bellow and bellow support
8x Fiducial bridge
8x Big flanges with reference surfaces and ref. holes
N x Drive flanges with tolerances and dowel pin holes
Same pipe-diameter for all chambers (300 mm)
Same support structure concept (only different lengths)
Same alignment bridge concept possible
Many common bakeout jackets
 common procurement?!

## Slide 20: Proc: 8x W-Collimator incl. support
Small procurement
  < 100 k€
  can be shifted until simulations are done
Blocks shall be adaptable to slow drives, same weight
Absorber blocks
  Material: Tungsten or Densimet
  ca. 50 cm x 8 cm x 3 cm, ~25kg
  2x four blocks, each 2 horizontal, 2 vertical
  Movement: ~20 mm, speed: 5 mm in 200 ms desirable
  Precision: +- 0.2 mm
Fluka Simulation required for
  angle
  material

## Slide 21: Proc: P-Absorber Shielding Pipe
~1 m bakeable vacuum pipe
Surrounded by (moveable) concrete shielding
Alignment & support
Open questions:
  Thickness of concrete?
  specifications for concrete?
  Can the heating jacket remain inside the concrete?
  More concrete required?
(no progress since last SIS100 workshop)

## Slide 22: Auxiliary Systems
Current measurement system
  IFCs are missing, procurement starting soon (BEA)
  All other components are delivered
Temperature measurement system for collimators (together with HEBT)
  SPS-based system
  Prototype has been developed (bachelor thesis, BEA)
  All components have been ordered and delivered
  Housing and support development
  Assembly pending, cabling needs to be done
Cameras for foil observation (BEA)

## Slide 23: Summary
Cryocatcher: running
Collimator chamber:
  Manufacturing running, FAT: middle/end of October 2025
  SAT and integration @ gsi: end of 2025
Slow drives:
  Contract (almost) awarded
  Deliveries starting from June 2026
Fast drives:
  Specification to be finished, coordination with ACO required
  Procurement start: End of 2025
Vacuum chambers:
  Specifications required, procurement start estimated for Q2/2026
Concrete pipe + W-collimators:
  Specifications to be developed, simulations required
Auxiliary systems:
  Proc. mainly by BEA
  Temperature monitor to be built