## Slide 1: SIS100 Workshop
Installation Plan Dipole and quadrupole
22.09.2025 – Hans Jürgen Löcker

## Slide 2: AGENDA
Content
01
Status Quo Installation (Status 2024)
02
Status Quo delivery dates Quadru-Poles
03
Installation Plan Quadru-Poles (Status 09.2025)
04
Open Issues / to clarify
05
Next Steps
06

## Slide 3: SIS100 Workshop – Installation Plan Dipole and quadrupole
Content
Installation Plan of Dipoles and Quadrupoles in SIS100
  Delivery Dates of Quadru-Poles M10-P (Status 09.2025)
  Start of Installation of Quadru-Poles
  Installation of Quadru-Poles
Further installation dates (beyond the Qadru-Poles) are not content of the today´s presentation. (will be presented on 23rd September 2025)

## Slide 4: AGENDA
Content
01
Status Quo Installation (Status 2024)
02
Status Quo delivery dates Quadru-Poles
03
Installation Plan Quadru-Poles (Status 09.2025)
04
Open Issues / to clarify
05
Next Steps
06

## Slide 5: SIS100 Workshop – Installation Plan Dipole and quadrupole
Status Quo Installation (Stand 2024)
DiPole
Quadru-Pole
Bogen
Gerade
Quadru- Pole
Quadru-Pole
ByPass
Cryo Nischen
straight section (warm connections)
Mechanical Completion
Tests und
Mechanical 2
Takt gem. Abstimmungen
LCM erstellt
Installationsbeginn Bogen 2 in KW39
Nach Kabelzugarbeiten
Beginn nach Vermessung und Nachjustierung
Typenweise Installation
Takt gem. Abstimmungen
Beginn nach Quadru-Pole Bogen Typenweise Installation
Takt gem. Abstimmungen
Tests und Mechanical 2 nach Quadru-Pole
Takt gem. Abtimmung
Fortsetzung Quadru-Pole Geraden
Typenweise Installation
Takt abhängig von Lieferterminen
Mechanical Completion
nach Fertigstellung aller Leistungen
In diesem Fall abhängig von Quadru-Polen in den Geraden

## Slide 6: AGENDA
Content
01
Status Quo Installation (Status 2024)
02
Status Quo delivery dates Quadru-Poles
03
Installation Plan Quadru-Poles (Status 09.2025)
04
Open Issues / to clarify
05
Next Steps
06

## Slide 7: SIS100 Workshop – Installation Plan Dipole and quadrupole
Status Quo delivery dates Quadru-Poles (delivery milestones M10-P in Planisware)
Basics / Boundary Conditions
  BNET36 is basis for definition of delivery milestones M10-P
  Technische Plätze (technical places) - information is assigned to each module in the installation plan
  3 weeks of non-working time at the turn of the year seam not to be included in the pre-assembly plan (to be claryfied)

## Slide 8: SIS100 Workshop – Installation Plan Dipole and quadrupole
Status Quo delivery dates Quadru-Poles (sequence according to delivery milestones M10-P)
2025
2026
2027
2028
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
Responsible
Type 2.123 S2
Straight
Type 2.123 S5
Straight
Type 2.123 S1
Type 1.7B B1-B6
Straight
Type 2.123 S6
Straight
Type 2.123 S4
Curve
Straight
Straight / Curve
Straight
Type 2.123 S3
Type 1.E / 2.4 S1-S6
Straight / Curve
Month
Type 1.6A B1-B6
Curve
Curve
Curve
Type 2.5 B1-B6
Type 2.8C B1-B6
Type 2.9 B1-B6
Activity

## Slide 9: AGENDA
Content
01
Status Quo Installation (Status 2024)
02
Status Quo delivery dates Quadru-Poles
03
Installation Plan Quadru-Poles (Status 09.2025)
04
Open Issues / to clarify
05
Next Steps
06

## Slide 10: SIS100 Workshop – Installation Plan Dipole and quadrupole
Installation Plan Quadru-Poles (Status 09.2025)
Start of Quadru-Pole installation
  02.2026 Start of installation Quadru-Poles
  according to installation plan Status 2024
Basics / Boundary Conditions
  3 weeks of non-working time at the turn of the year is included in the installation plan (manually due to missing calender with 3 weeks off)
  Technische Plätze (technical places) - information is assigned to each module in the installation plan
New Apporach of installation:
  Order of delivery (M10-P) defines order of installation (Status 09.2025)

## Slide 11: SIS100 Workshop – Installation Plan Dipole and quadrupole
Installation Plan Quadru-Poles (installation of quadru-pole modules)
2025
2026
2027
2028
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
Type 1.6A B1-B6
Type 2.123 S1
Straight
Type 2.123 S5
Type 2.5 B1-B6
Type 1.E / 2.4 S1-S6
Straight / Curve
Curve
Curve
Type 2.123 S2
Straight
Type 1.7B B1-B6
Straight / Curve
Type 2.9 B1-B6
Curve
Straight
Type 2.123 S3
Straight
Activity
Responsible
9/22/2025
Type 2.123 S4
Straight
Curve
Type 2.8C B1-B6
Straight
Type 2.123 S6
Month

## Slide 12: SIS100 Workshop – Installation Plan Dipole and quadrupole
Installation Plan Quadru-Poles (Free buffer time: delivery milestones and installation dates)
2025
2026
2027
2028
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
Straight / Curve
Curve
Type 2.5 B1-B6
Type 2.9 B1-B6
Type 1.6A B1-B6
Straight
9/22/2025
Month
Type 2.123 S2
Straight
Straight
Type 2.123 S5
Responsible
Straight
Type 2.123 S1
Type 2.123 S3
Straight
Curve
Activity
Curve
Type 2.123 S4
Straight / Curve
Straight
Type 2.8C B1-B6
Type 1.E / 2.4 S1-S6
Type 1.7B B1-B6
Type 2.123 S6
Curve

## Slide 13: AGENDA
Content
01
Status Quo Installation (Status 2024)
02
Status Quo delivery dates Quadru-Poles
03
Installation Plan Quadru-Poles (Status 09.2025)
04
Open Issues / to clarify
05
Next Steps
06

## Slide 14: SIS100 Workshop – Installation Plan Dipole and quadrupole
Open issues / to clarify (Status delivery until today)
2025
2026
2027
2028
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
9/22/2025
Type 2.123 S2
Straight
Straight
Curve
Type 2.123 S5
Straight / Curve
Straight
Type 2.123 S1
Straight
Type 2.123 S6
Month
Straight
Type 1.E / 2.4 S1-S6
Straight / Curve
Type 2.9 B1-B6
Activity
Responsible
Curve
Type 1.6A B1-B6
Type 2.123 S4
Straight
Curve
Type 2.8C B1-B6
Type 1.7B B1-B6
Curve
Type 2.123 S3
Type 2.5 B1-B6
Some milestones for the delivery of the modules have been achieved but are not yet completed (according do the status in Planisware).
Recommendation:
Confirmation of the status of past delivery milestones.

## Slide 15: SIS100 Workshop – Installation Plan Dipole and quadrupole
Open issues / to clarify (non-working time at the turn of the year)
2025
2026
2027
2028
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
Straight / Curve
Curve
Type 2.5 B1-B6
Type 2.9 B1-B6
Type 1.6A B1-B6
Straight
9/22/2025
Month
Type 2.123 S2
Straight
Straight
Type 2.123 S5
Responsible
Straight
Type 2.123 S1
Type 2.123 S3
Straight
Curve
Activity
Curve
Type 2.123 S4
Straight / Curve
Straight
Type 2.8C B1-B6
Type 1.E / 2.4 S1-S6
Type 1.7B B1-B6
Type 2.123 S6
Curve
Recommendation:
Add 3 weeks of non-working time at the turn of the year in pre-assembly (A10-P) and the M10-P Milestones for the quadru-poles.
All following M10-P Milestones are affected by that.

## Slide 16: SIS100 Workshop – Installation Plan Dipole and quadrupole
Open issues / to clarify (Section 1 – Type 2.123)
2025
2026
2027
2028
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
Straight / Curve
Curve
Type 2.5 B1-B6
Type 2.9 B1-B6
Type 1.6A B1-B6
Straight
9/22/2025
Month
Type 2.123 S2
Straight
Straight
Type 2.123 S5
Responsible
Straight
Type 2.123 S1
Type 2.123 S3
Straight
Curve
Activity
Curve
Type 2.123 S4
Straight / Curve
Straight
Type 2.8C B1-B6
Type 1.E / 2.4 S1-S6
Type 1.7B B1-B6
Type 2.123 S6
Curve
Delivery milestones vary considerably for Type 2.123 in Sector 1 (approx. 5 months).
Recommendation:
Clarification and confirmation of delivery dates for modules in all sectors.

## Slide 17: SIS100 Workshop – Installation Plan Dipole and quadrupole
Open issues / to clarify (Section 5 – Type 2.123)
2025
2026
2027
2028
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
Straight / Curve
Curve
Type 2.5 B1-B6
Type 2.9 B1-B6
Type 1.6A B1-B6
Straight
9/22/2025
Month
Type 2.123 S2
Straight
Straight
Type 2.123 S5
Responsible
Straight
Type 2.123 S1
Type 2.123 S3
Straight
Curve
Activity
Curve
Type 2.123 S4
Straight / Curve
Straight
Type 2.8C B1-B6
Type 1.E / 2.4 S1-S6
Type 1.7B B1-B6
Type 2.123 S6
Curve
Just 2 M10-P Milestones are defined for Sector 5.
Recommendation:
Clarify whether in fact only two quadru-pole modules (Type 2.123) will actually be installed in sector 5.

## Slide 18: SIS100 Workshop – Installation Plan Dipole and quadrupole
Open issues / to clarify (Interruption delivery milestones)
2025
2026
2027
2028
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
Straight / Curve
Curve
Type 2.5 B1-B6
Type 2.9 B1-B6
Type 1.6A B1-B6
Straight
9/22/2025
Month
Type 2.123 S2
Straight
Straight
Type 2.123 S5
Responsible
Straight
Type 2.123 S1
Type 2.123 S3
Straight
Curve
Activity
Curve
Type 2.123 S4
Straight / Curve
Straight
Type 2.8C B1-B6
Type 1.E / 2.4 S1-S6
Type 1.7B B1-B6
Type 2.123 S6
Curve
There are conspicuous, incomprehensible time slots between individual delivery dates for the modules
Recommendation:
Clarification of delivery dates and interruptions for the modules.

## Slide 19: SIS100 Workshop – Installation Plan Dipole and quadrupole
Open issues / to clarify (postponed delivery milestones of last modules)
2025
2026
2027
2028
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
Straight / Curve
Curve
Type 2.5 B1-B6
Type 2.9 B1-B6
Type 1.6A B1-B6
Straight
9/22/2025
Month
Type 2.123 S2
Straight
Straight
Type 2.123 S5
Responsible
Straight
Type 2.123 S1
Type 2.123 S3
Straight
Curve
Activity
Curve
Type 2.123 S4
Straight / Curve
Straight
Type 2.8C B1-B6
Type 1.E / 2.4 S1-S6
Type 1.7B B1-B6
Type 2.123 S6
Curve
The delivery dates for the final modules have been postponed compared to the installation plan (Status 2024). The installation dates will also be postponed accordingly.
The critical path for installation is defined by the delivery, installation and commissioning by the last modules.
Recommendation:
The delivery dates of the final modules must be checked and coordinated in detail with the suppliers.

## Slide 20: AGENDA
Content
01
Status Quo Installation (Status 2024)
02
Status Quo delivery dates Quadru-Poles
03
Installation Plan Quadru-Poles (Status 09.2025)
04
Open Issues / to clarify
05
Next Steps
06

## Slide 21: SIS100 Workshop – Installation Plan Dipole and quadrupole
Next Steps
Start / continuation of work preparation for the start of installation of the Quadru-Pole in February 2026.
Clarification of the topics highlighted in the previous slides.