## Slide 1: Commissiong SIS100
Peter Spiller
Picture 3. SIS100 workhsop

## Slide 2
Performance Changes
 | Technical modification or issue |  | Performance impact | Reason
1. | Reduced dipole power converter power |  | Reduced maximum ramp rate 4 T/s > 2.5 T/s | Cost saving
2. | Reduced number of quadrupole power converter |  | 3 circuits > 2 circuits, no irregular optical setting and gamma_t shift in p-operation | Cost saving
3. | Reduced number of acceleration cavities |  | Reduced maximum ramp rate | Cost saving
4. | Reduced number of bunch compression cavities |  | Enhanced bunch length after fast compression | Cost saving
5. | Restrictions in maximum HV voltage in pulse cables |  | Lower injection energy. Limited maximum fast extraction energy. | Technical limits. Availability on market.
6. | No appropriate technical concept for E-septum |  | Limited maximum avergae intensity to 3E11 u/s | Radiation hardness of e-septum wires
7. | Concept not approved. Evtl. KO feed back. |  | No suitable micro structure | 
No major performance and beam parameter change beside # 5.

## Slide 3
Most important open procurement packages:
Power Converter for Extraction Septum 2 + 3 (start of procurement in 2024)
Power Converter for Extraction Septum 1 + Lamberston Steerer
Power Converter for Fast Quadrupole + Power Converter for Radiation Hard Quadrupole
Power Converter for Lambertson Septum
Power Converter for Injection- and Extraction Quadrupole
Delivery of above PC may end in 2026-2027.
Quench detection cabinets and trigger matrices
Most critical day-one item in terms of technology development:
KO Exciter
Major technological change in comparison to SIS18 exciter based on new (transformer) approach.
Significantly delayed due to changing and leaving WPL in Ring RF.
KO extraction is reference slow extraction method.
Late Procurements
Consequently commissioning of above PC systems and corresponding magnets can not happen before 2026/2027.

## Slide 4
Late Procurements versus Early Beam Commissioning
General strategy:
All constructed space for late or non-day-one items is temperarily bridged by a beam pipe.
We attempt to procure all items of the cost book ! Priority in execution is set to the devices needed for beam commissioning.
In case they are available before beam commissioning, they will be installed or fed in later in dedicated shut downs (e.g. Q kicker, BTF exciter, broad band cavities, part of Halo collimation system). Most extreme case: EE kicker system consitsing of three modukles.
Last room-temperature items mechanical completion in 2027
Last cryogenic items mechanical completion in 2028

## Slide 5
Major Milestones SIS100 Commissioning:
2025 - Regular current feed processes for power converter and racks
(how do we proceed ?)
2025 - Establishing safety organisation for upcoming hardware commissioning and transistion in room/area responsibility..
2026 - First hardware commissionings with and without load. Especially SAT Ab of main power converter systems.
2027 - Continuation of hardware commissioning with and without load for late items.
2028 – Staged, first cool down and commissioning of local cryogenics, quench detection system and cryo industrial controls
2028 - SAT Ba of main power converter systems.
2028 - First commissioning of s.c. main magnet systems and s.c. corrector magnet sytems.
2028 - Implementation of first operation cycle and beam commissioning.
Commissioning - Major Milestones

## Slide 6
Commissioning of SIS100 – Draft Overview

## Slide 7
Safety Responsibilities
Safety Organisation has to be established before start of hardware commissioning:
Assumption:
Future „Anlagenbetrieber“ = „Anlagenverantwortliche“ (equipment operator embedded in dpt) = Present WPLs
„Sicherheitstechnischer Verantwortlicher STV“ (aea safety manager) embedded in division: . O. Ciosk or successor in Subproject SIS100/SIS18 (already communicated to SiSt)
Strahlenschutzbeauftragter (radiation protection officer) embedded in dpt. for Electrostatic – Septa (x-ray emitter)
Transfer of responsibilities.

## Slide 8
Hardware Commissioning Room Temperature Sections
Hardware commissioning for several technical systems is identical to all other subprojects e.g.
conventional power converter and magnet systems.
RT UHV system (with enhanced requiremens)
beam profile monitors, beam loss monitors etc.
Take-over of LCM planning from e.g. HEBT possible.
SIS100 specific hardware to be commissioned:
Injection- and extraction kicker systems
Electrostatic extraction septa
Rf acceleration and Rf compression systems
IPM monitor and Schottky system etc.
CT UHV system
Most of these systems have already been tested with final supply unit and load.

## Slide 9
AMP
LLRF
CAV
PSU
Commissioning Ring Rf
Development of commissioning procedures in testing hall.
Each one ACC and BC Cavities stay in testing hall until end of commissioining,

## Slide 10
Annahmen für alle Schritte:
die Umgebungsbedingungen für die Inbetriebnahme von Hochspannungsanlagen müssen erfüllt sein (Zugangskontrolle, Unterweisungen, etc.)
generelle Gebäude-Infrastruktur wie Steckdosen, Kommunikation (Internet, Kommunikation zwischen Versorgungs- und Maschinentunnel), sanitäre Einrichtungen muss funktionell sein
Zu beachten: Die Breitbandsysteme (Barrier Backet und Longitudinal Feedback), sowie das KO-System sind in diesem Umfang noch nicht enthalten. Ihre Inbetriebnahme wird erst später stattfinden.
Arbeitsschritt | Voraussetzung Medien | System | Arbeitsaufwand RRF Personal SIS100 Gesamt [Personen-Tage] | Arbeitsaufwand RRF Personal 1S4 (6xACC + 3xBC) [Personen-Tage]
Vakuumtest CAV | von VAC zu definieren | ACC | 31 | 13
 |  | BC | 20 | 7
Stand-Alone-Inbetriebnahme PSU | Geschlossene Luftkühlung, elektr. Leistungsversorgung und Erdung | ACC | 455 | 195
 |  | BC | 293 | 98
Stand-Alone-Inbetriebnahme CAV+AMP | Kühlwasser | ACC | 380 | 163
 |  | BC | 293 | 98
Stand-Alone-Inbetriebnahme LLRF | elektr. Leistungsversorgung und Erdung | ACC | 571 | 245
 |  | BC | 367 | 122
Inbetriebnahme HF-Station | alle aus Stand-Alone-Tests + Nutzerkabel, Strahlenschutzfreigabe | ACC | 2510 | 1076
 |  | BC | 1614 | 538
Inbetriebnahme HF-System | alle aus Inbetriebnahme HF Station + Kontrollsytem, Timing | ACC | 1134 | 486
 |  | BC | 729 | 243
Commissioning Ring Rf

## Slide 11
Estimated total commissioning effort: ca. 8000 FTE x d
2025: Development of commissioning procedures at the Ring RF test stand in
testing hall. Documentation of procedure.
Commissioning of LLRF requires expert know-how and can not be shared with externals ! 9 FTE of REL will work continuously for commissioning of SIS100 LLRF.
In total 16 FTE of Ring Rf will work for SIS100 Ring RF commissioning full time for 2 years.
Contracting of manufacturer for cavity commissioning, e.g. for finding and analysing faults.
Focusing on acceleration cavities (no user for bunch compression systems yet).
Establishing of base funtionality and setting of of priorities (e.g. less flexibility).
FESA class development can be started in 2025. Testing from 2026.
Commissioning Ring Rf
>We need to start with hardware commissioning in 2026
>Can we defined „mechanical completion“ on the level of systems ?

## Slide 12
General:
The overall equipment commissioning duration has to be estimated taking into account the estimated duration per device, the number of devices and the available number of experts. Is there work which can be done by externals/non-experts ?
e.g. PC 1 day per PC x 300 devices = 300 days
> Hardware commissiong procedures have to be launched early enough.

## Slide 13
Commissioning of Main Power Converter
Commissioning of main power converter will start in April 26 finally using the dummy loads, and will be interrupted by 2-2.5 years and will end with the magnet string in cold state.
Commissioning will be conducted in frame of the SAT process by GE/Vernova in collaboration with the subproject SIS100/SIS18. Especially in close interaction with dpt. EPS (WP leader V. Plyusnin, H. Welker) as potential future „Anlagenbetreiber“.
After SAT Ab with dummy load, the power converters have to be maintained by regular powering etc. until final commissioning with magnet string (SAT Ba) and operation (delay generates additional cost).

## Slide 14
Commissioning of Main Power Converter

## Slide 15
Commissioning of Main Power Converter

## Slide 16
dipole module
DPM #16
dipole
module DPM#26
quadrupole
module QDM type 2.5
end box (EBx)
end cap (EC)
with CWT
RT
pumping
chamber
He supply
bypass line (BPL)
Feedbox
LHe supply
SIS100 String test serves as a crucial preparatory for the installation, commissioning and operation of the SIS100 accelerator
Main purposes are:
establishing installation sequence and procedures
verification of design and interfaces
preparation of work procedures and quality assurance
validation of the cryogenic system
quench and protection study
powering behavior of the system
functionality of the beam and insulation vacuum system
accelerator relevant operation
SIS100 arc segment
String-Test

## Slide 17
SIS100 LSA Set-value Generation
ParaModi window for SIS100 magnet cycle.
Operation of stringtest power converters using set-values generated by LSA.

## Slide 18
SIS100 Industrial Local Cryo Controls
Excellent progress and status in development of industrial controls for SIS100. Technical information, e.g. the data of >1600 temperatir sensors have been provided to industrial controls early.
Feed box 1 visulization (ready for cold testing in 2025
End box visualization
Endbox Box
  Cabinet status: Delivered
  Functional analysis status: In progress
  PLC software status: Completed / Semi-Automatic process
  HMI software status: Visualized
Feed Box
  Cabinet status: Delivered
  Functional analysis status: In progress
  PLC software status: Completed / Semi-Automatic process
  HMI software status: Visualized
Operation of stringtest and planned cold test of FB1 are pushing the development of LSA and industrial controls.

## Slide 19
SIS100 Industrial Locak Cryo Controls
Sector
  Cabinet status: Design starts presumably in October
  Functional analysis status: In progress
  PLC software status: In progress / Test ongoing with StringTest
  HMI software status: In progress / Visualisation ongoing with StringTest
Sector visualization

## Slide 20
SIS100 Industrial UHV Controls
Status
  Cabinet status: 12 delivered, 10 in production / Delivery in 2024
  PLC software status: Completed
  HMI software status: Visualized / Based on UNILAC and HEBT

## Slide 21
First Cool-Down
Separation of functional sections via feed-boxes.
Pre-Condition: Commissioning of cryo plant and cryo distribution system
All instruments and valves are online in controls SCADA and test/verification at warm / atmospheric pressure (IND + CRY, 10 min per channel) => 50 days (2 people) completed.
Pumping and purging of insulation vacuum system completed (can only be done after full integration of cryomagnetic system) 2 weeks per sector.
(Risk of leak in insulation vacuum system (telescopic bellow system)
which may delay cool-down.)
HV and continuity test of quench detection circuits.
Cool-down and cold tests (regulation loop adjustments, etc.) of two of six sectors (12 Wochen).
Cool-down and cold tests (regulation loop adjustments, etc.) of all sector (8 Wochen).
Requires full integration of local cyo systems with LHe transfer line.(end of 2027)

## Slide 22
Hardware Commissioning after First Cool-Down
LCL heater commissioning.
Commissioning of corrector power converter with magnet load.
SAT Ba of main power converter.
> First static main magnet powering.
> First main magnet powering with ramps.
Magnet quench training.

## Slide 23
First Cool-Down . Quench Detection System

## Slide 24
First Cool-Down – Quench Detection System

## Slide 25
First Cool-Down – Quench Training
Quench training may be skipped ?

## Slide 26
Beam Commissioning
Low Z and moderate intensity light ion
a) need to be visible on BI systems
b) should have no damage potential in case of complete uncontrolled loss)
c) beam loss should be clearly correlated with technical issues
(no intrinsic physical beam loss mechanisms due to space charge, current and charge state)
E.g. 109 ions/cycle of Ar10+ - no partially charged heavy ions like U28+
No Protons because of activitation.
Single injection (no stacking) at reference rigidity (18 Tm)
Prefered ion species for injection into SIS100

## Slide 27
Limiting stress to s.c. magnet and crygenic systems
Start cycle at reference injection magnetic regidity (18 Tm).
End cycle at 2/3 of maximum magnetic rigidity (e.g. 60 Tm).
Limited ramp rate, e.g. 0.5 T/s up and 2.5 T/s down and 1 s plateau.
Fast extraction onto SIS100 underground beam dump with slow extraction optics.
Setting SIS18 extraction and optimizing transport and matching with beam on injection dump.
Deflecting beam into SIS100 plane for injection.
Injection kicker system setting for deflecting the beam on reference orbit.
Section-by-section transport of beam from first-turn-chamber to first-turn-chamber.
Injection of two bunches without Rf capture (bunched > coasting beam).
Later: Injection of four batches with stacking. Commissioning and test of bunch-to-bucket transfer.
First indications for cross talk and issues with magnetic field precision.
Beam Commissioning

## Slide 28
 |  | Loss@4 K | Loss@50 K | Wall plug Power
Total Loss in magnet system DC no current (incl. current leads) |  | 1.969 kW | 7.895 kW | 0.863 MW
Additional Loss in magnet system DC full current (incl. current leads) | RIB cycle U28+ (Table I-1.2.1.) | 1.703 kW | 2.274 kW | 0.752 MW
Additional Loss in magnet system AC triangular current (incl. current leads) | triangular cycle U28+ 0.25 Intensity | 10.702 kW | 6.556 kW | 3.9 MW
Static and Dynamic Heat Load
The head load in SIS100 is dominated by AC loss (fast ranping) and depends a lot on the magnet cycle.
In the commissioining phase an apropriate setting for the magnet cooling has to be developed assuring a sufficiently low temperature over the full magnet string and an most energy efficient operation (two phase cooling > no liquid in return header).
Possible adjustments via supply header pressure, Helium pumps in FB and heaters in parallel magnet hydraulic circuits.
First experimental studies with the heaters of the string test magnets started. Heater control needs to be supported by physical models (systems design,croy):

## Slide 29
Machine: (single user operation) Development of machine cycle with appropriate local cryo settings for first NUSTAR cycle.
User: First limited single cycle user (NUSTAR) beam time.
Machine: (single user operation) Development of machine cycle with appropriate local cryo setting for first CBM cycle.
User: First limited user beam time (CBM).
Machine: Development of parallel operation.
Long term : Development of fully flexible operation (like room temperature synchrotrons), with heat load prediction and coupling of LSA with cryo controls.
Preparation of Regular User Operation

## Slide 30
Evolution of SIS100 Klausur
2020/22: SIS100 Procurement
2023: SIS100 From Procurement to Installaton
2024: SIS100 Procurement and Installation
2025: SIS100 From Procurement and Installation to Commissioning