## Slide 1: Draft Concept for Beam Commissioning
D. Ondreka, GSI (SYS)
4th SIS100 Workshop, 24 September 2025

## Slide 2: Contents
Goals
Conditions
Strategy
Preparations
Cycle

## Slide 3: Goals
Testing each individual component with beam
Establishing proper functioning of SIS100
Validating machine protection systems
Preparation of first NUSTAR experiment in FS
Cycle for U28+,1.5GeV/u, 4 injections, 2s extraction

## Slide 4: Annual Schedule 2028
user beam time
129 days (3096 h)
machine time
13 days
FAIR HEBT & SIS100
beam
commissioning
Early Science
physics
(Source: S. Reimann, Beam Time Retreat 2025)

## Slide 5: Conditions
Pre-conditions
  Machine cooled down
  Hardware commissioning finished
  Cryo system tuned for commissioning cycle in dry run
  Operational and commissioning tools tested in dry run
Expected boundary conditions
  Six weeks of exclusive operation for SIS100 BC
  Six weeks of shared operation with physics run at SIS18
  Commissioning only during day shifts (F, S)
    Limited personnel (machine experts)
    Frequent interventions by technical groups expected
  Semi-automated test-procedures maybe run over night

## Slide 6: Organization: Commissioning Team
BC manager (+ deputy)
  Organizes and coordinates commissioning program
  Authorizes major program changes in response to issues
BC leader (machine experts, weekly turn, overlap with SIS18 on-call)
  Responsibility for execution of commissioning
  Coordination of commissioning activities
  Reporting in daily commissioning meeting
BC shift crew (machine experts, operators)
  Execution of commissioning
  Experts for difficult tasks, operators for systematic checks

## Slide 7: Strategy: Commissioning Tracks
Fast track (‘pioneers’)
  Try to get beam through machine as fast as possible
  Ignore non-functional devices if not critical (but document the fact)
Main track
  Systematically check all devices, follow-up on non-functional ones
  Document achieved intermediate results
  Establish commissioning, set-up, and tuning procedures for operation

## Slide 8: Commissioning Sequence (I)
Beamline from SIS18 to SIS100
  Main goal: beam spot on injection screen/grid with correct parameters
  Steering, optics verification
First turn in SIS100
  Main goal: loss-free transport around circumference up to injection point
  Beam steering using BPMs and first-turn grids
Circulating beam at injection level
  Main goal: prepare systematic measurements
  Options for injection
    Bunch-to-coasting and bunching in SIS100
    Bunch-to-bucket
  Beam deposition at injection energy on collimator using orbit bump
Systematic measurements
  Main goal: validate and establish proper functioning of correctors and BI
Correction of closed orbit and tune
  Main goal: establish correct optic and good orbit for further steps

## Slide 9: Commissioning Sequence (II)
Commissioning of fast/emergency extraction
  Main goal: establish simple way to dispose of beam
  Useful for systematic tests of everything except SX
Commissioning of acceleration
  Main goal: establish accelerated beam
  Test of synchronicity of acceleration RF (among cavities and with magnets)
Commissioning of slow extraction
  Main goal: establish slow extraction with high efficiency
  Expected to be most challenging step due to strong non-linearities
  Quick shot based on design settings shall be tried
  Systematic approach with simpler schemes will be prepared

## Slide 10: Preparations
Development of commissioning procedures
  Description of steps to be executed in the commissioning sequence
  Include input and exit conditions and define criteria for fulfillment
Development of software tools for commissioning
  Necessary due to large size of SIS100 for efficient commissioning
Tool | Purpose
First-Turn Steering | Steering based on single-pass BPM data
Closed Orbit Correction | Correction of closed orbit based on multi-pass BPM data
Tune Measurement | Measurement and correction of machine tune Measurement and correction of chromaticity Validation of sextupoles Validation of octupoles?
ORM Measurement | Validation of steerers and BPMs Validation of optics Validation of octupoles?

## Slide 11: Commissioning Cycle
Boundary conditions
  Heat load must correspond to experiment cycle
  Flat-top rigidity in experimental range
  Reasonably short cycle time for commissioning
Expectations for first NUSTAR experiment
  U28+, 1 – 1.5 GeV/u, <1011/spill
  ES intensity limit: 2∙1011, 2s extraction, 4s cycle
Proposed cycle
  Flat-top rigidity: 50 Tm
  Duration: 4 – 5 s
  Flexibility in defining flat-bottom/flat-top length
  Low charge state ions to lower energy (Ar10+: 3 GeV/u, Kr16+: 2 GeV/u, U28+: 1 GeV/u)
    Minimization of activation (interventions!)
    Better control of SX losses (collimation system!)
Cycle for U28+,1.5GeV/u, 4 injections, 2s extraction
Cycles with identical heat load

## Slide 12: Summary
Goals, preconditions, organization, and strategy sketched
Coarse commissioning sequence presented
Procedures and tools need to be developed
Thanks for your attention!