Session Chair Template for Documentation of Action Items

Niels Pyka, Session 3

| Workpackage | Required Action/Activity | Activity Owner | Due Date |
| --- | --- | --- | --- |
| NC-Magnets |  | Rottländer |  |
| Fast quad | Some mech. rework; doc as res. sext.; | PRo | tbd |
| Inj. Septa | Fast interlock system from ex-septa; some minor rework; engineering time for integration? | PRo | tbd |
| Rad. res. Quads | Vac-chamber, collimator, pumping chamber; exchange of weld-on flanges, assembly | Pongrac Bozyk | tbd |
| Lambertson Septum | NEG coating of VAC chamber (SAES) – add. costs; add. pumps during SAT nec.? | GSI -Elytt, Pongrac | tbd |
| Ex. septa 1+2 | Add. pumps | Pongrac | tbd |
| Ex. septum 3 + Lamb. steerer | Add. internal beam dump; Add. pumps; NEG coating; | Martin, Pongrac | tbd |
| Power converter |  | Plyusnin |  |
| PC | Several PC to be procured -> DS to be prepared; |  | tbd |
| RRF |  | Laier | tbd |
| BC | Power supplies to be installed by OCEM; | Zipfel | tbd |
| Broadband systems | Technical concept in preparation; | Frey | tbd |
| KO Exciter | Technical concept in preparation; | Orth | tbd |
|  | Installation support by external companies necessary; | RRF | tbd |
|  | Conditioning of RF components is urgend; | Ciosk | tbd |
|  | Commission one complete system as fast as possible; | SMG | tbd |
| LLRF |  | Lens |  |
| OTS system | Development necessary |  | tbd |
| SiC gap switches | Call for tender ongoing (development contract); prototype existing |  | tbd |
|  | Cabling within supply areas by ELC or AÜG |  | tbd |
|  | 2 technicians AÜG for support remaining work at LLRF stations |  | tbd |
|  | Start LLRF commissioning with all media latest in Q4/2026 | SMG | tbd |
| Laser cooling system |  | Winters |  |
|  | Continuation of the installation at the ceiling; | TRI | tbd |
| RHV |  | Petzenhauser |  |
| I-Kicker | 2nd injection kicker module necessary; new cables with better el. isolation; | IPe; Company RI |  |
| EE-Kicker | New cables with better el. isolation; | IPe; Company RI |  |
| NC-VAC |  | Zeller |  |
|  | Beschaffung schnelle Ventile | Pongrac |  |
|  | Beschaffung große, „normale“ Ventile Inj/Ext | Pongrac |  |
|  | Sektor-1 Zellen 1+2 change of the empty tubes necessary, meeting 7.10.2025 | Pongrac |  |
| Special Installations |  | Bozyk |  |
|  | Temporary replacement of the “kicker-hat” with collimator for slow extracted ion beams? Fast drives necessary; |  |  |
| BEA |  | Kowina |  |
|  | Delays due to reduction of ressources: ES (SFRS, HEBT) |  |  |