Session Chair Template for Documentation of Action Items

| Workpackage | Required Action/Activity | Activity Owner | Due Date |
| --- | --- | --- | --- |
| SMG Installation SIS100 | Analysis of preconditions for installation of the machine components | N. Pyka |  |
| Electrical Installations | Align the cabling activity sequence with the machine installation planning | H. Welker |  |
| Electrical installations | Evaluate possibilities to further decouple machine installation and cabling works | H. Welker + N. Pyka |  |
| SMG | Revise strategy for fire protection wall installations with respect to the positioning of the machine | J. Kollarczyk |  |
| IFJ Pan | Develop inspection plans for mechanical tests of the telescopic balg connections of the SC magnet interconnections | M. Sienkiewicz + SCM |  |
| SMG | Detail the resource planning for installation activities | J. Schmidt + GSI departments |  |