Action Items, Session 4, Commissioning	V. Kamerdzhiev

| Workpackage | Required Action/Activity | Activity Owner | Due Date |
| --- | --- | --- | --- |
|  | Clarify the ladder issues | H. Hagelskamp |  |
|  | Define Anlagenzuständige | SPL/deputy |  |
|  | Define STVs | SPL/deputy |  |
|  | Define a radiation protection responsible person | SPL/deputy |  |
|  | Define the entire safety organization for SIS100 commissioning | SPL/deputy |  |
|  | Find a way to ensure the insulation vacuum is leak free, mitigate risk |  |  |
|  | Find out if quench training is to be performed |  |  |
|  | track closely, WC bus bars for main supply on critical path, | V.Plyusnin |  |
|  | Establish/prepare automated commissioning procedures in advance | SYS |  |
|  | Consider and prepare in advance additional modes for beam instrumentation | SYS, BEA |  |
|  | Act on the basis of the current keep-alive list ASAP | O.Ciosk |  |
|  | Complete the keep-alive list, update regularly | O.Ciosk |  |
|  | Organize kickoff meeting for SIS100 commissioning | SIS100 FCM |  |
|  | Consider collaborations with other Helmholtz Institutions, also international institutions on specific topics of installation and commissioning. Exchange of personnel with specific qualifications for limited time, weeks/months to resolve critical issues, e.g. welding | SPL/deputy GF |  |