## Slide 1: Summary of the commissioning session
4th SIS100 Workshop
V. Kamerdzhiev, 24.09.2025

## Slide 2: Project interfaces
Structure and interfaces explained
The website https://www.gsi.de/work/gesamtprojektleitung_fair/site_management_smg/maschinenmontage
    contains a lot of usefull information
    is updated frequently
Contact person for all questions regarding installation:
  in the machine tunnel - Jan Kollarczyk
  in the aux. tunnel - Mike Draisbach

## Slide 3: General considerations for FAIR commissioning
Expectations from FAIR Commissioning team briefly communicated
Need to start the detailed discussion on SIS100 commissioning ASAP
  kick-off meeting
  establish safety organization
  …

## Slide 4: General considerations for SIS100 commissioning
2027 mechanical completion for room temperature components
2028 mechanical completion for cryo components
need to continue the collaboration with JINR and work together with europian industry
Start first commissioning activities in Apr. 2026
  Main PC, jointly with GE
  other HW commissioning

## Slide 5: Status availability and commissioning of technical building infrastructure
The work is progressing well
The TBI prios/schedule can be realigned to certain extend if there are strong reasons to do so. --> requires open communication on what is really needed when

## Slide 6: Intermediate powering needs
the generation of the keep-alive list is well under way
  good support by numerous departments
  need further support to keep the list up-to-date
no need to wait for the completion of the list to take action
  agreement on immidiate action on the basis of the current version