## Slide 1: Schedule for SC Unit and Module Manufacturing until Completion incl. Risk Scenarios
4th SIS100 workshop – procurement and installation| Kloster Eberbach | September 22, 2025
Christian Roux

## Slide 2: Outline
status overview
JINR deliveries
risk assessment: termination scenarions
BNET36: QPUs from industry
conclusion

## Slide 3: project status

## Slide 4
22 % of FATs
Position in ring |  | Quadrupole unit pairs |  |  | Delivered QPUs |  | Quadrupole doublet type (QDM) | FAT accepted
 |  | QPU1 | QPU2 |  |  |  |  | 
Arc |  | VQD | SF2B |  | 12 / 12 |  | 2.5 | 5 / 6
 |  |  |  |  | Spare: 0 / 2 |  | - | -
 |  | VQD | SF1B |  | 24 / 24 |  | 1.7B | 12 / 12
 |  | BQD | SF1H |  | 22 / 24 |  | 1.6A | 1 / 12
 |  | BQD | SF2H |  | 0 / 24 |  | 2.8C | 0 / 12
 |  | BQD | SF2J |  | 0 / 24 |  | 2.9D | 0 / 12
Arc termination (+ special) |  | QDBb | SF2M |  | 0 / 10 |  | 2.4 | 0 / 5
 |  | MQD | SF1Bb |  | 0 / 10 |  | 1.E | 0 / 5
 |  | QDBx | SF2Mx |  | 0 / 2 |  | 2.4x | 0 / 1
 |  | MQDi | SF1Bi |  | 0 / 2 |  | 1.Ei | 0 / 1
Straight |  | QDB | SF2 |  | 0 / 28 |  | 2.123 | 0 / 14
 |  | QDB | SF2s |  | 0 / 6 |  | 2.13s | 0 / 3
 |  | Total: |  |  | 58 / 166 (+0 / 2 spare) |  | Total FATs: | 18 / 83
QPUs and QDMs: (production) status
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
35 % of QPUs
108 QPUs
to go
65 QDM
FATs
to go

## Slide 5
Detailed information on progress, see
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
Quadrupole units
QPU production and testing at JINR – J. Ketter
Plan B
  QPU prototype production at BNET – J. Ketter
  Test equimpent for QPUs from BNET – A. Szwangruber
Quadrupole doublet modules
QDM integration – T. Winkler
QDM testing – A. Chiuchiolo
QDM non-conformities – M. Janke
Notes: produktionsqualität
offene technische Aspekte

## Slide 6
QPUs and QDMs: baseline schedule (after 2022) and status
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
VQD | SF1B
BQD | SF1H
BQD | SF2H
QDB | SF2
QDB | SF2s
BQD | SF2J
QDBb | SF2M
MQD | SF1Bb
QDBx | SF2Mx
MQDi | SF1Bi
JINR:
production and testing following schedule (minor issues, see dedicated talk)
complicated logistics causing effort and delay of few months (see below)
( )6
( )
BNET:
delay of several months apparent (note: 3 FATS announced but not yet accepted)
several factors contributing to delay, see talk T. Winkler
Common schedule already under pressure. Further delays to be avoided
Notes: letzte Lieferung:
1.6A: zwei nicht dicht
daher sollte die zwei 2.5
hier Genehmigung nicht i.O.
Daher nur 6

## Slide 7: JINR deliveries

## Slide 8
Interaction with JINR: authorization
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
typical document set:
Contract Addendum
JINR – FAIR/GSI
End User Certificate
JINR
Authorization document
BAFA
Technical documents
GSI
FAIR Ausfuhrkontrolle
iterative
iterative
iterative
To be „adjusted“ to sanctions
(e.g. Alumium walls at boxes)
iterative
„Refreshment“ needed after new sanction package even without change in relevant restrictions
Notes: logistics umreisen
Probleme mit Beispielen
Aktueller Status

## Slide 9
Authorization status
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
direction | Article | amount | Comment | BAFA
JINR → FAIR | Units | 140 | - | Authorization available
Both | Transport boxes | 10 | Complications: Wooden walls Aluminum walls Boxes in different conditions with different authorization documents | 
FAIR → JINR | HTS interceptions | 20 pcs | - | BAFA approval available
 | Cold terminals | 220 pcs | - | BAFA approval available
 | Temperature sensors | 350 pcs | - | BAFA approval available
 | Gamma-t jump magnets | 12 pcs | Critical supply Long time scales for re-procurement if needed. | Application in preparation but not yet submitted
 | Gamma-t jump power supply | 1 pc | Critical supply | Application in preparation but not yet submitted to BAFA
 | Corrector wire (superconducting) | ≈ 50 km | Critical supply Long time scales for re-procurement if needed. Availability not guaranteed. | 
 | Units for „repair“ | tbd | Was available for two units | Not available
Notes: logistics umreisen
Probleme mit Beispielen
Aktueller Status

## Slide 10
QDM (QPU) type | # | Planned delivery | Customs clearance in Germany | Total transport time (months) | Schedule delay (months) | comment
1.7B (VQD, SF1B) | 4 | 04-2024 | 06.05.2024 | 0.5 | 1 | First clearance after interruption, minor iterations at customs office (few days)
1.7B | 4 | 09-2024 | 14.10.2024 | 0.5 | 1 | Smooth transport
1.6A (BQD, SF1H) | 8 | 12-2024 | 17.02.2025 | 2 | 2 | Two approaches at EU border, delay at German customs office; Speed up in production (few weeks) „eaten“ by logistics
1.6A | 8 | 03-2025 | 02.06.2025 | 0.5 | 3 | Major delay in start of transport due to iteration of authorization for boxes; Two units rejected
1.6A | 6 | 05-2025 | 21.07.2025 | 0.5 | 2 | Speed up in production beneficial
TOTAL | 30 |  |  |  |  | 
QPU deliveries after 2022
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
complications (examples):
(wall) material of transport boxes: wood, Aluminum, steel → iteration of authorization needed each
wording: „units“ on authorization but „magnet“ on shipment document → assessment at custom authorities
change of sanctions makes existing authorization invalid (last minute)
delay kept „acceptable“ only due to major effort

## Slide 11
Risk factors
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
Geopolitics
Logistics vs. sanctions
logistics dominates schedule: delay might develop severely out of our control
Authorizations are expiring. New sanction packages might cancel given authorizations. No guarantee for re-issuing
BAFA allowances not fully available yet
Repairs complex to organize (special authorization needed)
Supply situation JINR
PS failures: repair challenging
Yokes: so far 4 out of 62 rejected for insufficient field quality. No spare yokes available. Re-production in Minsk not taken into account
Technical
complex units with new technology upcoming, technological iteration expected
  SF2F: integration of Gamma-t magnet as FAIR supply. Cold testing with PS as FAIR supply
  MQD, SF2M: units with two correctors where multipole (three nested coils, …) is one of it
no personal visits → extremely challenging coordination and quality assurance
Multiple risks over project time span of two years
Notes: produktionsqualität
offene technische Aspekte

## Slide 12
Impact on science program
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
The scientific impact of a delayed start of the user program in a competitive environment of world-wide research is critical (and not accounted below)
Young researchers adapt their research activities according to their personnel career optimization
FAIR is in competition: there is a number of other facilities offering excellent conditions for research in equivalent fields. There is also a number of new competitive facilities on the path to completion (e.g. HIAF in China, NICA Russia).
Notes: produktionsqualität
offene technische Aspekte

## Slide 13: risk analysis and mitigation

## Slide 14
Risk mitigation – Manufacturing capacities in industry (Plan B)
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
MAC Recommendation
R26.3: Continue with the plan to build quadrupoles in industry with high priority until all quadrupoles needed for SIS100 completion are accepted and the risk can be retired.
  Consequences
  Additional resources load at GSI.
  Magnetic field measurement equipment has to be developed an procured (stretched/vibrating wire, rotating coil, anticryostat…).
  Series testing cryostat with LCL and anticryostat has to be developed and procured.
  Occupation of one or more feed-boxes for the period between Q1/2026-Q4/2027
  Status
  Collaboration contract with CERN on magnetic field measurement equipment signed.
  Major components of the stretched wire system ordered.
  Rotating coil under development in collaboration with CERN.
  Design and production of two testing cryostats awarded to Fantini.
  Anticrostat awarded to ILK Dresden.
  Overall amount of resources and equipment needs depends on the number of units produced in industry.
Fallback-plan (FAIR Council)
Material: re-procurement of steel and sc wire for full series (plus further goods)
Production technology and tooling at BNET – see talk J. Ketter
  four prototype units ; production completed
  two multipole correctors (two types)
Testing capabilities at GSI – see talk A. Szwangruber
  test cryostat with anti-cryostat
  field measurrment devices (wire, rotating coils), in collaboration with CERN

## Slide 15
Remaining deliveries: risk assessment
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
Termination scenarios: (virtual) sudden stops of deliveries from JINR
special focus: status of deliveries from FAIR, especially for critical supplies with long procurement times
(→ Gamma-t, corrector wire)
Notes: die Prototypen werden gebaut, um den Falle eines Abbruchs „einigermaßen“ abzusichern.
Aber was passiert dann. hier die Studie: Termination mit Prototypen

## Slide 16
Schedule analysis: termination scenarios - baseline schedule
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
Termination: 07/2025 – Total: 108 QPUs from industry
End: 09/2029 – SIS100 delay: 20 months
Needs:
(all) missing to be produced at BNET
Analysis taking into account:
Resume phase of QPU production and QDM integration at BNET
QPU production and testing rates
(re-)procurement of FAIR supplies
QPU pairing at integration
Note: arbitrary reference point to make schedules comparable. Not necessarily official milestone of SIS100 project plan

## Slide 17
Schedule analysis: Testing of QPUs from BNET
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
Strategy
all QPUs from BNET need to be cold tested at GSI
enormous additional load on ressources:
  personnel
  STF
  equipment
maximum rate not easy to estimate. Here: 3 QPUs/month
possibly limiting supply chain
effort depends on total amount of QPUs from BNET
(also relevant for BNET36, see below)
BNET: QPUs → GSI: Cold Testing → BNET: QDM integration

## Slide 18
Schedule analysis: termination scenarios - baseline schedule
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
Termination: 07/2025 – End: 09/2029 – Delay: 20 months
Termination: 01/2026 – End: 10/2029 – Delay: 21 months
Termination: 07/2026 – End: 09/2029 – Delay: 20 months
Termination: 05/2027 – End: 11/2029 – Delay: 22 months
without further measures:
delay of ~ 20 months to be expected over the whole span of the remaining QPU production
108 QPUs from BNET
82 QPUs
from BNET
52 QPUs
from BNET
12 QPUs
from BNET
18
108 QPUs from BNET
82 QPUs
from BNET
52 QPUs
from BNET
12 QPUs
from BNET
major project delay along the whole project span: ~ 20 months even with prototypes from BNET
Notes: hier muss die Aussage sein, dass dies die Erwartung „trotz Prototypen“ ist.

## Slide 19: BNET36 (and BNET24)

## Slide 20
BNET36: suggested planned QPU production at industry
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
QPUs at BNET, planned
(instead of JINR)
24 QPUs for 2.4(x), 1.E(i) → multipoles
12 QPUs for type SF2J
→ Gamma-t magnets
PRO 1: shortening dependeny on deliveries from JINR (~1 year)
PRO 2: active QPU production at BNET allowing fast transition/extension if required
PRO 3a: most complex units to be produced nearby (multipoles, Gamma-t)
PRO 3b: critical supplies do not need to be supplied to JINR (Gamma-t, corrector wire)
PRO 4: potential earlier completion of QPU production due to parallelisation
PRO 3
PRO 1
PRO 2
PRO 4

## Slide 21
Schedule advantage BNET36 (example scenario 3)
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
Baseline (QPUs from JINR only): 20 months delay
long ramp-up phase at BNET
critical supplies to re-procured
significant delay of QDM integration
BNET36 (QPUs from JINR + BNET): 4 months delay
fast switch: BNET can produce remaining QPUs quickly
critical supplies available
→ almost full mitigation of project delay
significant shorter ramp up with BNET36

## Slide 22
Schedule advantage BNET36: summary
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
With BNET36, the project completion schedule of SIS100 can be secured. Major benefit over baseline scenario

## Slide 23
BNET24
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
QPUs at BNET
(instead of JINR)
24 QPUs for 2.4(x), 1.E(i) → multipoles

## Slide 24
Schedule advantage BNET36 and BNET24
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
Favoring BNET36:
BNET36 offers a schedule advantage compared to BNET24 in terms of schedule risk mitigation
Gamma-t magnets and PS would need to be sent to JINR for BNET24 (note: BAFA for PS not available)
Favoring BNET24: less invest

## Slide 25
SIS100 (FAIR) delay
personnel
running costs
Site management
mitigation measures
multi-risk insurance
…
Cost drivers: termination scenarios
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
risk budget
QPU production + QPU testing (devices + ressources)
QDM follow-up
missing QPU supply leads to delay and extension of QDM integration period
FAIR supplies: (re-)procurement
Gamma-t magnets
SC wire
Interceptions
Cold terminals
Temperature sensors
major contribution
major contribution
(at early termination: many QPUs from BNET)

## Slide 26: conclusion

## Slide 27
Summary: risk mititagion with BNETxx
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
Scenario | Termination date | Contracting of industry units in 2025 | Total QPU production in industry (#) | Total additional costs | Benefit BNETxx (comparison to baseline) | 
 |  |  | # |  | Cost avoidance: Total costs baseline – total costs BNETxx (M€) | Time saving: delay baseline – delay BNETxx (months)
1 | 07/2025 | no | 108 | 93.5 |  | 
2a | 01/2026 | no | 82 | 84.0 |  | 
2b |  | BNET36 | 36 + 46 | 67.6 | 16.4 | 7
2c |  | BNET24 | 24 + 58 | 72.1 | 11.9 | 5
3a | 07/2026 | no | 52 | 71.3 |  | 
3b |  | BNET36 | 36 + 16 | 33.3 | 38.0 | 16
3c |  | BNET24 | 24 + 28 | 45.5 | 25.8 | 11
4a | 05/2027 | no | 12 | 56.6 |  | 
4b |  | BNET36 | 36 + 0 | 18.5 | 38.1 | 22
4c |  | BNET24 | 24 + 0 | 13.1 | 43.5 | 22

## Slide 28
Summary: risk mititagion with BNETxx
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
Major schedule advantage with BNETxx
with contracting a sub-series at BNET in 2025, the timeline of SIS100 (FAIR) can be secured for termination of deliveries from JINR.
Major cost avoidance with BNETxx
BNET36/BNET24 offer huge costs savings for FAIR in case of termination of deliveries from JINR
In view of the overall situation, contracting of BNET with a sub-series of QPUs (favorable: BNET36) is highly suggested in terms of risk mitigation for FAIR

## Slide 29
Summary: risk mititagion with BNET36
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
contracting of BNET36 is highly suggested and pushed forward
it offers a MAJOR schedule and cost advantage compared to the baseline scenario and to BNET24 in terms of risk mitigation

## Slide 30: Thank you

## Slide 31
Summary risk analysis
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections

## Slide 32
import / export
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
Transport/logistic process
The „ready for integration“ date at BNET of the quadrupole units for integration into quadrupole modules is less determined by the production at JINR rather than by the difficult import- and export conditions.
(The present delay of three months is a result of a transport/logistic process which has lasted two month!)
Sanctions change continuously and are enhanced inbetween two shipment dates (about each three month).
Beside a complete interruption or termination of the collaboration with JINR, sanctions may be strengthened so much that they inhibit any further import- or export process.
Examples
Sanctions often address the transport box rather than the units (e.g. Aluminum walls had to be removed).
Even simple wording inconsistencies confuse the authorities. E.g. the different naming of units in two documents has launched an internal investigation by customes (document 1: magnet, document 2: units).
Translation in Russian and Polish language of all documents for the border control and logistics company is required.
The T1 document issued at entering the European Union limits the time for the costums and clearance process in Würzburg.

## Slide 33
import / export
SIS100 string: ion optical cell of SIS100
collective behavior of cryo-modules: mechanical, electrical, hydraulical, vacuum, etc.
installation procedures of module interconnections
Supply of new items
Several new parts and items have to be supplied to JINR for the upcoming unit types.
Each supply requires new documents and specific approval of the item by BAFA.
Process for supplying new parts:
a) two addenda to the main contract have to be prepared and signed by both parties
b) end-user-certificate has to be prepared and signed by both parties
c) BAFA application has to be issued by FAIR
d) BAFA approval has to be awaited and received
e) Suitable shipment/logistics process (truck, ship) and transport container has to be developed
In case of an uncontrolled interruption of the collaboration it is not expected that the supplies will be sent back.