## Slide 1: Lessons learned from practical and daily installation process
4th SIS100 Workshop Procurement and Installation
Jan Kollarczyk, for Machine Installation Team
24.09.2025

## Slide 2: Basic Points
Process of installation at FAIR [12 min]
  On-site Machine Installation
  Interaction with works on Technical Building Equipment (TBE)
  Lean Construction Managent (LCM) for SIS100
  Work registration, preparation and documentation
Discussion [3 min]

## Slide 3: On-site Machine Installation
1) -
2) ELC, RRF
1) TRI
2) ELC, FSB
1) ELC
2) FSB
1) ELC
2) FSB
1) -
2) -
1) -
2) IFJ, TRI, SCM
1) ELC, FSB
2) SCM, MEW
1) TRI
2) TRI, VAC
Status of
Works in Machine Tunnel
1) -
2) -
1) MEW
2) MEW, IFJ
1) ELC
2) ELC, FSB
1) MEW
2) IFJ
1) ongoing
2) soon within next 8 weeks

## Slide 4: On-site Machine Installation
TRI
  Backbone team of machine installation
  Machine transport and positioning
  Preparation for other work packages
  Changing conditions and capacities
  LCM plan adjusted for 1 team
Later

## Slide 5: On-site Machine Installation
TRI
  examples of issues during assembly
    Deliveries of material for assembly
    Resonance Sextupole Assembly
    Laser cooling beamline on the ceiling
    Missing tool for bellow interconnections
Later

## Slide 6: On-site Machine Installation
TRI
  Transport issues
    Space in Machine & Supply tunnel
    Magnet Modules under fire protection walls
Later

## Slide 7: On-site Machine Installation
IFJ PAN
  Welcome back
  Scope of works defined
  Restart in October 2025
Later

## Slide 8: On-site Machine Installation
IFJ PAN
  Coming activities:
    String test
    Dipole-Dipole Magnet Interconnections, arc 6
    Leak test of process pipes, arc 1
      input from VAC: work instructions
Later

## Slide 9: On-site Machine Installation
VAC – vacuum acceptance tests, straigt 3
MEW – welding of interconnections, arc 2
SCM – electrical tests, arc 6
RRF – RF cavities, sector 4
BEA – racks in niches
NCM – Survey and Alignment
EPS – power systems planning

## Slide 10: On-site Machine Installation
Dealing with contractors of GSI
  Registration at FAIR
  List of necessary documents
  Installation concepts
  Time schedules
GE Vernova
  Installation of SIS100 Power Converters

## Slide 11: Interaction with TBE works
Basic features:
  Work registration
    safety measures and work coordination considerations
  Regular communication
  Reflection in LCM plan for Machine installation
FSB
  List of rest works for the whole building K0923A
  List for single areas not existing
  LCM FAIR: TBE activities

## Slide 12: Interaction with TBE works
Example of TBE Works:
  Dismantling of temporary pipeline with fire-fighting medium
  Grouting of water entry points (Leakage on ceiling)
  Cable trays to the machines on the floor
  Fireproof insulation of cable pipelines
  Masonry works and door in arc 5
  Room temperature sensors
  Paintwork on the floor
  Fire protection walls
  Cable installations

## Slide 13: LCM for SIS100
Machine installation & TBE works comprised
Planing on daily level
Every activity captured in LCM plan
Coordination with all current installation participants
Coordinated parallel works possible and necessary
Team capacity considerations
Prioritising, Flexibility

## Slide 14: Work registration, preparation and documentation
Installation Readinness
Work Registration at SMG
DGUV sheet:
  according to German Social Accident Insurance
  occupational health and safety
  installation management
  on-site supervision
  work coordination authority
Work & Test instructions, Work Binders
EDMS Structure
Following Quality Control Plan during instalaltion

## Slide 15: Work registration, preparation and documentation
Installation Readinness
Work Registration at SMG
DGUV sheet:
  according to German Social Accident Insurance
  occupational health and safety
  installation management
  on-site supervision
  work coordination authority
Work & Test instructions, Work Binders
EDMS Structure
Following Quality Control Plan during instalaltion

## Slide 16: Conclusion
Following installation towards Mechanical Completion
  Transformation of installation strategy into serial assembly
  Keeping harmony between Machine installation & TBE
  Centralised coordination of Machine installation
  Communication of each intention on first place
  Ideas for improvements welcome
  Reflection of weak points

## Slide 17: Discussion
Thank you for your attention