## Slide 1: Project Interfaces Machine Installation
SIS100 Klausur 22.-24.09.2025
Janet Schmidt

## Slide 2: FAIR Project
EDMS:1762113

## Slide 3: Machine Installation – Project Milestones
Order |  | Name | Description
0 | 1 | M10 | SAT A accepted / component ready for installation or pre-assembly
0 | 2 | M10-1 | 1st component ready for installation or pre-assembly
0 | 3 | M92 | End of Shipment
9 | 4 | S06P | Pre-assembly and testing of components / modules
1 | 5 | A10-P | Pre-assembly and testing of components / modules
2 | 6 | M10-P | Pre-assembly and testing of components / modules is finished
13 | 7 | MB10 | Building ready for installation
14 | 8 | ACC10 | timeframe for machine installation
15 | 9 | MCC150-MB10-LV | Building ready for installation + Low Voltage distribution boards active
13 | 10 | SCC4 | Building commissioning / Inbetriebnahme Gebäude (Anteil Lp 8)
1 | 11 | MCC160-S | start with testing and commissioning Building
2 | 12 | ACC160 | testing and commissioning
3 | 13 | MCC160-MB11 | completion of testing and commissioning Building
7 | 14 | S007 | Installation in tunnel / cave
0 | 15 | ABL1 | Blue lining
1 | 16 | MBLF1 | Blue Line Finished
2 | 17 | A110 | Transport into tunnel / to experimental site
3 | 18 | M102-S | Start of ACC/EXP components installation
4 | 19 | A112 | Assembly of ACC/EXP components
5 | 20 | M102-1 | 1st ACC/EXP component assembly and alignment finished
6 | 21 | M102 | End of ACC/EXP components installation
7 | 22 | AAL1 | Alignment of ACC/EXP components
8 | 23 | MALF1 | Alignment of ACC/EXP components is finished
9 | 24 | MR103-S | Start of ACC local commissining (Phase 1.0) - Gate Review

## Slide 4: Machine Installation – Project Milestones
Order |  | Name | Description
0 | 1 | M10 | SAT A accepted / component ready for installation or pre-assembly
0 | 2 | M10-1 | 1st component ready for installation or pre-assembly
0 | 3 | M92 | End of Shipment
9 | 4 | S06P | Pre-assembly and testing of components / modules
1 | 5 | A10-P | Pre-assembly and testing of components / modules
2 | 6 | M10-P | Pre-assembly and testing of components / modules is finished
13 | 7 | MB10 | Building ready for installation
14 | 8 | ACC10 | timeframe for machine installation
15 | 9 | MCC150-MB10-LV | Building ready for installation + Low Voltage distribution boards active
13 | 10 | SCC4 | Building commissioning / Inbetriebnahme Gebäude (Anteil Lp 8)
1 | 11 | MCC160-S | start with testing and commissioning Building
2 | 12 | ACC160 | testing and commissioning
3 | 13 | MCC160-MB11 | completion of testing and commissioning Building
7 | 14 | S007 | Installation in tunnel / cave
0 | 15 | ABL1 | Blue lining
1 | 16 | MBLF1 | Blue Line Finished
2 | 17 | A110 | Transport into tunnel / to experimental site
3 | 18 | M102-S | Start of ACC/EXP components installation
4 | 19 | A112 | Assembly of ACC/EXP components
5 | 20 | M102-1 | 1st ACC/EXP component assembly and alignment finished
6 | 21 | M102 | End of ACC/EXP components installation
7 | 22 | AAL1 | Alignment of ACC/EXP components
8 | 23 | MALF1 | Alignment of ACC/EXP components is finished
9 | 24 | MR103-S | Start of ACC local commissining (Phase 1.0) - Gate Review

## Slide 5: M102-S Gate Review „Installation Readiness“
Input:
Readiness of the machine components (M10 / M10-P)
  hardware and documentation
Readiness of the work preparation
  instructions, work binders, planning, scope, material, safety
Readiness of the installation area
  FSB open tasks
  cabling status
  overall area condition
Output:
Discission to start machine installation in a new area
EDMS: 3327242

## Slide 6: M102-S Gate Review „Installation Readiness“
Input:
Readiness of the machine components (M10 / M10-P)
  hardware and documentation
Readiness of the work preparation
  instructions, work binders, planning, scope, material, safety
Readiness of the installation area
  FSB open tasks
  cabling status
  overall area condition
Output:
Discission to start machine installation in a new area
SMG-APLs machine, assembly responsibles
SMG work preparation, excecuting teams
FSB (U. Munsberg, J. Uhrich), electrical installation team
SMG SSPL machine installation and SMG-APLs machine
(based on input from the review team)

## Slide 7: Machine Installation
Process
EDMS:2206040,
2217753 and more
People
GSI - Maschinenmontage
EDMS:2401271,
2381180 and 3313828

## Slide 8: Machine Installation Compleation
M102 acceptance protocol
  template from QUA (EDMS: 1458121)
  based on technical locations
M102 status:
  all components positioned
  vacuum closed and tested
  media connected
    cooling water
    cooling air
    cabling
    pressured air, N2, experimental gases
    cryo
  all connections tested
    no electrical power and no cryo distribution during installation
  beamline aligned
handover to commissioning

## Slide 9: Transition from Installation to Commissioning
Gate Review - review of readiness for commissioning – document status (incl. M102 acceptance protocol), organisation, role designation status
On Site Safety inspection and preparation of a remaining issues list
Handover of safety responsibility from SMG to FCM&GAT upon signature
  Enforcement of access rules for commissioning phase, Key handover
  Commissioning safety organization (SiFas, STVs, AZs) becomes effective
slide by S. Reimann!