Wet Run 02.2026
Operator School
Introduction

---
Outline
- Goals and Schedule for the School
- Goals and Schedule for the Wet Run
- Operating Restrictions for the Wet Run

---
Goals and Schedule for the School
- Disseminate information about changes and current status of the control system for the upcoming wet run
- Introduce new applications and operating procedures to operators and related staff in preparation of the beamtime
- Prepare operators for tutorials, hands-on-training and practice operation during the wet run
- Disseminate goals and planning information about the wet run
- Schedule see indico page: https://indico.gsi.de/event/23845/

---
Goals for the Wet Run
- Verify operational readiness
  - Changes due to development since Wet Run 2025
  - New and upgraded MCR features
- Re-establish Storage Ring Mode
- Re-establish coupling with ESR and CRYRING
- New control system: introduction and training
- Verify Operating Scenarios for Beamtime 2026/27.1
  - Dual beam
    (carbon and helium)
  - Plasma physics (Single request workaround)
  - Multi-multiturn injection (not yet ready for regular operation)
  - Slow extraction (extraction times for schedule length restrictions)

---
Schedule for the Wet Run
- Planning and documentation of Wet Run:
  https://www.acc.gsi.de/wiki/FAIR/Intern/WetRun_26_1
- 7 weeks

---
Schedule for the Wet Run: Week 1
- UNILAC commissioning
- operator school

---
Schedule for the Wet Run: Week 2
- UNILAC RF commissioning
- operator tutorials
- Cooler magnet tests

---
Schedule for the Wet Run: Week 3
- UNILAC RF commissioning, SIS commissioning
- Dry Run UNILAC+SIS
- operator hands-on-training
- Ion source tests

---
Schedule for the Wet Run: Week 4
- UNILAC beam commissioning, SIS commissioning
- Wet Run UNILAC
- SOS test

---
Schedule for the Wet Run: Week 5
- UNILAC engineering run, SIS and ESR commissioning
- Optimizer/AI studies
- Operators: UNILAC operation training

---
Schedule for the Wet Run: Week 6
- UNILAC engineering run, SIS beam commissioning
- ESR commissioning
- Wet Run UNILAC+SIS

---
Schedule for the Wet Run: Week 7
- UNILAC+SIS engineering run, ESR Dry Run
- Wet Run UNILAC+SIS, Dry Run UNILAC+SIS+ESR
- Operators: UNILAC+SIS operation training

---
Operating Restrictions for the Wet Run
Restrictions resulting from radiation protection and/or renovation of experimental hall
- No acceleration in SIS18
- No extraction from SIS18
- Max. 1E7 particles per second in SIS18
- HEST not available
- beam intensity at UNILAC limited to low duty cycle and reasonable low beam currents (for orientation: overall intensity like M-Branch experiments)
- available beam targets at UNILAC:
  - TK
  - M3
  - X/Y/Z: only up to GUT1DC2

---
Operating Restrictions for the Wet Run
Restrictions resulting from in-development state of the control system
- max. 2 SIS Chains in a Pattern with UNILAC at the same time
- SIS Chains must be removed from UNILAC/SIS Pattern before length changes of SIS chain can be made
  - Workaround may be available („rubber time paramter“)
- length of Master Schedule restricted to 20s (1000 slots), has to be checked manually
- setting of TK stripper using ParamModi and Device Control, not Stripper App

---
Operating Restrictions for the Wet Run
Other restrictions
- do not use stabilizers and conditioners for HLI
- only UNILAC VirtAcc/SID 1-13 usable (as long as DevAcc devices are present)
- not all limits and checks are implemented:
  think before setting values, set only reasonable values

---
Final remarks
The control system is and will be in constant development right up to the start of the beamtime.
Do not expect too much continuity, rather than change, especially during the wet run. Stay vigilant!
Things will have changed until the beamtime, therefore we plan for another, longer operator school end of June 2026.