## Slide 1: Status Magnet Production and Further Collaboration Steps
Haik Simon
GSI, April 17th, 2026

## Slide 2: Collaboration Topics
Collaboration status
Sc multiplets
  production and testing status
Sc dipoles
  production and testing status
Sc magnets and local cryogenics
  delivery after testing w.r.t. installation schedule
Summary and Outlook

## Slide 3: History of the project
Addendum No.4:
Procurement of pre-cooler, QPS, Survey tools
Addendum No.5:
Floor, control room
2013
2014
2015
2016
2020
2021
2022
2023
2024
Amendment No.1 to Addendum No.12: update “Liability”
Amendment No.2 to Addendum No.12:
extension to end of 2026
2025
Amendment No.3 to Addendum No.12: extension to end of 2029, redefine scope of magnets to be tested, update resource assignment, options for work outside of regular working hours, parallel powering
Workshop at CERN
“CERN maintains the facility operational,
GSI executes the testing.”
with some exceptions:
welding, crane operation, cryo operation, fiducialization, …
CERN-GSI Agreement K1727/DG:
General agreement on collaboration in accelerator science and technologies
2010
Addendum No.12 KR3912:
Testing operation phase
2017
2018
Addendum No.2:
Cryogenic testing of S-FRS Magnets at CERN
2011
2012
2019
GSI testing team deployed, first magnet received, commissioning of the facility started
“Kick-off meeting” at CERN
On 14/04/2010, GSI and CERN signed the Agreement K1727/DG establishing an operational framework for collaboration in accelerator sciences and technologies, and other scientific domains of mutual interest
K. Sugita

## Slide 4: Collaboration Structure
K. Sugita

## Slide 5: Sc multiplets (for ES: 7 short and 13 long)
Procurement sc multiplets: a short history
20(/32) sc multiplets for ES. GSI in-kind.
GSI contract signed: July 2015 (ASG, IT)
FAT FoS short multiplet: January 2019
FAT FoS long multiplet: September 2020
Manufacturing status for ES in July 2023 (first round): 92%
 Technical issue (leakage at cold)
  Task Force GSI-CERN-ASG
  technical solution for thermal shield implemented
  no leakage since first repaired LM (Apr-24)
  repair (all multiplets)
Since April 2024: regular monitoring of external qualified supervisor at ASG premises
multiplets at FAIR campus
12/11/2024 CERN
sc multiplets at FAIR March 2026
Current status: all sc multiplets for ES produced and Factory Acceptance Test successfully done
see next slides

## Slide 6: Sc multiplets for Early Science (ES)
shielded target area
LM11
LM09
LM10
SM06
SM02
SM03
SM01
SM04
SM05
SM08
LM16
LM18
LM20
LM21
LM22
LM23
LM25
LM13
LM15
LM29
at ASG, FAT done
CERN test done
at CERN, next on the bench
CERN test ongoing
Section installed and pressure & vacuum tested 19.12.25

## Slide 7: FAIR 2028 and beyond Low Energy Branch (LEB), Energy Buncher, and Ring Branch (MSV)
Ring Branch
High Energy (Early Science)
Low Energy Branch with Energy Buncher
According to current planning the Low Energy Branch is the next NUSTAR facility to come (FS+++)

## Slide 8: SC multiplet production (ASG Italy, all ES magnets done)

## Slide 9
9
4
6
Source: ASG 06-09-23
Technical issues already resolved
GSI-CERN-ASG task force
3
1
2
5
Wherever possible brazed copper pipes have been replaced.
2) Remaining pipe brazing is strictly quality controlled.
Notes: Space expert Jonathan McDowell says on ISS 2023 leaks, if you have three such leaks, you have a problem: "One doesn't matter, two are a coincidence, three are systematic."

## Slide 10
Quality Criteria and X-Ray proc.
GSI-CERN-ASG task force
Specific brazing quality agreed upon in late 2023 between GSI and ASG, following the recommendation of the task force. The Must-Criteria shown below reflect the DIN/EN 18279 from Level C to Level D:
incomplete
penetration
outer edge (ring)
inner edge (ring)
Notes: THESE are massive reductions against level B
With the tolerance of -10%, the 2nd must Criterion 2 reduces to level D for LM9-10-11-SM06 and below in all other modules.
Must Criterion 3 isn‘t defined in the standard for good reason. It is a massive Q-reduction.

## Slide 11
Technical Issue, solution found via
GSI-CERN-ASG task force
A leak rate of feedthroughs increases after exposure to high pressures.
Quality issue at supplier
  At ASG, around 20 % failure rate during incoming inspection (leak test at 22 bars for 96 hours).
  At SAT, leaks found at incoming and specially after thermal cycle
    Acceptance criteria at FAT : a global leak rate < 5 x 10-5 mbar l/s
    To proceed cool down at CERN : a local leak rate < 1 x 10-4 mbar l/s
Lemo Feed-throughs under pressure:
Voltage taps, CERNOX sensors, level sensors
Lemo Feed-throughs
under vacuum

## Slide 12: Ongoing Repairs at FAIR
Decision for LEMO Repair, February 2026

## Slide 13
Sc standard dipoles for ES: 3 D2 (11°), 10 D3 (9.75°)
21 superconducting standard dipoles (13 for early science)
FAIR contract: January 2018 (Elytt Energy, ES)
Procurement status for ES (d.d: Nov. 2023) advanced; coil casing by Vacree (China) and WME (Italy)
Planned installation: Nov 2025 – Oct 2026
FoS D3 (9.75°)
FAT: ▪ Dec-2020
@CERN: ▪ Feb-2021
on test bench ▪ May-2021
- dust cleaned
- big leak detected at cold on thermal shield
SAT aborted ▪ Nov-2021
FoS D2 (11°)
FAT: ▪ Oct-2021
@CERN: ▪ Jan-2022
on bench: ▪ Feb-2022
- dust cleaned
- leak detected at cold on thermal shield
- chamfer movement detected after 1st thermal cycle
- leak detected in cryostat after 2nd thermal cycle
end SAT (magn. field OK; leakage NOK) ▪ Jan-2023
2022: leaks detected in several magnets in production at Elytt
May 2022: all production going beyond thermal shield assembly was stopped by manufacturer
June-December 2022: extensive R&D to resolve leak issue
Beginning 2023: work on cryostats resumed using new brazing machine
2023: further non-conformities detected
mid-2023: task force GSI-CERN-Elytt activated
Sep-2023: resignation of key engineer at Elytt
end 2023: mitigation NC established:
  dust: cleaning of pipes; endoscopic inspection by FAT
07/2024 chamfer: development of new (2nd) fixation for series dipoles
11/2024 Implementation of X-ray brazing checks
Dipole
Multiplet
Multiplet
Dipole
Multiplet
CERN Bât.180 12/2025
Procurement sc dipoles: a short history

## Slide 14
New brazing method:
Using filler material rings
Inductive brazing
Additional intermediate test:
Local leak test of pressurized pipe with chamber on each brazing
X-ray inspection of each joint
Chamber for T-joint testing
CERN-X-ray on Elytt sample
Sc dipoles technical issue - solved
Thermal shield brazing joints
GSI-CERN-Elytt task force
Old Design:
6 m Cu pipes → about 20 brazing joints
New Design:
7 m Cu pipes → only 8 joints
2 F- and 2 T-joints in coil casing area
4 straight joints in chimney area
OLD
NEW

## Slide 15
Sc dipoles technical issue - solved
Chamfer movements
GSI-CERN-Elytt task force
caused by bending of screws and delamination in yoke due to high magnetic forces (40 kN) acting on chamfers
Solution:
External fixation with retainer screwed on end plate
Status (31.10.24):
Retainers for 2 magnets ready
Status (07.11.24)
Integration at Elytt

## Slide 16: Sc dipoles for Early Science Current status
at Elytt, FAT done
CERN test done
at CERN, next on the bench
CERN test ongoing
shielded target area
11°
9.75°
9.75°
9.75°
D01
D02
D03
D04
D05
D06
D07
D08
D09
D13
D14
D15
D10
D11
D12
in construction
14/04/2026
Production dashboard

## Slide 17
Lemo Feed-throughs under pressure:
All mounted on current lead flange already by Marc & Wedell
T90 temperature sensors
Voltage Taps
He-Level sensors
Leak test on magnets at CERN
D01 (FoS D2): Leaks detected (1e-4 mbarl/s) at 12 bar on three connectors D06 (3rd D3): no leaks detected at 1.3 bar
Tests and Repair strategy with input from GSI-CERN task force
Remaining technical issue
Lemo Feed-Throughs
GSI-CERN-Elytt task force

## Slide 18
shielded target area
LM11
LM09
LM10
SM06
SM02
SM03
SM01
SM04
SM05
SM08
LM16
LM18
LM20
LM21
LM22
LM23
LM25
LM13
LM15
LM29
magnet produced
CERN test done
magnet already at CERN
CERN test ongoing
Sc magnets delivery to CERN overall schedule
D01
D02
D03
D04
D05
D06
D07
D08
D09
D13
D14
D15
D10
D11
D12
magnet in production
Data date: April 2026
04.26
05.26
06.26
07.26
10.26
11.26
01.27
01.27
07.26
10.26
05.26
02.27
03.27
04.27
Delivery to CERN

## Slide 19: Comparative view: up: sc magnets delivery to FAIR down: local cryogenic branches, installation completed
shielded target area
T
P1
P2
M1
M2
M3
H
G
LM11
LM09
LM10
SM06
SM02
SM03
SM01
SM04
SM05
SM08
LM16
LM18
LM20
LM21
LM22
LM15
D01
LM23
LM13
LM25
P: Inox, Kriosystem
DD: Mar-26
M: Cryo Diffusion
DD: Mar-26
H: Cryoworld
DD: Mar-26
T: Inox, Kriosystem
07.26
11.26
12.26
10.26
02.27
01.27
02.27
D02
D03
G: Cryoworld
DD: Mar-26
magnet already at FAIR
magnet’s delivery to FAIR (data date: 10/04/2026)
D04
D05
D06
D07
D09
D08
D10
D11
D12
D13
D14
D15
Local cryogenics benches: installation completed
08.26
05.26
09.26
05.26
05.26
06.26
10.26
11.26
12.26
01.27
03.27
05.27
05.27
05.27
06.27
09.26
05.26
05.26
03.27
04.27
LM29
11.26
done

## Slide 20: Test at CERN: speed-up possibilities
Time driver identification
  Some possible time savers associated to risk estimates have been identified.
  Recently new identified time savers:
    eDAQ gives us the quench file on the spot. Shorter commissioning (0.5h/quench, 1 day).
    Automatic evaporation allows to run over night and reach 10 K much sooner (1-2 days gain).
    Over-heating (T > Tdew point) allows to break vacuum right after the leak test (more stat needed, but 1-2 days gain).
H. Bajas Workshop 15/04/2026
Additional:
under development: additional devices for dipole magnetic measurements (test up to 3 dipoles in parallel)
Continuous adaptation and optimization of testing plan (improved criteria in work)
Preparation of Magnet Avatar measurements (remaining dipoles)

## Slide 21: Successful Implementation of Quality Measures (ASG)
Melanie Cho, 17/02/2026
3rd visit 17 March 2026, ASG
Follow up at first (FAT acc. LM13)

## Slide 22: Summary
Very successful collaboration !
Major technical and quality improvements thanks to CERN-GSI-FAIR-industry task forces
Expediting team solved several major production issues but still hindering problems are in process to be solved
Expediting and technical advisors in place to stabilize Elytt delivery schedule
Sc dipole production currently in critical path for testing schedule and Early Science scope
Upgrade of CERN testing facility (talk by Germana Riddone) and ramp-up of testing team (GSI and TSU) result in a resilient testing response
Next steps:
Early Science scope / First Science+++ scenario: Branched Dipoles / Low Energy Branch
Prepare Operation – measure Avatar relevant data for magnets (remaining dipoles) 
avatar/digital twin of spectrometer (talk by H. Müller) Thanks to the Team !