## Slide 1: HEBT and beam dumps overview
F. Hagenbuck
11th FAIR – Machine Advisory Committee Meeting

## Slide 2: Outline
Introduction
Magnets and Vacuum Chambers
Power Converters
Beam Diagnostics
Special Installations
Technical System Design
Connection SIS18 – CR
Status HEBT Buildings

## Slide 3: HEBT – Module 0-6
42 sections (22 connections/beam lines)
total length (HEBT) ca. 2.5 km
two superconducting beam lines (SIS300 – CBM, SIS300 – Dump), all other beam lines normal conducting
nominal magnetic rigidity: 300Tm, 100Tm, 18Tm, 13Tm
parallel operation

## Slide 4: HEBT – MSV (Module 0-3)
27 sections (11 connections/beam lines)
total length (HEBT) ca. 1.5 km
all beam lines normalconducting
nominal magnetic rigidity 100Tm, 18Tm, 13Tm
parallel operation
full version has to be taken into account for building planning of the MSV

## Slide 5: Outline
Introduction
Magnets and Vacuum Chambers
Power Converters
Beam Diagnostics
Special Installations
Technical System Design
Connection SIS18 – CR
Status HEBT Buildings

## Slide 6
75 dipole magnets (19 types) in M0-3
189 quadrupole magnets (7types) in M0-3
92 steering magnets (3types) in M0-3
Almost all HEBT Magnets (338/356)  Efremov institute (Council V, VI, VII)
Magnets similar to CR Magnets (2+5)  Budker institute (IKRB VIII)
Super-FRS Quadrupoles (9)  GSI in-kind (Council IV)
all HEBT magnets assigned
verbal confirmation that BINP will take over all related vacuum chambers (not yet all PSP-codes assigned to BINP, some PSP-codes unclear)
Magnet Types

## Slide 7
Batch1
Content: 51 dipoles and related vacuum chambers
Contracts signed with BINP (Jan. 2013) and Efremov (Aug. 2013)
Exchange on working-level with BINP started in Feb. 2013, with Efremov in Oct. 2013
Common kick-off meeting at GSI on 10.-11.12.2013
Common techn. meeting at Efremov Inst. on 13.-14.5.2014
details on next slides
Batch2
Content: 17 dipoles, 102 quadrupoles, 80 steering magnets and related vacuum chambers
Detailed Specs in 2nd EDMS approval process (release expected 30.05.); draft version given to Efremov and BINP in Dec. 2013, EDMS approval version on 12 May
Draft version of contract will be sent to Efremov at beginning of June, to BINP at mid of June
Batch3
content: 5 dipoles, 71 quadrupoles, 12 steering magnets and related vacuum chambers
Parameter tables ready and given to Efremov and BINP in Dec. 2013; 3D models and 2D drawings ready
Detailed Specs ready in early summer; draft version will be given to Efremov and BINP until mid of June
Batch1 – 3

## Slide 8
Batch1 contains two pre-series magnets and vacuum chambers
at present – approval of 3D models and general drawings of pre-series magnets and vacuum chambers delivered by Efremov and Budker institute, resp.
Status Batch1
dip1s_0
dip13_0
3D model by Efremov institute
3D model by Efremov/Budker institute

## Slide 9: Purchase of Basic Materials
Purchase of basic materials is carried out only for the two pre-series magnets dip1s_0 and dip13_0.
Purchase of following positions are performed:
For yoke:
Electrical steel Power Core 1200-100A with cover Stabolit 70.
«ThyssenKrupp Steel Europe», Germany
Forecast material delivery date – September 2014
courtesy Efremov Inst.

## Slide 10: Purchase of Basic Materials
For coils:
Copper wire with dimensions12х12Ø6 mm (main winding) for dip1s_0.
- Copper wires with dimensions 26х26Ø13,5 mm (internal winding) and
32х13,5Ø6 mm (external winding) for dip13_0.
All «Luvata», Finland
Copper wire Multogan 2х5 mm (for correction winding)
«SCHEIING KG», Germany
courtesy Efremov Inst.

## Slide 11
Fixture for winding of coils dip1s_0.
Production of Tooling
courtesy Efremov Inst.

## Slide 12
For dipole magnet dip1s_0:
Tooling for winding and impregnation of coils were developed, designed and produced.
Tooling for compression and impregnation of coils
Production of Tooling
courtesy Efremov Inst.

## Slide 13
Manufacturing of die for punching of lamination dip1s_0.
Stripper and shedder for die of dip1s_0.
Other details of die are in the process of manufacturing.
Production of Tooling
courtesy Efremov Inst.

## Slide 14
Details of fixture for assembly and baking of packets for yoke of magnet dip1s_0.
dip13_0:
Tooling was developed and designed.
Fixture for winding, baking and compression of coils are in the process of manufacturing. Die for punching is in production.
Production of Tooling
courtesy Efremov Inst.

## Slide 15: Schedule Magnets
Batch1: At the moment Efremov Institute is ruled by the production schedule presented at the Kick-off meeting in Darmstadt on 10th of December 2013, based on Annex 2, Table A1 of the contract.
Batch2&3: “At the present time the Efremov Institute goes behind drawings and parameter tables ...... and performs production schedule and commercial offer for HEBT magnets Batch2-3 for performance and agreement with FAIR and GSI.”
pre-series vacuum chambers Q1/2015

## Slide 16: Prioritization at FAIR@GSI
SIS18
CBM
HESR
P-LINAC
CR
SFRS
PBAR
Dump
AP, PP
SIS100
HEBT A
SIS18  SIS100
SIS18  S18-Dump
SIS18  SFRS Target
SIS100  Dump
SIS100  CBM
HEBT B
SIS100  AP, PP
SIS100  SFRS Target
SIS18  AP, PP
HEBT C
SIS100  pbar Target *
SFRS  CR
CR  HESR
Primary Beams Q2/2018 (M11) (beams from SIS18, SIS100)
Secondary Beams Q1/2019 (M11) (beams from SFRS, pbar)
FAIR@GSI

## Slide 17
Prioritization at FAIR@GSI
In agreement between FAIR@GSI and FAIR
Efremov Institute and Budker Institute were asked (in meeting 12/2013 and 05/2014) to work out a production plan for Batch1-3 sorted according to HEBT A/B/C .

## Slide 18: Outline
Introduction
Magnets and Vacuum Chambers
Power Converters
Beam Diagnostics
Special Installations
Technical System Design
Connection SIS18 – CR
Status HEBT Buildings

## Slide 19
21 Dipole PC types
(quantity 51)
Det. Specs released for 7 Quadrupole PC types (quantity 151)
Power Converter
3 Steerer PC types
(quantity 92)
11 Quadrupole PC types (quantity 170)

## Slide 20
First Contract closed (May 5, 2014) on 3 (+1) HEBT Quadrupole PC types (quantity 77+1) with Bose Institute(shareholder)/ECIL (provider)
Power Converter

## Slide 21
2.3.3.2.10.1 – HB.Q10 (1 pre-series )
(for quad11 in T1X1, T1X2, TXL2, TAP1 – „ fast“)
2.3.3.2.1.1 – HB.Q1 (23)
(for quad2 in THE1, TSF1 – „slow“)
2.3.3.2.2.1 – HB.Q2 (50 incl. 1 pre-series) (for quad2 in T1S1-T1S4, TSX1 – „fast“)
2.3.3.2.15.1 – HB.Q15 (4)
(for quad2 in T1S3 – series connection, „fast“)
covers all quad2 of batch2 and batch3 (#81)
(= all* quadrupoles in 18Tm/13Tm sections)
* except CR similar quadrupoles
Power Converter
Scope of contract
09/2015 – FAT pre-series HB.Q2, HB.Q10

## Slide 22
SIS18
CBM
HESR
P-LINAC
CR
SFRS
PBAR
Dump
AP, PP
SIS100
HEBT A
SIS18  SIS100
SIS18  S18-Dump
SIS18  SFRS Target
SIS100  Dump
SIS100  CBM
HEBT B
SIS100  AP, PP
SIS100  SFRS Target
SIS18  AP, PP
HEBT C
SIS100  pbar Target *
SFRS  CR
CR  HESR
Primary Beams (beams from SIS18, SIS100)
Secondary Beams (beams from SFRS, pbar)
FAIR@GSI
Power Converter

## Slide 23
SIS18
CBM
HESR
P-LINAC
CR
SFRS
PBAR
Dump
AP, PP
SIS100
HEBT A
SIS18  SIS100
SIS18  S18-Dump
SIS18  SFRS Target
HEBT B
SIS100  AP, PP
SIS100  SFRS Target
SIS18  AP, PP
HEBT C
CR  HESR
Primary Beams (beams from SIS18, SIS100)
Secondary Beams (beams from SFRS, pbar)
Quadrupole Power Converter
SIS100  Dump
SIS100  CBM
SIS100  pbar Target *
SFRS  CR
Power Converter
Delivery series
02/2018
12/2018

## Slide 24: Outline
Introduction
Magnets and Vacuum Chambers
Power Converters
Beam Diagnostics
Special Installations
Technical System Design
Connection SIS18 – CR
Status HEBT Buildings

## Slide 25
Beam Diagnostics
Overview devices
total 207
(without BLM)
Common Specification:
F-CS-BD-01e: Common Specifications for FAIR Beam Diagnostics: RELEASED
Detailed Specifications:
F-DS-BD-04e_AC+FCT_T : Fast Current Transformer: RELEASED
F-DS-BD-08e_AC+CCC_T+CR: Cryogenic Current Comparator: IN WORK (not day 0 diagnostics)
F-DS-BD-09e_AC+RT_T+PT+F: Resonant Transformer: UNDER APPROVAL
F-DS-BD-12e_Elecprofile+MWPC_T :Multi Wire Proportional Chamber: IN WORK
F-DS-BD-13e_Elecprofile+SEM_PL+T+PT: Secondary Electron Emission Grid: UNDER APPROVAL
F-DS-BD-16e_Optprofile+SCR_T+PT+F Scintillating Screens: UNDER APPROVAL
F-DS-BD-19e_Optprofile_BIF_PL_T_F Beam Induced Fluorescence: IN WORK (not day 0 diagnostics)
F-DS-BD-23e_Pos+BPM_T+PT+F: Beam Position Monitor: RELEASED
F-DS-BD-26e_PD+BLM_T_1S_CR_PT Beam Loss Monitor: RELEASED
F-DS-BD-27e_PD+PDC_T: Particle Detection Combination: UNDER APPROVAL
F-DS-BD-40e_DAQ Data Acquisition System: RELEASED
F-DS-BD-43e_Mech+MechanicalDrives: Mechanical Drives: RELEASED
F-DS-BD-44e_Mech+VacuumChambers: Standard Vacuum Chambers for HEBT: RELEASED
F-DS-BD-46e_Subsys+HighVoltage High Voltage: RELEASED
F-DS-BD-47e_Subsys+PneumaticDrive Pneumatic Drives : RELEASED
F-DS-BD-48e_Subsys+DetectorGasflow: Detector Gas Flow: IN WORK
Most of the Specifications released or under approval

## Slide 26
Detailed, technical drawing and specification of all standard diagnostic chamber, diagnostic chamber with collimator and BPM chamber
All technical documents of standard diagnostic chambers (8 types, ~65 pieces) delivered to Indian shareholder (April 14, 2014)
3D models for special diagnostic chamber
Test production of first FAIR-type diagnostic chamber
Detailed, technical drawing of FAIR standard pneumatic drive
Test production of first FAIR-type pneumatic drive
Mechanics
Detailed, technical drawing of transformer chamber
Test production of first FAIR-type RT/FCT

## Slide 27
A new, fully FAIR-conformal system for standard scintillating screen based beam diagnostics including digital image acquisition, remote controllable optical system and mechanical design, was set up and commissioned with beam during last beam time in Feb./March 2014. CUPID (Control Unit for Profile and Image Data) is based on the Front-End Software Architecture (FESA) to control beam diagnostic devices.
Scintillating Screen (Complete System)

## Slide 28
DAQ
BD acquired extensive expertise with the software architecture of the new control system, FrontEnd Software (FESA) as well as expert GUIs
Future software architecture for DAQ and expert GUIs have been implemented for major beam diagnostic devices: beam position monitors, beam transformers, GigE cameras for scintillating screens, counting devices like scintillators, ionization chambers or SEM-Grids
Electronics
Pre-series production and beam test of new MWPC and SEM-Grid electronics
New concept for pneumatic drive and stepping motor control system
DAQ System
1 ∙ 108 Au18+,
300 MeV/u,
slow extr. 1.8s

## Slide 29: Outline
Introduction
Magnets and Vacuum Chambers
Power Converters
Beam Diagnostics
Special Installations
  Charge State Stripper
  Halo Collimation Systems
  Safety Beam plugs
  SIS100 Injection/Extraction Beam Dump
Technical System Design
Connection SIS18 – CR
Status HEBT Buildings

## Slide 30: Stripping Stage SIS18  SIS100
Stripping stage to increase the charge state between SIS18 and SIS100, i.e. U73+  U92+
  higher energies for CBM-Operation
  H-like ions for atomic physics experiments
subsequent: 3 pairs of collimators, to remove unwanted charge states

## Slide 31: Stripping Stage SIS18  SIS100
Chanel | Fraction
U92+ | 87.0%
U91+ | 12.5%
U90+ | 0.5%
Stripping efficiency
for U73+ at 967 MeV
in Nb-foil, 195 mg/cm²
Stripping
stage
3 collimator pairs

## Slide 32: Collimators behind the Stripping Stage
Incident particles of U73+ :
  1.25 ∙ 1010 per shot primary beam
  1.37 ∙ 109 Ions/s primary beam
   up to 9.4 ∙ 107 Ions/s lost on collimators
  Uranium @ 967 MeV: 3.5 W
Collimators will be installed in beam diagnostics chambers
Length of 10cm assumed
Next steps:
  Choice of material
  Mechanical design
  Design Stripper Station
Energydeposition
1 GeV Uranium in Cu
beam
CF250
for collimator

## Slide 33: Outline
Introduction
Magnets and Vacuum Chambers
Power Converters
Beam Diagnostics
Special Installations
  Charge State Stripper
  Halo Collimation Systems
  Safety Beam plugs
  SIS100 Injection/Extraction Beam Dump
Technical System Design
Connection SIS18 – CR
Status HEBT Buildings

## Slide 34: Halo Collimation SIS100  CBM – Experiment
CBM-Experiment needs a well collimated beam to
  protect the detectors (silicon tracker close to the beam)
  have a minimal background
At 5 mm distance to beam axis  intensity < 10-5
Showers of secondaries out of the collimators have to be considered
   collimator can produce background for experiment
  Dipole between last collimator and experiment to supress this background

## Slide 35: Halo Collimation SIS100  CBM – Experiment
Appropriate positions for collimation determined by ionoptical calculations
Next steps
  Check of available space
  Tracking calculations of secondaries
  Choice of material
  Mechanical design
to CBM

## Slide 36: Outline
Introduction
Magnets and Vacuum Chambers
Power Converters
Beam Diagnostics
Special Installations
  Charge State Stripper
  Halo Collimation Systems
  Safety Beam plugs
  SIS100 Injection/Extraction Beam Dump
Technical System Design
Connection SIS18 – CR
Status HEBT Buildings

## Slide 37: Safety Beam Plugs
Device to protect accessible areas from unwanted beam  block which intercepts the beam (accidential scenario!)
  Acess only possible, if dipole magnets in front of area in safe state
  Safety beam plugs provide redundancy to interlock magnets
18 beam plugs forseen
High energy beams can not be stopped completely, production of secondaries
Beam is „diffused“  safety beam plugs = „diffusor“
D20 currently under investigation

## Slide 38: Safety Beam Plugs
Proton beam, Ek = 29 GeV, 2.5 x1013 p (one shot)
Effective Dose on ground level (G017.1) for different lengths of the diffuser D20 (1m, 0.5m, 0.2m)
Investigation of accessibility of neighbouring areas
G004
G017.1

## Slide 39: Safety Beam Plugs
For an accidental scenario with D20, with the (shortest) length of 20 cm:
Effective Dose <1 µSv at the surface (Bld G17, NE25 and NE26)
Effective Dose <80,150 μSv in the underground areas NE50 and NE30, resp. Access to these areas possible.
Next steps
Investigation of the radiation level at different critical positions
Definition of the required length and material
Mechanical design of pneumatic drive and vacuum chamber
Design of drive control (safety aspects have to be considered)

## Slide 40: Outline
Introduction
Magnets and Vacuum Chambers
Power Converters
Beam Diagnostics
Special Installations
  Charge State Stripper
  Halo Collimation Systems
  Safety Beam plugs
  SIS100 Injection/Extraction Beam Dump
Technical System Design
Connection SIS18 – CR
Status HEBT Buildings

## Slide 41: SIS100 Injection Beam Dump
Located in H0705A (G004) U30
@-19.2m (relative to SIS18 beam height), slope -15°
For set value generation of beamline SIS18 – SIS100
For use with full intensity but reduced repetition rate
Dose rate for p@4.7GeV, 5∙1012/s: 50mSv/h, 500mSv/h (in beam direction)
to SIS100
from SIS18
5.65m
H0705A
2m
2m
2m
3m
Design – overlapping structure
  36 blocks of concrete, 4 types, mmax~3.5to, mtotal~90to
  30 blocks of iron, 4 types, mmax~4.6to, mtotal~95to
2m
2m
3m

## Slide 42
SIS100 Extraction Beam Dump
Located in K0619A (T112)
@-9.4m (relative to SIS18 beam height), slope -3.333°
For set value generation of SIS100 (and later SIS300)
For use with full intensity but reduced repetition rate
Dose rate for 238U @2.7GeV/u,1∙1011/s: 500µSv/h, 50µSv/h (in beam direction)
238U @1.5GeV/u,5∙1010/s (typ. SFRS)
4m
4m
2m
1m
to CBM
Dump
T112
Design – overlapping structure
  100 blocks of concrete, 5 types, mmax~2to, mtotal~105to(+35to)
  199 blocks of iron, 7 types, mmax~3to, mtotal~520to
  graphite core will be foreseen (SiSt)

## Slide 43: Outline
Introduction
Magnets and Vacuum Chambers
Power Converters
Beam Diagnostics
Special Installations
Technical System Design
Connection SIS18 – CR
Status HEBT Buildings

## Slide 44
SIS18
SIS100/300
CBM
DUMP
SIS100/300
SFRS
Technical System Design
3D model of the complete HEBT system
Most complex – Central Transfer Building G004

## Slide 45
SIS18
SIS100/300
SIS100/300
CBM
SFRS
pbar, APPA
Technical System Design
Central Transfer Building G004
Branching and crossing point for 8 beam lines (full version)
Several beam lines inclined
Components of many other beam lines are transported through this building

## Slide 46
Technical System Design
Two advanced design projects with the dept. of computer integrated design of TU Darmstadt
  Draft concept of assembly-, alignment- and disassembly processes in G004
  Draft concept for a transportation unit for assembly and disassembly on the injection and extraction ramp.
At the moment detailed specifications for the design of the support structure for G004 are under preparation – support structure not in costbook
to SFRS
to CBM/ DUMP
to SIS100
from SIS100/SIS300

## Slide 47: Outline
Introduction
Magnets and Vacuum Chambers
Power Converters
Beam Diagnostics
Special Installations
Technical System Design
Connection SIS18 – CR
Status HEBT Buildings

## Slide 48
current connection scheme
proposed connection scheme
Project lead:
Ions for HESR via CR
Investigate connection SIS18 – CR for MSV
Connection SIS18  CR

## Slide 49
from SIS18
to NESR (y=+1.2m)
to CR
current layout
y=0
y=0
y=+1.2m
y=0
y=+1.2m
Dx=2m
TSN1
TAP1
in Module 6, bypassing CR
pbar
from SIS18
to CR
TFC1
TSN1
TAP1
TSR1
TSN2
FREX
y=0
y=0
y=+1.7m
y=0
y=+1.7m
Dx=2m
to NESR (y=+1.2m)
proposed for MSV (M0-3)
new layout
pbar
Connection SIS18  CR

## Slide 50
TSN1
(new)
(old)
TSN1MH02
T113
T103
2m
TSR1
„no“ modification of building planning required
Connection SIS18  CR

## Slide 51
ion optical layout
check mechanical integration
„no“ (minor,CR138) modification at building T113
cost estimation (2005) 1.8 – 2.1 M€ (only HEBT)
include beam line into MSV?
Connection SIS18  CR

## Slide 52: Outline
Introduction
Magnets and Vacuum Chambers
Power Converters
Beam Diagnostics
Special Installations
Technical System Design
Connection SIS18 – CR
Status HEBT Buildings

## Slide 53
G017.1
G018
T108N
T108S
with HEBT Supply
T103
T110
with HEBT Beamline
G050
07
G0
06C
G0
HEBT Buildings
T101
T104
T106
T112
T113
G004
G004A
GAP HEBT
HEBT Buildings T101, T104, T106, T112, T113, G004, G004A
Execution planning
approval 2nd preliminary building shell summer 2013
2nd collision check DMU/building end 2013/beginning 2014
G004:
3rd preliminary building shell 12/2013
T106:
3rd preliminary building shell 01/2014
intermediate status TGA 03/2014
preliminary collision check DMU/building/TGA 03/2014
T101, G004A:
4th preliminary building shell 01/2014
intermediate status TGA 03/2014
preliminary collision check DMU/building/TGA 03/2014
5th preliminary building shell 05/2014
approval building shell plans until mid June
53

## Slide 54
Summary
Procurement of material and manufacturing of tooling pre-series magnets done/in work
Delivery of pre-series magnets and vacuum chambers expected for Q1/2015
Detailed Specs Batch2 close to release (30.05.); draft contract in preparation and will be sent to Efremov/BINP in June
Preparation Detailed Specs Batch3
Production plan for Batch1-3 sorted according to HEBTA/B/C needed
Contract on 78 Quadrupole Power Converters closed with Bose Institute/ECIL
Preparation Detailed Specs Dipole Power Converter
Progress in many fields of Beam Diagnostics (DAQ, electronics, Scintillating Screens, ....)
Detailed, technical drawings and specification (all released) of standard diagnostic chambers delivered to Indian shareholder
Completion of physical and design parameters of Special Installations
Proposal worked out to deliver Ions to HESR (via CR) – include into MSV?
Approval of building shell plans of T101, G004A until mid of June
Revision of MS-Project Plans in work
 | Primary Beams |  | Secondary Beams
status 26.05.2014 | HEBT A | HEBT B | HEBT C
M11 Magnets | 10/2018 | 12/2018 | 09/2019

## Slide 55
Thank you
for your attention
and thanks to all colleagues from GSI, FAIR and international partners for their work and support for this presentation.

## Slide 56
Backup

## Slide 57
Magnets Batch 1 – 3

## Slide 58
Parallel Operation requires pulsing of sections and switching between the sections with divider/combiner dipoles  ‚fast‘ magnets
Some sections don‘t have to be pulsed (e.g. target-section, 13Tm, 300Tm)  ‚slow‘ magnets
pbar + RIB fixed target (U28+) + AP (HE)
HESR
SIS18
SIS100
CR
p-Linac
Unilac
D. Ondreka
Some sections are shared in a pulse to pulse mode by different beams with different targets and different magnetic rigidities, e.g :
Operation Mode

## Slide 59: Halo collimation SIS100  CBM – Experiment
Collimation in both transversal planes required
  Phase space needs to be cutted in position and angle
  Two different collimator positions required
X
Y
CBM-Target
81.5 m of beam line
225.7 m

## Slide 60: Safety Beam Plugs
Maximum Effective Dose values :
<50 mSv after the first 4m length of Tunnel 104
<80 μSv along NE50 (G018)
1dim projection along z – Tunnel 104 + NE50 (G018)
1dim projection along the 80 m long Tunnel113 with NE30
Maximum Effective Dose values:
<0.7 mSv along the Tunnel 113;
<150 μSv along NE30 (Tunnel T113)

## Slide 61
Plot of a ~1 nA current signals which are produced by bunched beam of 109 particles of Ni26+ at an energy of 600 MeV extracted from SIS18. The beam is extracted with an extraction time of 500ms.
Beam test with new SQUID electronics
Construction work preparation for new cryostat
Cryo Current Comparator