## Slide 1: Super-FRS Status
M. Winkler
11th FAIR - Machine Advisory Committee Meeting

## Slide 2: Outline
Status SC Magnets & Testing
Status Local Cryogenics
Status (radiation hard) NC Magnets
Status Target Area Installation and Infrastructure
Status Super-FRS Instrumentation
Redesign of the Energy Buncher
Status Civil Construction
Summary
Notes: In-Flight  energies as high as 1500 MeV/u

## Slide 3: SC Dipole Magnets
Status:
Collaboration agreement with CEA/Saclay signed (11/2013):
  Detailed design
  Technical follow-up
  Participation at CERN testing
Technical Kick-off 1/2014
IMP Visit 4/2014 (CEA & GSI)
PDR planned for 6/2014 (includes external advisor)
FDR planned for 9/2014 (without special dipoles)
Tender by FAIR Q4/2014 (option on special dipoles)
First of Series ready for testing: Q2/2016
Series production and testing: Q3/16 – Q4/18
3 dipole units 11°
21 dipole units 9.75°
  3 times modified cryostat
Iron dominated
Warm iron
SC coil
Aperture ±190mm x ±70mm
Weight: 50 to 60 ton
Prototype built and tested (FAIR China Group)
Branching Point
cryostat & yoke
modification
small yoke
modification

## Slide 4: Collaboration with CEA/Saclay Overall Status
Procurement Strategy under discussion
  3 lots (yoke, cold mass, integration)
  branching units as option
  pre-ordering of wire ?
  ‘pre-bidder conference’ after PDR
Time Schedule updated
Focus on the short dipole version
Project includes
Magnetic design
Cryogenic Design
Quench Analysis
Mechanical Design (including
cool down, magnetic forces)
Protection & Quench Detection
Instrumentation
Interfaces with GSI/FAIR
(cryogenics, PC, DMU, ...)

## Slide 5: Collaboration with CEA/Saclay Status Magnetic Design
Magnetic design finalized
Good field region +/-190mm (horizontal), +/-70mm (vertical)
field homogineity: about 2x10-4
Updated design with faced end chamfers shapes being calculated
Prototype magnet end chamfer

## Slide 6: Collaboration with CEA/Saclay Status Mechanical Design
First CAD model provided by IMP
Modification of mechanical design under way
  By taking into account the lessons learned from the prototype (motion of the cryostat during the test)
  By ensuring the lack of physical interference between two successive magnets
Old
Design
New
Design

## Slide 7: Collaboration with CEA/Saclay Preliminary CAD Model

## Slide 8: SC Multiplets
7 m
iron dominated, cold iron (≈40 tons)
common helium bath
warm beam pipe (38 cm inner diameter)
per magnet 1 pair of current leads
max. current <300A for all magnets
Tender Status:
Tender opened Q3/2013
Bidder submitted quotes Q4/2013
1st round negotiation finished Q1/2014
2nd round negotiation finished Q2/2014
3rd round negotiation and signing of contract expected for June 2014
FAT of first short multiplet Q1 - Q2/2016
FAT of first long multiplet Q2 - Q3/2016
Series production: Q3/2016 – Q1/2020
25 long multiplets (MS)
8 short multiplets (PS)
Quadrupol triplet / QS configuration
up to 3 sextupoles and 1 steerer
Octupole coils in short quadrupoles

## Slide 9: Multiplet tendering: Comparison of Timelines
Overall time for production of 33 multiplets ≈5.5 to 6 years
Start in Q3/2014,
  1st multiplet at CERN: Q1–Q2 /2016
  WP runs at least until Q4/2019
Series Production Rate approximately 1 unit/month;
  PR of Bidder 3 too fast (<2 years, would require 4 test benches at CERN)
 | FAT short multiplet (month after project start) | FAT long multiplet (month after project start) | Release of SP (month after project start) | FAT 1st series (month after project start) | FAT last series (month after project start)
Project Plan | 19 | 23 | 27 | 31 | 62
Bidder 1 | 20 | 22 | 26 | 33 | 68,5
Bidder 2 | 22 | 25 | 27 | 36 | 73
Bidder 3 | 24 | 27 | 28 | 34 | 56

## Slide 10: Magnet Testing & Mapping @ CERN
GSI-CERN Agreement K1727/DG & Addendum #2 (signed)
Scope (separator magnets):
  24 Dipoles (PS & MS),
  31 Multipletts (+ 2 spare)
Place: CERN building 180
3 universal test benches, basically:
  1 setting-up & cool-down
  1 measuring
  1 warm-up & disassemble
Ready for testing: Q4/2015
Time estimate (single multiplet): 44 days
  Installation, connection, cool-down: 15 days
  Cold test (powering, magnetic field): 15 days
  Warm-up, disassembly: 14 days
overall series measurement time: ≈ 3-3.5 years
Notes: 10
10

## Slide 11: Magnet Testing Area @ CERN
Existing equipment
  magnet-measurement station, crane
  Cryo: Ghe Buffer, distribution box pre-cooler (10kW) + compressor
New required equipment (mainly cryo-parts):
  2nd pre-cooler (10kW) + compressor
  3 satellite valve-boxes & cryogenic lines
  LN2 & LHe tank
Notes: 11
11

## Slide 12: Super-FRS Local Cryogenics
Flow scheme / Cooldown processes
  FB controls: 3 dipoles / 2 multiplets
  Total cold mass (PS + MS): ≈1.100 ton
  Cryogenic operation modes
Revision of feedboxes
Updates of cryogenic interfaces
Emergency cases
  Normal quench → 70% of energy deposited in quench protection system
  Worst case scenario → full energy in He
  dimensioning of safety valves/burst disc

## Slide 13: Super-FRS Local Cryogenics Routing
100 m
FPF2
Focusing system
FHF1
LEB
R3B

## Slide 14: Warm gas lines for local cryogenics in the main tunnel of Super-FRS
Main 300 K high pressure Gas Supply line (HD)
DN 80
Main Current Leads Gas Return line (ND)
DN 80
After the Super-FRS target and throughout the Super-FRS tunnel:
Vacuum jacketed warm multipurpose line (ND - HD)
DN 200
Branching 300 K high pressure Gas Supply line (HD)
DN 80
Branching Current Leads Gas Return line (ND)
DN 80

## Slide 15: Radiation Resistant Magnets (at the Target Area of Super-FRS)
Normal conducting magnets using MIC cable
3 dipole units, 3 quadrupoles, 2 sextupoles
Prototype dipole built (95 ton) and tested by BINP
Handling tests at GSI under way
Remote alignment under revision
Remote connectors (current, water, and interlocks) under revision
Specification in preparation,
Tendering via FAIR
Prototype dipole
at GSI testing-hall
new water
connector

## Slide 16: Radiation Resistant Magnets (at the Target Area of Super-FRS)
Beam
Target
Chamber
BC1
BC2
BC3
 | Quad 1a | Quad 1b
Leff | 0,9 m | 1,2 m
(Br)max | 15,9 T/m | 12,2 T/m
RPol | 70 mm | 95 mm
IMax | 980 A | 1.400 A
New design of first two NC quadrupoles
  required field gradients were too high
  no technical/mechanical solution found due to too large bending radius of MIC
  individual designs for the each NC quad
Specification in preparation,
GSI resigned EoI on quads at last IKRB
Tendering via FAIR (together with dipoles)

## Slide 17: Target Area Installation Overview
Major Installation
Target chamber & plug inserts
  German in-kind
  collaboration contract with KVI-CART in preparation
Target wheel & plug inserts
  German in-kind
  collaboration contract with KVI-CART in preparation
Beam catcher
  Indian in-kind
  chamber and plug inserts for
  slow and fast extracted beams
Major Infrastructure
Hot Cell Complex
      German in-kind
      So far planning by nuclear engineering company
Shielding flask
  Finnish in-kind
  requires special authority approval.
Iron shielding (approximately 6.000 ton)

## Slide 18: Target Chamber (needs revised layout)
vacuum seals
connections
(hands on)
motor
devices in beam
target
plug
pillow seals
pillow
seals

## Slide 19: Target Wheel
increase beam spot size
usually (s): 1x2 mm2
to (s): 4x6 mm2
to have target survive Pmax tensile ~ 26 MPa
d = 450mm (prototyp)
biggest issue, bearings in vacuum
Revision ongoing
  larger wheel size
  omit transverse motion (moving mechanism)
  design for remote handling
WP will be done in collaboration with KVI-CART
Notes: 19

## Slide 20: Beam Catchers
Indian in-kind
Institute CMERI Durgapur designated to do the mechanical design work
Chamber design adjusted (additional pumping channels)
Draft specification available
Mechanical design and draft spec need to be updated to represent the status of actual planning
GSI@FAIR installed a direct GSI contact person
Beam power in one short pulse of 100 ns can destroy vacuum chamber. It must not
hit chamber only dedicated beam catchers.

## Slide 21: Energy Deposition
graphite
copper
linear drive
460 mm
Thermal simulation shows cooling problem with radiation damaged graphite, 1014/cm2 is reached after ~1/2 day.
Separate catcher for fast extraction, (NUSTAR storage ring experiments)
graphite
Be/Al

## Slide 22: Indian In-kind
Institute CMERI Durgapur designated to do the mechanical design work instead of VECC Kolkata.
However, CMERI wants large extra sum (from India) for: R&D, man-power and infrastructure, 500 INR Lakh (625 k€), + more ? for construction 700 INR Lakh (875 k€), latter close to costbook (779 k€ in 2005)
Reduction of R&D and testing in India would require more effort at GSI.
- choice and behavior of material in beam (GSI)
- design of alignment system (can be GSI)
- types of drives and moving parts (can be partly GSI)
- vacuum layout + testing (should be India)
Or find other partner in India -> time delay. Testing is foreseen this year, contract Feb 2015.
GSI mechanical designs need up-date, to represent state of actual planning.

## Slide 23: Shielding Flask
In-kind Finland
  Hollming Works Ltd., ENMAC,
  Aalto University (academic partner)
Goal: agreement on allowed reduced dose rates
  0.5 mSv/h -> 3 mSv/h
  Weight 60 ton -> 50 ton.
Some uncertainty on size without more detailed beam catcher and target design
Draft specs available (October 2013)
GSI/FAIR will have responsibility on operation permissions, preplanning to go into approval process, then order production.
0.1 m
0.4
5.35 m
Internal guide rails
beam catcher plug
shielding lid
dust collection tray and brushes
Internal crane
hall crane interface

## Slide 24: Large Size Pillow Seals
new polishing, seal #4 ~ 1x10-6 mbar l/s
seal #3 ~ 1x10-6 mbar l/s
Pillow seals to be used in the Target Area
standard will be round Pillow Seal with Ø500mm
special large size rectangular (1200x160 mm2) seals between dipole and beam catcher
Developed together with MEWASA
Test setup at GSI
Requirements fulfilled
Long time stability tests running (temperature, ...)
Next steps: full plug design

## Slide 25
SuperFRS Hot Cell
Based on a study by nuclear
engineering company
Preliminary planning completed
Execution planning running
Mock-up installed on ESR roof
Window frames in preparation
(to be installed during shell construction)
Hot-Cell mockup installed on ESR roof
(Getinge, France)
Window frame at company
(Getinge, Sovis, France)
Quantity: 2
Size: 2.8m x 2.5 m
Weight: 4 ton (each)

## Slide 26: Super-FRS Beam Instrumentation
y-slit system:
block size: 400mm x 90 mm
material: Tungsten alloy
Slit-systems
  Specification established
  Overall 18 slit pairs along the separator
  Remote handling in the Pre-Separator
  Collaboration signed with KVI-CART
  Project group at KVI established
  Kick-off done / regular meetings with KVI
    Pre-designs in preparation
    Pre-Series slit-system expected for Q2/2015
Media pannel,
robot controlled
x-slit system:
block size: 200mm x 200 mm
material: Tungsten alloy
total weight: ca. 750 kg

## Slide 27: Beam Diagnostics
  GEM-TPC (Finnish in-kind)
    Collaboration Partner: HIP, Helsinki
    Various prototypes ready and on-line tested
    Large-active-area size prototype in preparation
    High-energy beam test at GSI, August 2014
    Final specification (Q1/15) → series production
    Ongoing design of multi-channel dead-free FEE
Optical Measurement at HIP
(precision table)
FEE
GEMEX
GEM Foil
Larger active area 380x80 mm2
Twin-TPC design
Usage in Vacuum chamber and air
Including as supply system
Field
Cage

## Slide 28: Layout off the Super-FRS (including revised S-shape EB)
±
revised Energy Buncher & LEB cave

## Slide 29: Energy Buncher: S-shape layout (using standard multiplet magnets)
Flexible operation
  large acceptance spectrometer
  high-resolution / energy buncher mode
  dispersion matching (Main-Separator and EB)
Intermediate focus at focal plane FLF4
  keep overall dispersion in limits
  in particular reduce gap size of magnets (use standard multipole magnets)
  reduce requirements on monoenergetic degrader at FLF5
  reduce technical risks
Enlarged experimental areas
  better matching of detectors / spectrometer performance

## Slide 30: Magnets for Energy Buncher
Magnets are Indian in-kind, revised parameters discussed with VECC
Maximum beam rigidity: 7 Tm
3 dipole units with 30°deflection angle
    superferric, warm iron, SC coils
    usable aperture: (x = ±250mm, y = ±70mm)
    expected weight <80 ton,
    cost reduction, easier to handle and to measure
    VECC is working on the new design
  Multiplet (quadrupole design same as in the separator)
    superferric, cold iron
    usable aperture: Ø380 mm,
    leff: 800 mm, max. gradient: 10 T/m
    configurations: 1 x QS, 3 x QQS, 1 x QQQ
    y-steerer still in discussion
    specifications ready
    saving development time & costs, reducing technical risks
  Magnet testing must be discussed, in principle possible at CERN
Original VECC dipole design

## Slide 31: Cave for LEB/Energy Buncher
Architects feasibility study prepared by ION42 (FAIR architects)
Cost estimate: 8.300k€ (2014)
  breakdown according German CC cost type (KG xxx) provided
Low-energy cave:
  area ≈800 m2
  height: 7.6m
  5 ton crane
MATS/LASPEC (annex):
  area ≈430 m2
  height: 10m (2 floors)
  5 ton crane
Annex space (technique):
  area 2 x 68 m2
  height: 3m / 4.5m (2 floors)
Most important now: clarify funding
Discussion with funding agenecies/RRB has been initiated
Additional required pillars can not be provided in an early phase (mid 2014)
Discussion with FLAIR/SPARC concerning possible impact of FLAIR SPARC building

## Slide 32: Super-FRS Buildings (MSV)
Tunnel 103
(Separator tunnel, supply tunnel)
Build. 006a, Service building
3 floors (~2000 m2)
Technique (PS, controls, ... )
Experimental preparation
Control room, electronics
Gas supply, gas mixing station
Main tunnel access
Build. 006
(High-Energy cave)
On top: Build. 17.2
(FAIR service building)
100 m
Basic evaluation completed
Preliminary planning completed
Approval planning completed
Execution planning under approval
but on-hold now since approximately 12 month
Running: route planning (cable, pipes, cryo)
Formwork planning & Tendering
Establishing cable data bank → tender of cables
FLF2
Experimental Area
FHF1
(End Focus HEB)
Build. 018, Target building
5 floors
Target area, shielding
Technique (PS, controls, ... )
Hot Cell complex
To CR

## Slide 33
Base plate concrete
Iron Shielding
Mass (blue 4574 t,
green 682 t, red 499 t,
all ~ 5756 t
Core
mass: 498.8 t
volume: 71.26 m²
planned as PSP 2.4.11.3.12
but not in cost book ~ 10 M€

## Slide 34: (Detector) Gas Supply
Super-FRS Gas Supply
Gas Mixing Station in Build. 6a
Standard Beam Diagnostic
defined for each focal plane
Detector gases defined for each focal plane (separator)
Gas storage & mixing station
Security requirements to be clarified
LN2 storage available (piping
not provided)

## Slide 35: Summary
SC dipoles: collaboration agreement signed with CEA/Saclay, design finalization and tendering documents in preparation; tender via FAIR, expected to start in Q4/2014
SC multiplets: tendering close to final; contract signing expected for June
Magnet test facility at CERN under preparation; timeline and testing scenario based on 3 test benches
NC magnets: remote alignment under revision, specification in preparation
Revision of target area components and preparation of specifications ongoing (will be partly procured in collaboration with KVI-CART)
Development of various beam instrumentation items in progress (various in-kind/collaboration partners, timeline critical elements under pre-production
Civil Construction
  execution planning under approval (basically on-hold since 12 month)
  route planning so far only for some NUSTAR buildings done
Revised layout for Energy Buncher (S-shape) proposed, using standard multiplets, dipole magnets under redesign by VECC, India