## Slide 1: Management Aspects of the HIT Project
Dr. Udo Weinrich

## Slide 2: Outline
HIT Project
Organisation
Planning along all project phases
Reporting and other communication
Personal statements
2

## Slide 3: HIT Project (former HICAT)
3

## Slide 4: Major Milestones
4
September 2000: Machbarkeitsstudie
Mai 2003: Genehmigung des Projektes
Oktober 2003: Firmen beauftragt
Mai 2004: Grundsteinlegung
Juni 2005: Richtfest
Oktober 2005: Montagebeginn Beschleuniger
September 2006: Gebäudeübernahme Klinik
Dezember 2006: LINAC-Strahl eingestellt
Januar 2007: Montagebeginn Gantry
Februar 2007: 1. Strahl im Synchrotron
Dezember 2007: Synchrotron/HEBT eingestellt
November 2009: Erster Patient behandelt

## Slide 5: Tasks
5
technical leadership
assembly
delivery of beam diagnostics
service of beam diagnostics
know how transfer

## Slide 6: Project Team WBS (04/2006)
6
typical project structure
subproject leaders in department of project leader
technical responsibles in technical departments

## Slide 7: Interfacing to users (04/2006)
7
sorted along topics
always including a clear deputy definition

## Slide 8: Interfacing to Building (04/2006)
8
many strong technical links to building and infrastructure
sorted along technical issues and room issues
support responsibility in some rooms

## Slide 9: Compliance with European laws
9
CE conformity
Risk analysis
Medical products and systems

## Slide 10: Resource loaded planning
10
early for commissioning with beam
commissioning along the beam
on real persons rather than generic resources

## Slide 11: Administrative support
11
early agreement on overtime accumulation and compensation

## Slide 12: Request of building quality
12
easy to define
easy to request
difficult to get into contracts
even more difficult to get assured on the construction site

## Slide 13: site and building
13
early agreement on 14 !! days reaction time on check and release of drawing from building planners
detailied process description for internal procedure in 6 steps

## Slide 14: Assembly preparation
14
many deficits
not always easy to decide what is minor and what is major

## Slide 15: SiGEKO
15
early establishment of safety officer on construction site
agreement on overtime accumulation and compensation

## Slide 16: Compliance with German laws
16
temporary operation permission
was eased by clear strategy for supporting documentation

## Slide 17: Beam sharing with users
17
commissioning with 3 shifts per day
from Monday noon to Saturday Evening
beam was the most critical resource

## Slide 18: Shift planning
18
beam commissioning in shifts
continuous beam commissioning for many months

## Slide 19: Transfer project to operation
19
tests and corresponding documentation
training and corresponding documentation

## Slide 20: The end
20

## Slide 21: Reporting to building coordination
21
building coordination meeting very difficult

## Slide 22: Reporting to GSI accelerator head
22
head of accelerator division H.Eickhoff
shows evolution within GSI organization

## Slide 23: Reporting to upper management
23
several times per year directly to GSI Management
several times per year directly to management of university clinic of Heidelberg

## Slide 24: Shift Reports
24
necessary to inform colleagues in a compact manner

## Slide 25: Weekly Reporting
25
internally
to operation meetings

## Slide 26: Reporting to HIT operation meeting
26
operation meeting started by GSI project team
rapid transfer to HIT operation team

## Slide 27: Formal game with formal partners
27
building and medical project partners reacted very formally
at some occasions formal reactions were necessary
project lead of university hospital proved to be very professional in the end

## Slide 28: Open Day at GSI
28
documentation and participation of therapy team

## Slide 29: Public Relations in Heidelberg
29
own sign on construction site

## Slide 30: Success
30

## Slide 31: Personal statements
I am grateful for all the experience I could gain within this great project – although it came along with a lot of stress
Complex or large projects will be successful due to and not despite of the focusing of the project leader towards project organization. Project Leaders are always under pressure to organize the existing and upcoming challenges within the project.
Complex or large projects will be successful due to and not despite of reporting by project members. Project Managers need to be informed of all critical items in order to organize things properly and they do not have the time to run after the information.
31