## Slide 1: „Status cw-linac“
Motivation
Timeline and status
Testing of components
Further strategy
GSI/HIM : W. Barth ● V. Gettmann ● M. Heilmann ● S. Mickat ●
M. Miski-Oglu ● S. Yaramyshev ● F. Dziuba
IAP GUF: M. Amberg ● M. Basten ● M. Busch ● H. Podlech ●
U. Ratzinger

## Slide 2: Motivation and Main Design Parameter
Status cw-linac, 22.8.16
W. Barth
 | GSI- Unilac | cw-Linac
Beam intensity(particle/s) |  | 
Beam on target | 10 weeks | 4 days
 | GSI- Unilac | cw-Linac
Beam intensity(particle/s) |  | 
Beam on target | 10 weeks | 4 days
Production of element fb (S. Hoffman, GSI)
Reactions at coulomb barrier  production of SHE
Operation cw
Mass / Charge 6
Beam current 1 mA
Injection energy 1.4 MeV/u
Output energy 3.5 - 7.3 MeV/u

## Slide 3: Superconducting CW-LINAC Layout (S. Minaev, 2009)
HLI
injector@GSI
Multigap CH-cavities
Small number of rf cavities and short cavity lengths (up to 1m)
acc. gradient of 5 MV/m  compact linac design
Several cavities, solenoids per cryostat
Modular construction
Status cw-linac, 22.8.16
W. Barth

## Slide 4: Layout and Time Line for Advanced Demonstrator
1.88
1.39
E (MeV/u)
2.4
3
HLI
injector@GSI
A/q=6
Step 0
Step 1
Step 2
demonstrator (1 cavity)
demonstrator (3 cavities)
advanced demonstrator (7 cavities)
2017
2019
2016
11 m
3.6
Evaluated within POF3
Status cw-linac, 22.8.16
W. Barth

## Slide 5: Step 0: CW-LINAC Demonstrator @ GSI
High Charge State Injector (existing)
Matching line (ready)
Technical challenges:
  Design and production of the sc CH-cavity
  Constant alignment of the components during cool-down
LHe infrastructure (ready)
delivered & tested
Tested
delivery @Mai 2016
Status cw-linac, 22.8.16
W. Barth

## Slide 6: Design of Cryomodule by Cryogenic
Final Design
Trial Design Aug. 2010
Frame with Cavity and Solenoids
Assembly
Status cw-linac, 22.8.16
W. Barth

## Slide 7: Delivery to GSI (19.11.15)
Status cw-linac, 22.8.16
W. Barth

## Slide 8: Cryomodule-assembly @ GSI
Frame with the dummy cavity
„Dry“ cooling of sc-solenoids
Special suspension of components preserves alignment during cooldown
Status cw-linac, 22.8.16
W. Barth

## Slide 9: First cool down test @ GSI (17.12.15)
Cryostat installed in cw-bunker
Temperature is monitored during cooldown
sc-Solenoids were ramped at 9.3 T
Standby losses of cryostat 3W
Drift of components during cooldown +-0.15mm
Status cw-linac, 22.8.16
W. Barth

## Slide 10: Cross Bar H-Mode Accelerating Cavity
field of H211 Mode
of ”pillbox“ cavity
Drift tubes are alternating connected to “+” and “-” potential
Cross bar H-mode cavity  CH-cavity
Status cw-linac, 22.8.16
W. Barth

## Slide 11: CH-Cavity for Demonstrator @ 216.8 MHz (F. Dziuba, Ph. D thesis)
b | 0.059
Frequency | 216.816 MHz
Cells | 15
Length bl-def (mm) | 691
Diameter (mm) | 409
Cell length | 40.82
Ea (MV/m) | 5.1
Bp/ Ea | 5.2
Helium vessel
Helium in
Tuner flange
Helium out
Dynamic bellow
tuner
Production @ RI
delivery September 2016
Transverse size & efficiency  2 x 108.408 MHz =216.816 MHz
Status cw-linac, 22.8.16
W. Barth

## Slide 12: Cavity Production @ RI (Bergisch Gladbach, Germany)
cavity inside
rf-coupler flanges
bellow tuner
cavity with end caps
Status cw-linac, 22.8.16
W. Barth

## Slide 13: Quality Factor Q vs Ea for CH-Demonstrator (F. Dziuba, Ph. D thesis)
RF-testing is completed
Q0=5 x 108 @5 MV/m (design acc. gradient)
Demonstrator cavity is in final production step (welding of He-reservoir)
Accelerating gradient can be increased by high pressure rinsing and Ar-discharge
IAP @ Uni Frankfurt
Status cw-linac, 22.8.16
W. Barth

## Slide 14: Transverse Emittance Measurement at Side of cw Demonstrator @ July 2015
Beam test of the matching line
Measurement of transverse emittance at side of cw-demonstrator
Reliable information about transverse emittance at exit of HLI for design of Advanced Demonstrator
Status cw-linac, 22.8.16
W. Barth

## Slide 15: Measurement Results and Backwards Calculation
Slit grid device measure the transverse emittance in horizontal vertical planes
Excitation currents of quadrupoles was gauged prior measurement with dedicated DC current transformer
Backwards calculations has been done by the matrix code ”TRACE 3-D”
Measurement for different quadrupole settings increase the significance
Discrepancy is due to different settings of steering magnets
Status cw-linac, 22.8.16
W. Barth

## Slide 16: Step 1&2: Advanced Demonstrator @ GSI
The standard cryomodule contains 2 cavities and 1 solenoid
Cavity 2&3 are already in production. Delivery @ Q1 of 2017
Tendering for cryostat @ Q4 of 2016
Advanced demonstrator allows first experiment at coulomb barrier for light and medium heavy ions
2.5 m
Status cw-linac, 22.8.16
W. Barth

## Slide 17: Infrastructure @ HIM
Ready to move in
High Pressure Rinsing (HPR)
RF testing (warm & cold cavities)
Cleanroom environment
Optional: setup for BCP
Status cw-linac, 22.8.16
W. Barth

## Slide 18
Summary
  Matching line is tested
  Liquid He infrastructure is tested
  Cold test of entire Demonstrator cryostat (incl. dummy cavity)
  sc-solenoids (B = 9.3 T) successfully tested
  RF-testing of Demonstrator cavity is completed @GUF
  Demonstrator cavity is in final production step
  2nd Rebuncher cavity ready for commissioning
  New clean room@GSI available
  2 Power coupler delivered
  Power coupler test bench in preparation
  Production of two further (short) CH-cavities already started
  Standard cryostat is defined
Status cw-linac, 22.8.16
W. Barth

## Slide 19: Recent delivery of components
108 MHz-rebuncher
Clean room upgrade @GSI
(class ISO 5 (required: ISO 6), at FFU unit: class ISO 2 (required: ISO4))
High Power rf coupler

## Slide 20
  Schedule of activities 2016
  April&July: First beam tests with cryostat
    3D matching
    sc-solenoids
    bunch structure monitor
  July: commissioning of local clean room
  >August: delivery of power coupler and rf-conditioning
  September: Commisiioning/Rebuncher
  October: rf-test of demonstrator cavity at site
  November: beam test of fully equipped cryostat (CH-cavity+solenoids)
  Next steps:
    Further Improvement of the demonstrator cavity
    Ordering of standard cryostats
    Commissioning of infrastructure @ HIM
    Delivery of “short” cavity
Status cw-linac, 22.8.16
W. Barth

## Slide 21: Further strategy I
Status cw-linac, 22.8.16
W. Barth

## Slide 22: Further strategy II
Status cw-linac, 22.8.16
W. Barth

## Slide 23: Further strategy III
Status cw-linac, 22.8.16
W. Barth
HSI
ALVAREZ
HLI
cw-LINAC

## Slide 24
UNILAC Upgrade
  Wie sind die Betriebslimits nach dem Upgrade (10Hz, 0,6ms)?
  10 Hz, ca. 0.5 ms
  Möglichkeiten gibt es diese Limits zu erweitern (20Hz, 2ms, für A3 Energie)?
    Derzeit keine Änderungen beim HF-Upgrade, GF-Beschluss: A1-A3 Senderupgrade>2021
  Übergangsphase
    Mischbetrieb 50Hz und 1Hz Hochstrom
    Mischbetrieb HLI/HSI stellt kein Problem dar
    Mischbetrieb HSI PIG/MEVVA oder MUCIS mit entsprechender Vorbereitung
      Wie kritisch ist der Parallelbetrieb?
      Welcher? – ansonsten: siehe oben
      Gibt es weitere Einschränkungen außer dem MAZ für die Alvarez DC Magnete?
      Es gibt jede Menge Einschränkungen – es hängt davon ab, welche Anforderungen erfüllt sein müssen?
Cw-Linac
  Ist eine Pulslängenvariation möglich?
  Ja, durch Makropulschopper
  Max. m/q? Welche Ionen können mit der heutigen EZR Quelle im cw-Linac beschleunigt werden?
  max. A/q =6, z.B. 48Ca10+, etc. – schwere Ionen stehen nicht mit einer ausreichend hohen Ladung zur Verfügung!
  Wie sind die Schritte eines modularer Aufbaus? Mögliche Ausbaustufen?
    siehe Vortrag, 2016: 1.9 MeV/u, 2019: 3.9 MeV/u (ca. 4.7 MeV/ für A/q=5)
  Ist ein Betrieb mit zweiter Quelle (Penning im nicht cw-Betrieb) möglich?
  Transferlinie HSI => cw-LINAC
Mögliche Strahlführung für einen zweiten LINAC (zB. cw-linac)
  Einkopplung EH, Chopper, Paralellbetrieb X, Y, Z, M
    siehe Übersichtsbild
Offene Fragen...