## Slide 1: machine status
CRYRING@ESR
  ion source operational, screens changed and calibrated
      source taken in operation, Mg beam calibrated to the end of injector
      applications are still buggy, frequent interrupts due to various updates
  CRYRING@ESR model implemented
      a dry-run is ongoing, limited due to simultaneous baking
  second attempt of e-cooler cool down test successful
      magnet filled on 10. Aug, LHe amount for roughly one week
  however, presumably no e-cooler operation due to lack of resources
  bake out of GHTY and YR03 started on 09 Aug, one week late
      commisioning run delay of two days to 22.08 after recabling on Mon and Tue
  detector and laser installation finished, calibration ongoing
  measurement and shift plan discussed and prepared
HITRAP
  cooling trap brought to operation, trapping time of HCI up to a minute
      systematic tests with O4-8+ and Xe30-44+ ongoing
CRYRING@ESR & HITRAP