## Slide 1: Operations - 15.01.2019
budget
  ok
Beam Time preparation
  new version of annual schedule will be published this week (minor changes - harmonization with beam time schedule)
  Commissioning planning incl. Machine Development slots about to get started this week
HKR team:
  3 days operator school ongoing (incl. security lessons)
  RF-conditioning shifts will start on Thursday this week  MCR manned
  Cryring bake out 28.01.-03.01. planned
Shutdown
  shutdown ongoing
  2 Problems:
    some tasks, marked as “proposed” in ACC-API-Sheet, are already planned in detail within the shutdown schedule (e.g. TK-Chopper)
    some tasks, which got priority, are not feasible because of missing parts which were not ordered. (e.g. HHD beamline)
     clarification needed, how to proceed (P. Schütt )
Misc.
  G2H Beamline report in preparation  M. Sapinski
Problems/ Issues:
no transmission monitoring system available for beam time