Proceedings

of the

First Joint BINP - FAIR collaboration Coordination Workshop

5th – 9th November 2018

Budker Institute for Nuclear Physics, Akademgorodok, Novosibirsk

Organisers

P. Shatunov

M. Kuzin

S. Utermann

1	General reports	4

1.1	FAIR project status	5

1.2	Status of HEBT	5

1.3	Status of CR and TCR1	5

1.4	Status of pBar separator	5

1.5	Status of Super-FRS	5

1.6	Logistics, pre-assembly and examples	5

1.7	PMO, Quality assurance and BINP	6

1.8	Digital mock-up	17

1.9	SPARC@HESR	24

2	Collector Ring	25

2.1	CR project(s) kick-off	26

2.2	Installations	33

2.3	CR kick-off continuation	34

2.4	CR magnets status	35

2.5	CR vacuum system	35

2.6	CR beam diagnostics	35

2.7	CR beam dynamics	35

2.8	GSI contribution to CR (RF, debuncher, stochastic cooling etc.)	35

2.9	CR vacuum	35

2.10	CR installation	35

2.11	CR injection/extraction	35

2.12	ILIMA	36

2.13	GSI contribution to CR beam diagnostics	45

2.14	CR magnets status	45

2.15	CDR CR vacuum chambers	45

2.16	FDR CR dipole	45

2.17	CDR CR pickups	45

3	Super Fragment Separator	46

3.1	Radiation hard magnets for Super-FRS	47

3.2	Super-FRS magnet testing	64

3.3	Super-FRS vacuum	64

3.4	Super-FRS installation	64

4	High Energy Beam Transport	65

4.1	Results of the SAT, HEBT vacuum chambers batch 2	66

4.2	HEBT vacuum chambers batches 2&3	67

4.3	HEBT vacuum components beyond batches 2&3	72

4.4	HEBT magnets batches 2 and 3	78

4.5	HEBT magnets beyond batches 2 and 3	86

4.6	Update on HEBT beam instrumentation (TCR1)	89

4.7	HEBT time schedule	89

4.8	Pre-assembly and istallation	89

4.9	HEBT round-up	90

5	pBar	93

5.1	P-bar power converter	94

5.1.1	P-bar power converter components	94

5.1.2	Action items	94

5.2	P-bar vacuum	95

5.3	P-bar magnets	99

5.4	TCR1 magnets	99

5.5	P-bar diagnostics	99

5.6	Update on p-Bar beam instrumentation	100

5.7	p-Bar collimators	101

6	Installation and building	102

7	CR installation	103

8	HAOI and other installation matters	103

9	Steering activities	104

10	Introductions and agenda	105

1.	HEBT vacuum chambers (batches 2&3) without FBL	105

2.	106

3.	HEBT Vacuum batch 4	106

4.	Radiation resistant dipoles for Super FRS (2 pcs)	107

5.	Radiation resistant multipoles for Super-FRS	107

Super-FRS diagnostics chambers	108

6.	Super-FRS dipole chambers	108

7.	p-bar rest contract	108

8.	Vacuum chambers forgotten beam line (FBL)	109

9.	PANDA dipole	109

10.	Other business	110

11	Possible future collaborations	111

12	NEG pumps (and ion getter pumps?)	114

13	Proposal of additional beam instrumentation items	118

# General reports

## FAIR project status

Corresponding Author(s): j.blaurock@gsi.de

## Status of HEBT

Corresponding Author(s): f.hagenbuck@gsi.de

## Status of CR and TCR1

Corresponding Author(s): koop@inp.nsk.su

## Status of pBar separator

Corresponding Author(s): k.knie@gsi.de

## Status of Super-FRS

Corresponding Author(s): h.simon@gsi.de

## Logistics, pre-assembly and examples

Corresponding Author(s): h.reich@gsi.de

## PMO, Quality assurance and BINP

Corresponding Author(s): h.schwarz@gsi.de

## Digital mock-up

Corresponding Author(s): c.will@gsi.de

## SPARC@HESR

Corresponding Author(s): a.kalinin@gsi.de

# Collector Ring

## CR project(s) kick-off

Corresponding Author(s): koop@inp.nsk.su

| – minutes | Nr.: 20181106 |
| --- | --- |
| Minutes of the CR parallel session, 06th November 2018, 1st BINP-FAIR Collaboration Coordination workshop | Name: O. Gorda |

| Important: | How to treat this document: I: Information (by xy) P: Presentation R: Remark D: Decision Q: Question A: Action Item |
| --- | --- |

| Topic | Due Date | Respsbl. |
| --- | --- | --- |

| - CR project – general aspects. |  |  |  |
| --- | --- | --- | --- |
| 1.1 | P (O. Dolinskyy) General overview and status of the CR project. |  |  |
| 1.2 | TCR1 diagnostics I (I. Koop): BINP is interested in production of the rest of TCR1 diagnostic components (fast current transformer and scintillation screens) which are presently assigned to GSI. A: BINP will prepare a letter of proposal to assign the rest TCR1 diagnostics to BINP. List of corresponding items with PSP-codes shall be provided to BINP by O. Chorniy. The letter of proposal will be prepared by Y. Rogovskiy/I. Koop and given to D. Urner who will then take necessary formal actions. We are interested in assignment of the components to BINP as soon as possible taking into account that BINP is already planning CDR/FDR. | 09.11.2018 | O.Chorniy, Y.Rogovsky, I.Koop |
| 1.3 | pbar channel diagnostics I (I. Koop): We would like to overtake the pbar-channel diagnostics if it is identical to CR/TCR1 design as we have already started the procurement. R (M. Schwickert): For pbar part diagnostics, we have to first discuss technical details before discussing the assignment and contracting of the pbar diagnostics. A: Technical discussion on the possibility to use the CR-type design of the beam diagnostics devices in the pbar-separator shall be organized during this workshop. | 09.11.2018 | O. Chorniy, Y.Rogovsky, M.Schwickert |
| 1.4 | Building planning R (O. Dolinskyy) Two change requests (building planning and power requirements) have been prepared and submitted by BINP. FAIR S&B has accepted the change requests. Currently planning of the CR building is stopped. It will be discussed in the dedicated workshop between FAIR S&B and BINP when and how to proceed with the building planning. A: The date of the workshop FAIR S&B and BINP has to be fix soon. The agenda for the workshop has to be prepared in advance. | 20.12.2018 | H. Hageslkamp, O. Dolinskyy |
| 1.5 | Organizational issues A: Monthly CR coordination meeting shall be re-established. Date and time has to be fixed during this workshop. A: Date for the next workshop between BINP and FAIR at GSI has to be fixed during this workshop. R (O. Dolinskyy): Monthly reporting in EDMS has to be regularly prepared for each WP prior to the regular PPM meetings. | 09.11.2018 09.11.2018 | I.Koop |
| 1.6 | Project Structure I (O. Dolinskyy) WP CR Installation – Oleg Gumenyuk is proposed to overtake this work-package starting from January 2019. |  |  |
| 1.7 | Communication A: Visit of the BINP QA expert shall be organized to discuss QA aspects with H. Shwartz. Date for this visit shall be agreed and fixed during this workshop. A: In table of the contact persons, Mr. Karnaev shall be replaced by Mr. Senchenko. Mr. Kolmogorov shall be replaced by Mr. Senkov. Rahimov shall be corrected to Rakhimov. | 09.11.2018 09.11.2018 | I.Koop, H.Schwarz O.Dolinskyy |
|  | Alignment A: BINP experts on magnet alignment will be invited to attend one of the sessions of this workshop and discuss communication issues. A visit of the BINP alignment team to GSI shall be planned during this workshop. | 09.11.2018 | I.Koop |
| 1.8 | Risk assessment and safety A: BINP shall designate a person who will be responsible for the risk assessment and implementation of safety regulations and directives. A: E. Petrova will contact H. Schwarz during this workshop to discuss requirements and necessary steps in the risk assessment issues. | 09.11.2018 09.11.2018 | I.Koop E.Petrova, H.Schwarz |
| 1.9 | Planning A: Time schedule for all required milestones for all BINP WPs has to be clarified and fixed during this workshop. R (O. Dolinskyy) Completion of required milestones is defined and fixed by the corresponding protocol with signatures of the involved BINP and GSI/FAIR persons as defined by the SPL. A: Optimization of the time frame for the CR pre-assembly and installation shall be discussed, and corresponding dates shall be fixed during this workshop. | 09.11.2018 09.11.2018 | WPLs WPLs, SPL |
| 1.10 | Manpower resources I (O. Dolinskyy) Preliminary estimations for the required manpower resources from GSI technical departments have been done for the CR project during the next years. A: We shall clarify with BINP WPLs during this workshop, what is the amount of GSI manpower resources that BINP needs as assistance from GSI technical departments during the execution of the CR project in the next years. |  |  |
| - CR beam diagnostics. |  |  |  |
| 2.1 | P (Y. Rogovsky): Overview and status of CR beam diagnostics. |  |  |
| 2.2 | CR Beam Position Monitor A: CDR of the CR BPM will be presented during this workshop. | 09.11.2018 | Y.Rogovsky |
| 2.3 | CR Scintillation Screen A: CDR of the CR Scintillation Screen will be presented during this workshop. | 09.11.2018 | Y.Rogovsky |
| 2.4 | CR Beam Loss Monitor A: During this workshop, we have to clarify whether the BLM should be assigned to GSI. | 09.11.2018 | Y.Rogovsky |
| 2.5 | Planning A: A more detailed and accurate time schedule of the component delivery shall be discussed. A: Separate delivery schedule milestones have to be specified for the TCR1 diagnostics components. | 09.11.2018 09.11.2018 | Y.Rogovsky Y.Rogovsky |
| 2.6 | Procurement R (O. Dolinskyy) BINP components which should be procured by GSI, have to be included into a list together with other components and delivered to D. Urner as a request for procurement. A: Possibility of delivery of the Libera to BINP has to be discussed with D. Urner. As a second option, delivery of the GSI test-box for pre-amplifier can be considered. A: Establish contact to Slovenia provider on the possibility to apply their pneumatic drives which have been planned for other devices at GSI also for BINP diagnostics. BINP drawings shall be provided to the provider. | 16.11.2018 20.12.2018 | Y.Rogovsky, O.Chorniy O.Chorniy, M.Schwickert |
| 2.7 | P (O. Chorniy) Overview of CR beam diagnostics – GSI in-kind. |  |  |
| 2.8 | DAQ CR Scintillation Screen A: It shall be checked with D. Urner whether the DAQ for scintillation screens has already been contracted. If not, it has to be included into the next in-kind contract between FAIR and GSI. | 09.11.2018 | O.Chorniy |
| 2.9 | CCC I (O. Chorniy): The prototype of the CCC cryostat is presently under production. The prototype will be tested at CRYRING. Afterwards, the specification will be prepared for the CR device. Then GSI will produce the device for CR. |  |  |
| 2.10 | Super-FRS BPM A: Information regarding the required changes (flange type etc.) of the BPM design for Super-FRS will be delivered to BINP during this workshop. | 09.11.2018 | M.Schwickert |
|  | - CR magnets. |  |  |
| 3.1 | P (A. Starostenko) Status of CR magnets. |  |  |
| 3.2 | A: A more detailed production and delivery time schedule including separate milestones for each of the series components shall be prepared for all magnets during this workshop. | 16.11.2018 | A.Starostenko, I.Koop |
| 3.3 | A: Meeting with QA experts shall be organized to discuss and clarify details on the documentation preparation. | 09.11.2018 | A.Starostenko |
| 3.4 | A: Concept of integration of the SC microwave damping modules into the wide quadrupole-sextupole chamber has to be discussed and clarified during this workshop. | 09.11.2018 | A.Starostenko |

## Installations

Corresponding Author(s): h.reich@gsi.de

## CR kick-off continuation

Corresponding Author(s): konstantin.istomin@fair-center.eu

Suggestion to include the following topics into the CR parallel I/II session

- BINP liaison officer

- CR installation plan / CR Schedule

  - Establishment of baseline schedule during workshop.

  - procedure how to modify schedule in future

  - discussion of possible conflicts with priorisation of FAIR items in workshop and design office

- Provision of items by FAIR:

  - establish procedure

- Update of WPL list including email addresses an phone number of BINP CR team and FAIR CR team

- Come up with a procedure for CDRs and FDRs also in view of a biannual workshop.

## CR magnets status

## CR vacuum system

Corresponding Author(s): a.a.krasnov@inp.nsk.su

## CR beam diagnostics

Corresponding Author(s): rogovsky@inp.nsk.su

## CR beam dynamics

Corresponding Author(s): dshwartz@inp.nsk.su

## GSI contribution to CR (RF, debuncher, stochastic cooling etc.)

Corresponding Author(s): o.gorda@gsi.de

## CR vacuum

Corresponding Author(s): a.a.krasnov@inp.nsk.su

## CR installation

Corresponding Author(s): a.prosvetov@gsi.de

## CR injection/extraction

Corresponding Author(s): p.yu.shatunov@inp.nsk.su

## ILIMA

Corresponding Author(s): h.weick@gsi.de

## GSI contribution to CR beam diagnostics

Corresponding Author(s): o.chorniy@gsi.de

## CR magnets status

Corresponding Author(s): astar_qqq@yahoo.com

https://edms.cern.ch/document/2025535/1

## CDR CR vacuum chambers

Corresponding Author(s): a.kraemer@gsi.de

Formularbeginn

https://edms.cern.ch/document/2037672/1.

Formularende

## FDR CR dipole

Corresponding Author(s): koop@inp.nsk.su

## CDR CR pickups

Corresponding Author(s): rogovsky@inp.nsk.su

# Super Fragment Separator

## Radiation hard magnets for Super-FRS

Corresponding Author(s): h.leibrock@gsi.de

Parallel Session Super-FRS on nc Magnets (20181106 12:00-~16:00)/DRAFT

Email distribution list:

a.v.utkin@inp.nsk.su ; d.s.gurov@inp.nsk.su ; h.weick@gsi.de; m.eibach@gsi.de; c.muehle@gsi.de; c.will@gsi.de; s.puroshothaman@gsi.de; h.simon@gsi.de ; s.utermann@gsi.de ;

Participants: Christina Will, Hanno Leibrock, Carsten Mühle, Sivaji Purushothaman, Martin Eibach, Denis Gudrow, Anatoly Utkin, Sonia Utermann (first part), Victor Varentsov (first part), Yuri Shatunov (first part), Haik Simon (minutes)

12-13: Dipole Presentation (H. Leibrock)

Dipoles

Q-BINP: Lubricant type? TFPE Oil (Flustar up to 1MGray) . Why not Graphite or similar ?
   Recommendation by the supplier of gear boxes, no issue from radiation side, lubricant presence for
   case of rare use.
   Responsibility for design on GSI side, i.e. no technical issue.

Conditions in shielded tunel: Site shall accessible only occasionally for urgent maintenance.

Installation procedure : Support, lower yoke with chamber, top part

No technical issues left (BINP ok)

14- 15  Qudrupole Presentation (H. Leibrock)

Q1a-Q1b combination

Q-BINP: Will different types for Q1a 1b require different tools?  -  yes

Coil production: Winding scheme? Pan cakes  (see attached document)
(separation with standard length of Hitachi, loger would be Tyco cable)

AI: GSI (H. Leibrock) provide details of winding idea and choice of direct cooling
(focus on molding form)

Installation procedure: Support, (frame with chamber and quad) – ok
Q-GSI: Could system  be prepared for being split up in two parts? - ok

General question:
Why a directly cooled magnet is used? Cable with water duct infers potential difficulties
AI: GSI (H. Leibrock) provide details on indirect vs. Direct cooling.

Q-BINP: Who produces cable? -  
Hitachi: GSI has contact via RIKEN, 
Q-BINP: What is the price per meter?

AI: GSI (WPL) shall find cable supplier and price (focus on Japanese suppliers and Tyco)

Q-BINP: Are the lifting bayonetts items that can be purchased  (40t)? 
Shall it be an own design with related responsibility or a purchasing piece?

AI: GSI (Ch. Will) checks whether this is available

Q-GSI: Can the same steel be used as for the dipoles – yes

QS combination:

Installation sequence: support –yellow frame with installed magnets

Q-GSI: Can BINP chamber be alreday be integrated? 
      (Full system delivery avoids interface and pre-assmbly issues)

AI: BINP Can chamber integration be foreseen at BINP premises ?
AI: GSI(S. Puroshotaman/H. Weick)  Check chamber dimension and shape

Q-BINP: How should water interconnections between lower and upper part be done (swagelock)? -  
     Metal seals required, wleding/cutting shall be avoided

Full assembly at BINP would be favourable

Magnet Q2-S scheme ok, no show stopper (full integration tob e checked), 
prerequisite: cable procurement conditions clarified.

Sextupole Beam Catcher combination

Installation sequence: Support – Internal frame with Sextupole (potentially with beam pipe)

AI: GSI+BINP Scope definition: Sextupole+internal frame ((+ chamber) + Support)
Clarification of Interfaces: to Beam catcher (CMERI) & Shielding

No obvious issues, final scope & interfaces to be clarified

Conclusion/Remaing issues

Question to management: 
    Can a supporting R&D contract be closed (e.g. on coil production) in order to further clarify
    price tags and remove technical uncertainties? – AI (BINP): Clarify necessary R&D items

Overall schedule:

Dipole schedule / Multipole schedule

Attachments:

- Presentation

- Information Material on coil winding

## Super-FRS magnet testing

Corresponding Author(s): h.simon@gsi.de

## Super-FRS vacuum

## Super-FRS installation

Corresponding Author(s): h.simon@gsi.de

# High Energy Beam Transport

## Results of the SAT, HEBT vacuum chambers batch 2

Corresponding Author(s): p.m.suherman@gsi.de

## HEBT vacuum chambers batches 2&3

Corresponding Author(s): l.urban@gsi.de

## HEBT vacuum components beyond batches 2&3

Corresponding Author(s): l.urban@gsi.de

## HEBT magnets batches 2 and 3

Corresponding Author(s): c.muehle@gsi.de

## HEBT magnets beyond batches 2 and 3

Corresponding Author(s): c.muehle@gsi.de

## Update on HEBT beam instrumentation (TCR1)

Corresponding Author(s): m.schwickert@gsi.de

## HEBT time schedule

Corresponding Author(s): f.hagenbuck@gsi.de

## Pre-assembly and istallation

Corresponding Author(s): h.reich@gsi.de

## HEBT round-up

# pBar

## P-bar power converter

Corresponding Author(s): u.clausen@gsi.de

### P-bar power converter components

| Pieces | PSP | Typ |  | Nomenclature |
| --- | --- | --- | --- | --- |
| 1 | 2.9.3.1.1.1 | pB.D1 | Dipole | PS01MH01 |
| 8 | 2.9.3.2.1.1.1 | pB.Q1 | Wide Quadrupole | PS01QS04-11 |
| 1 | 2.9.3.2.2.1 | pB.Q2 | Wide Quadrupole radiation hard | PS01QS03 |
| 2 | 2.9.3.2.1.1.3 | pB.Q4 | Narrow Quadrupole radiation hard | PS01QS01-2 |
| 4 | 2.9.3.3.1.1 | pB.C1 | Sextupole | PS01KS01-4 |
| 7 | 2.9.3.4 | pB.C2 | Steerer | PS01KH01-3 PS01KV01-4 |

### Action items

- Data for Quadrupole magnets, radiation hard, still needs to be defined

- Contract for power converter is needed

## P-bar vacuum

Corresponding Author(s): a.kraemer@gsi.de

## P-bar magnets

Corresponding Author(s): p.yu.shatunov@inp.nsk.su

## TCR1 magnets

Corresponding Author(s): p.yu.shatunov@inp.nsk.su

## P-bar diagnostics

Corresponding Author(s): rogovsky@inp.nsk.su

## Update on p-Bar beam instrumentation

Corresponding Author(s): m.schwickert@gsi.de

## p-Bar collimators

Corresponding Author(s): p.katrik@gsi.de

# Installation and building

# CR installation

Corresponding Author(s): koop@inp.nsk.su

# HAOI and other installation matters

Corresponding Author(s): h.reich@gsi.de

# Steering activities

# Introductions and agenda

Corresponding Author(s): david.urner@fair-center.eu

| Meeting: | Steering parallel II at 1st BINP-FAIR workshop |  |
| --- | --- | --- |
| Date: | 06.11.2018 13:00-17:45 | Author: S. Utermann |
| Participants: | Y. Levichev V. Varentsov D. Urner J. Blaurock A. Andreanov D. Shwarz S. Utermann M. Schwickert M. Marenich L. Urban A. Krämer A. Krasnov H. Simon |  |
| Distribution: | Participants + K. Knie, Y. Rogochev, Y. Tichonov, P. Shatunov, F Hagenbuck |  |
| Document Number: | F-PR-...to_follow (see work instruction for document identification) |  |

| A: Action, D: Decision, I: Information |  | Who | Due Date |
| --- | --- | --- | --- |
| # HEBT vacuum chambers (batches 2&3) without FBL |  |  |  |
| D I A A A | 1.544 M€ at 2018 prices and scope are acceptable to BINP Want to close this ASAP without FBL FAIR needs a letter of assignment, IKRB will write recommendation to Council, Council makes assignment, then official negotiations. Request for assignment is drafted, FAIR will support this letter. FAIR is confident that request will be recommended by IKRB (we have submitted estimates based on information from BINP). Specs are ready, CB value is ready S. Utermann to send request for assignment draft to Y. Levichev. ROSATOM does not need to sign. YL returns to IOP (DU, SU or MM) within two weeks. HEBT SPL needs to specify size of initial tubes (standard tube size or not (this has financial consequences) --> This needs to be sorted before council (mid-December) Action: Aim to close batch 2 and 3 contract 2018 SU to send to YL within two weeks. Partly unassigned, we can put a disclaimer to this end in the contract. | SU, YL F. Hagenbuck SU | 2 weeks By council 2 weeks |
| Beam Diagnostics (mechanical and pre-amp, screens and drives) |  |  |  |
| I A A I I | Items identical or similar to CR M. Schwickert will send Y. Leveichev, D. Shwarz & Y. Rogovsky--> a technical description and scope and PSP and CB value. (YR is BINP responsible) YL will answer first informally in writing, then assignment will follow as above. First technical, then administrative Capacity is available at BINP for greater productivity beyond batches 2 & 3 | MS, DS, YR YL, FAIR IOP |  |
| # HEBT Vacuum batch 4 |  |  |  |
| I A A A A | Technical aspects were discussed in parallel session. Because there is little scope for series production (many types), A. Krasnov has concerns about BINP workshop capacity. Action: L. Urban sends list to A.Krasnov Action: FAIR looks at relaxing schedule wrt to pre-assembly and also looks at standardisation Meeting L. Urban and A. Krasnov to look at the proposed delivery schedule for batch 4 this week BINP to check workshop capacity, taking into account batches 2&3 and all the others (S-FRS, CR etc.) | LU LU & DMU LU & AK AK | Q1 2019 This week Q1 2019 |
| # Radiation resistant dipoles for Super FRS (2 pcs) |  |  |  |
| I A A A | 1.9 M € per dipole, and FAIR would supply the cable at 450 k per dipole (2018 prices) So BINP would make 2 dipoles for 1.45 M each, 2018 prices. Not yet assigned to BINP. BINP can possibly buy the steel for the dipoles and multipoles together: it is the same steel, should BINP agree to provide multipoles Dipole contract is on the critical path Specs and draft contract are ready. Decision from BINP this week, after magnet expert meetings SU to send YL draft contract. Aiming for 2018 signature (as HEBT vacuum batches 2&3) including the assignment clause. IOP to get the assignment done, responsible IOP. | YL and BINP magnet experts SU IOP | This week 2 weeks By council |
| # Radiation resistant multipoles for Super-FRS |  |  |  |
| I A A A D | 3 different quadupoles, 2 sextupoles and beam catcher, not assigned 1.2 M Euro H. Simon reports that technical discussions are still underway re. steel procurement, titanium for chamber with grazing primary beam. Action: BINP to make a cost estimate: H Simon will send technical information to the sessions during this week. BINP to assess the resources needed to develop cost estimate by the end of November. Video conference for follow up (also supports, beams, pipes). Result may be R&D contract or price quote. No assignment until then. | HS, YL BINP HS, YL, others | This week By 30 Nov End Nov |
| # Super-FRS diagnostics chambers |  |  |  |
| I D A D | Status: Assigned to BINP, CB exists. Specs are ready. BINP can produce at CB 2005 escalated to 2018. Specs are ready for beam diagnostics chambers. A. Krasnov: BINP has capacity. Decision: no AFAAs (Annex for additional assignment) SU to send draft to YL within two weeks Aim for contract signature end of 2018 | SU | 2 weeks |
| # Super-FRS dipole chambers |  |  |  |
| I A A | Super FRS dipole chambers are very similar to CR vacuum chambers. Assigned to BINP, PSP in CB. There has been change of scope -->dedicated beam catcher in the chamber. Need adjustment of specs (titanium or not?) Action: joint preliminary technical decision process starting this week. Preliminary assessment finished by the end of 2018 in writing as joint initiative. Then BINP needs to estimate price. | HS, others FAIR, BINP | This week End 2018 |
| # p-bar rest contract |  |  |  |
| Q D Q A A A | Workshop capacity? It was close before CR was moved by a year. Scope includes 2 quadrupoles and 1 dipole radiation hard. Elements before TCR line that are identical to CR: BINP agrees to produce all items that are already series items. CR type quadrupoles: BINP capacity is there. What about beam optics? What happened to the change request to optical ion layout? Who is the responsible person at fair? Sergey Litvinov? FAIR to answer this week. Complete beam optics: K. Knie end of February 2018 (to be confirmed by KK) --> send to D. Shwartz and P. Shatunov Scope/list of components: K. Knie --> BINP | DU KK KK | This week 28.2.19? Q1 2019? |
| # Vacuum chambers forgotten beam line (FBL) |  |  |  |
| I A Q A A A D | CB 8 value = 4.8 M€ in 2018 money (power, magnets, vacuum etc. D. Urner notes that some of FBL was reassigned to ACC from EXP. Same type, FAIR will join the PSPs. Not in costbook 7 Action: FAIR to prepare detailed steering activities this for 2nd FAIR-BINP meeting. How soon does BINP need the contract? To this end: Action: FAIR itemised list AtB to Y. Levichev, A. Krasnov and I. Morozov in two weeks Q is optical layout ready? Action: D. Urner to check BINP to say when they need the contract in order to fit FBL production into existing series production. Aim for contract signature 2nd half of 2019 | IOP, PMU DU DU A.Krasnov | Q1 2019 2 weeks 2 weeks Q1 2019 |
| # PANDA dipole |  |  |  |
| I A | Proposal: common collaboration contract FAIR-BINP In draft at FAIR Then action an implementing agreement for the PANDA dipole. 300 k€ R&D engineering agreement exists, signed between FAIR and BINP Action: meeting D. Urner and Y. Tichonov to discuss the status of the R&D contract and future contracts this week | DU & YT | This week |
| # Other business |  |  |  |
| D D A A | On Thursday afternoon there will be a parallel session to disccuss progress 17:00 and 18:00. action S Utermann: communicate this, D. Shwartz to invite on the BINP side BINP liaison officer programme: all parties wish an extension. 90 days is not enough. Letter to Y. Leveichev from J. Blaurock --> BINP directorate Next liaison officer need a visa with a work permit for Germany. FAIR to check. | SU, DS JB DU | Wed. |

# Possible future collaborations

Corresponding Author(s): david.urner@fair-center.eu

# NEG pumps (and ion getter pumps?)

Corresponding Author(s): a.kraemer@gsi.de

# Proposal of additional beam instrumentation items

Corresponding Author(s): m.schwickert@gsi.de