## Slide 1: CR BINP-Workshop 21.05.2019 Overall process analysis machine installation CR
J. Dübel-Müller
21.05.2019

## Slide 2: CR | Einbringen der Maschine - Machine Installation
ID |  | Aktion erforderlich - Action required |  | Wer? Who? |  | Bis wann? Until?
1. |  | Versorgungsbereich: Zeitpunkt der Einbringung der stochastischen Kühlleitungen zu klären (1,25m Höhe). Supply area: Clarify when the stochastic cooling lines should be installed (1.25m high). |  |  |  | 
2. |  | Strahlbereich: Durch wen wird der Kabelanschluss der Netzgeräte und Low Level Racks ausgeführt? Beam area: Who is responsible for the cable connection of the power supplies and low level racks? |  |  |  | 
3. |  | Nachfolgend ist nur RRF dargestellt. Erstrebenswert wäre eine ähnliche Detailschärfe für alle Bereiche. Only RRF is shown in the following. A similar sharpness of detail would be desirable for all areas. |  |  |  | 
4. |  |  |  |  |  | 
6. |  |  |  |  |  | 
7. |  |  |  |  |  | 
8. |  |  |  |  |  | 
9. |  |  |  |  |  | 
Aktionsliste – List of actions

## Slide 3: CR | Machine Installation
Rough timeframe
Nov./ Dec. 2022 and
Feb./ Mar. 2023
Overall process analysis G007/ E10 – Supply Area RRF CR Debuncher
Stochastic cooling line
See point 1 List of actions

## Slide 4: CR | Machine Installation
Transport of power supply units
(CR BB)
Before tunnel installa-tion
Overall process analysis G007/ E10 – Supply Area RRF CR Debuncher
Protection of power supply units
(CR BB)
Position of the power supplies.
Transport equipment+power supply equipment
TGA comple-ted
Transport Low Level Racks
(CR BB)
Electrical connection power supply unit 400V Netz
Systemintegration (RRF)
Systemintegration Low Level (RRF)
Air supply (external)
Overall integration(RRF)
Assemblies are positioned and integrated
external
execution
external execution
Dust-free environment or safe protection against dust.
- Cable pull completed
- Electricity available
Cooling air available
- Cable trays laid and cable trays above the low level racks (length compensation)
With electric forklift.
Positioning together with user desired.
No pre-assembly possible.
Duration approx. 4 weeks.
No pre-assembly possible.
Duration approx. 4 weeks.
Ring HF (RRF)

## Slide 5: CR | Machine Installation
Rough timeframe
Sep. 2022 - Jun. 2023
Overall process analysis G007/ E10 – Beam Area RRF CR

## Slide 6: CR | Machine Installation
Ring HF (RRF)
Placing 5 cavities
Placing 5 power amplifier
total integra-tion
external
execution
Placing 5 x 2 Tetrodes
Placing water distributors
Placing 3 Interface- racks (wall)
Connec-ting water distributor.(to system)
Connec-ting water distributor.(to compo-nents)
To central water system/ to components (lay hoses)
Alignment of 5 cavities on Blue-/ Beamline
Connec-tion of cavities to VAC (CF flange)
Cable connection to Inter-faceracks
Connection of cables to cavities
Cable connection to power amplifiers
Cable connection to Low Level Racks
Cable connection to power supply units
Durch wen?
By whom? (see action list ID 2)
Installation of tetrodes in power amplifier
- Lifting device required
- special care, tetrodes are very sensitive, therefore installation shortly before total/ final integration
Overall process analysis G007/ E10 – Beam Area RRF CR