| – minutes | Nr.: 20190524 |
| --- | --- |
| Minutes of the CR alignment session, 24th May 2019, 2nd BINP-FAIR Collaboration Coordination workshop |  |

| Important: | How to treat this document: I: Information (by xy) P: Presentation R: Remark D: Decision Q: Question A: Action Item |
| --- | --- |
| Participants | O.Chorniy, D. Bianculli, O.Dolinskyy, O.Gorda, R.Fuchs, R. Hetrick, O.Meshkov, K.Muehle, I. Pschorn, M.Radionova, A.Rakhimov, A.Rogovsky, S.Semenov; L.Serdakov, S.Shiyankov, A.Starostenko, D.Shwartz A.Sukhanov, T.Ziglasch, C.Zhang, C.Will |

| Topic | Due Date | Respsbl. |
| --- | --- | --- |

| - Alignment in the CR |  |  |  |
| --- | --- | --- | --- |
| 1.1 | I (R. Fuchs): GSI intend to take over the responsibility for the alignment at CR. The corresponding in-kind contract can be signed after definition of work scope, which should be performed by GSI and BINP, and the decision of the FAIR council to assign the alignment of CR as a German in-kind |  |  |
| 1.2 | R (D. Shwartz): BINP would like to have a possibility to pre-align the magnets together with vacuum chambers with accuracy of ±0.5 mm during installation. This is needed mainly for assembly, closing and compensation of tolerances in the stiff vacuum system of the CR. |  |  |
| 1.3 | R (I. Pschorn): Usually the GSI team makes fine alignment only for IOL purposes. One has to find a special solution for the CR installation process, which presently out work scope of GSI alignment group. |  |  |
| 1.4 | A (D. Shwartz, O. Dolinskyy): A table of required alignment tolerances for the different CR magnets/components based on ion-optical requirements has to be prepared and sent to the GSI alignment team. |  |  |
| 1.5 | I: 3D models of the stands, magnets, vacuum chambers are available at DMU and can be provided by Ina Schurig. In EDMS one can find specifications of all CR magnets. |  |  |
| 1.6 | I (A. Starostenko): Fiducialisation will be done by BINP. Information about fiducials and correlation of their positions with magnetic axis will be provided. |  |  |
| 1.7 | A (D. Shwartz): BINP will prepare a list of final coordinates of the mechanical fiducialisation for the magnets and diagnostics components. |  |  |
| 1.8 | R (Y. Rogovsky) BINP will provide different information required for alignment purposes: geometrical center of vacuum chambers, electrical center of BMPs, difference between the centers of the chamber and BPM with respect to the fiducials etc. |  |  |
| 1.9 | R (I. Pschorn) Measurement protocols will have to be prepared in an understandable way. BINP and GSI teams should stay in contact and develop common protocol templates. |  |  |
| 2.0 | I (I.Pschorn) After discussion the following understanding came up: The BINP requires that the alignment team should accompany the installation work from first up to last magnet. Not the magnets (like supposed at first), but the vacuum flanges should be aligned to each other with +/- 0.5 mm precision during the installation of the machine, so that the welding method works (magnet yoke can be pre-aligned with some mm). This means that a relative alignment of 0.5mm between two adjacent flanges is required, but not an absolute accuracy of the vacuum system of 0.5mm in relation to the blue line and thus to the ion-optical layout. This accompanying of the installation work is therefore not a classic task of alignment (=high-precision positioning of the accelerator components in relation to the overall 3D machine coordinate system), but part of the assembling of the system.” (The +/- 0.5 mm cannot be found in the installation concept, maybe it’s good to get the written work procedure of welding the flanges in order to understand at best how the support of BINP should be) “GSI-alignment-team is not able to comply with the requirement of accompanying the installation/assembling work of CR. As intended in each FAIR machine, external service professionals must be hired. For an additional CR assembling work these are not included in any cost book or timetables.” |  |  |
| 2.1 | A. Postscript (O.Dolinskyy) To clarify what kind of activity is necessary to be done by alignment team, it is proposed that BINP team prepares detailed installation process in such a way that each individual work step is described exemplarily using e.g. two „modules“. So we can better understand what kind of work is really needed from alignment team, what waiting times occur, what accuracies are actually needed for what, etc. The cost for accompanying alignment works and its assignment should be defined. GSI and BINP teams collaborate on this issue. | 15.08.2019 | A.Rakhimov/D.Shwartz/V.Prosvetov |
| 2.2 | A. Postscript (O.Dolinskyy) In the next Level One Workshop in September 2019 the full scope of alignment work of CR should be finally presented, so that in the Q4/2019 FAIR council the decision to assign the alignment of CR as a German in kind contribution can be taken.“ | 17.09.2019 | D.Shwartz(BINP)/I.Pchorn(GSI) R.Fuchs |