## Slide 1: SIS 18 Status

## Slide 2: Status Digitizer Project
There are no dedicated resources for that project right now. It is running on „best-effort“ basis.
Goal is to roll out the systems till EOY Eng Run:
  SIS18 MTI optimization (Bumper, TK transformer, septum..)
  SIS18 Schottky
  SIS18 Extraction (Kicker modules, Septum..)
  SIS18 RF
  SIS18 Main Power Supplies
  ESR Main Power Supplies
  a few Cryring devices
There will be only base functionality.. So acquisition. But no interlock, post mortem, free configuration.
There is hope (but no guarantee) for a first GUI in MCR for operating.

## Slide 3: Spillglättung
The cavity needs some mechanical work (shorted). Not high precision but the ppl who can help are in vacation. I will still be possible to finish that and do commissioning
Commissioning outside tunnel, P. Hülsmann, 4 Weeks
Move into tunnel according to SIS18 Plan, (Hülsmann, Jönke, Großmontage, Gruber, Savino)
Commissioning w/o beam in Tunnel: 2 Weeks (Hülsmann)
Commisioning with beam, 4 Shifts machine beamtimewith break, (Ondreaka, Hülsmann)
-> Machine beamtime for spill scructure

## Slide 4: General
Extraction area vacuum problems need to be addressed in shutdown
IPM Magnets
Contract for design of new E-septum for extraction should start in 2019
Dedicated setup for „Forck/Sighn/Welker spill cleanup“
GAF work in shutdown (including nitrogen extinguisher test run)
regular maintenance