## Slide 1
Machine meeting 04.06.19 - UNILAC
  LEBT QQ beam pipe:
    all parts in house, assembly of A-pipe pending
    tests with todays pipe completed, cross-checked
    next step: removal of pipe, test with unloaded magnet
  Vacuum controls upgrade:
    LSB2: Equipping and connecting of new racks in progress
    LSB4: New racks in place, electric and air connection pending
    Installation of new hardware in progress

## Slide 2
Machine meeting 04.06.19 - UNILAC
  HSI RFQ:
    section 1-7: new electrodes implemented
  HSI IH 1:
    leak repaired, metal seals for re-assembly prepared
    electrical short checked, right now higher resistance  re-check after DT is in place
  FoS:
    drift tubes with stems ready for shipping
    FoS delivery in June
    PO for DT with quadrupole in July (yesterday good meeting with DANFYSIK)
    Cu cathode supports under production
    positive feedback from last MAC