## Raw Schedule
September
| So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo |  | Stage | 8am - 8pm (Mo.-Fr.) | 8pm - 8am (Mo. - Fr.) + Weekend
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
[32 empty] | RF | RF Cond. for Uranium (HSI, Alvarez, TK) | - " -
HSI + Alv. + TK | [31 empty] | OP | Operator Training | - " - | bar: September So to September Mo
[31 empty] | 31 | COM | Commission without beam | - " -
[32 empty] | U01 | RF Cond. for Uranium (HSI, Alvarez, TK) parallel Beam Setup with Ar | - " -
[32 empty] | U02 | Stable beam for TK (low prio: parallel beam to ex-hall) | - " -
| September So: October |  | U03 | switch to Uranium, when ready
| Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
[32 empty] | S01 | Beam Setup | Beam Setup
HSI + Alv. + TK | October Di: RF; October Mo: RF+COM |  | S00/H00 | FAIR machine development | FAIR machine development
[32 empty] | S02 | Beam setup - prepare slow ext, fast ext, cooled beam | Machine Studies / Detector Tests
[32 empty] | S04 | Beam Setup - transfer to ESR | Machine Studies / Detector Tests
[32 empty] | S05 | Beam Setup - transfer to FRS | Machine Studies / Detector Tests
| October Di: November |  | S06 | stable beam parallel to ESR + FRS | Machine Studies / Detector Tests
| Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa |  | S07 | stable beam parallel to ESR + FRS, HEST beam setup (transfer ESR-Cryring) | Machine Studies / Detector Tests
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
[32 empty] | H01 | HHD for SIS Optimisation | Machine Studies / Detector Tests
Sources: HSI-UL | November Sa: ...; November So: 238U (when ready, 208Pb else) |  | H02 | Transfer optimisation SIS-ESR | Machine Studies / Detector Tests
Sources: HSI-UR | November Mo: 40Ar or 84Kr; November Mo: ... |  | H03 | Transfer optimisation FRS | Machine Studies / Detector Tests
[32 empty] | H04 | Optics evaluation and optimisation HTC | Machine Studies / Detector Tests
HLI | November Fr: Shutdown (work in cw-bunker) |  | H05 | Optics evaluation and optimisation HTA | Machine Studies / Detector Tests
HSI + Alv. + TK | November Fr: RF+COM; November Mo: U01; November Mi: U02 |  | H06 | Transfer setup and optics evaluation HHT | Machine Studies / Detector Tests
SIS18 | November Mo: COM; November Mi: S01; November Do: S02; November Fr: S04; November Mo: S05; November Mi: S06 |  | H07 | Optics evaluation and optimisation of transport ESR->CRYRING | Machine Studies / Detector Tests
HEST | November Mo: COM; November Mi: H01; November Fr: H02; November Mo: H03; November Mo: H04; November Fr: H05; November Di: H06; November Do: H07
ESR | November Mo: E01; November Fr: E02; November Mi: E03; November Do: E04
FRS | November Mo: COM; November Mo: F00; November Mi: F01; November Mo: F02; November Mo: F03 |  | E01 | Dry Test of Control System - storage ring mode | pause
Cryring | November Do: bake out extraction; November Fr: COM; November Mo: C00 |  | E02 | Beam setup (storage, cooling) | pause
[32 empty] | E03 | Beam setup (decceleration) | pause
[32 empty] | E04 | Beam setup (extraction) | pause
[32 empty] | E05 | stable beam for Cryring-Transfer | pause
December
| So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | [12 empty] | F00 | beam optimization for FRS | pause
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | [12 empty] | F01 | Primary beam SIS-TA, TA-S4, new SIS energy, detector signals, ID (including verification via tagging) | pause
[32 empty] | F02 | Beam to S8 (slow extraction) | pause
Sources: HSI-UL | December So: 238U (when ready, 208Pb else) | [12 empty] | F03 | Beam to S6, fast extraction | pause
Sources: HSI-UR | December So: 40Ar or 84Kr | [12 empty] | F04 | Training of people | pause
[32 empty] | F05 | Further options - Detector Tests | pause
HLI | December So: Shutdown (work in cw-bunker)
HSI + Alv. + TK | December Mo: U03; December Di: OP
SIS18 | December So: S06; December Di: S07; December Mo: S07; December Sa: S00; December Di: OP | [12 empty] | C00 | Beam setup with local injector / Test extraction system | pause
HEST | December So: H07; December Sa: H00; December Di: OP | [12 empty] | C01 | optimize/match injecton into YR (0.8/ 1.4 Tm) | pause
ESR | December So: E04; December Di: E05; December Mo: E05; December Di: OP | [12 empty] | C02 | optimize stored beam at injection energy, incl. orbit (0.8/ 1.4 Tm) | pause
FRS | December So: F04; December Mo: F05; December Di: OP | [12 empty] | C03 | setup cooling at injection energy | pause
Cryring | December Mo: C01; December Di: C02; December Mi: C03; December Do: C04; December Fr: C05; December Mo: C06; December Di: C07; December Mi: C08; December Do: C09; December Fr: C10; December Di: OP | [12 empty] | C04 | measure lifetime w/o cooling | pause
[32 empty] | C05 | setup deceleration from 1.4 Tm to 0.8 Tm | pause
[32 empty] | C06 | setup cooling at low rgidity | pause
[32 empty] | C07 | measure lifetime at low energy | pause
[32 empty] | C08 | Beam size/ position at 0.8 Tm | pause
[32 empty] | C09 | Tune Meas. to determine space charge limits | pause
[32 empty] | C10 | Test detector setups (move, scrape, measure) | pause

## Beam Studies
ID | Spokesperson | Title | status | target | ion
2019-BEA-001 | V.Kornilov | Measurements of the beam quality (emittances) preservation during the ramp and storage. | proposed
2019-BEA-002 | R. Singh | Improvement of spill micro-structure by tune wobbling for slow extraction | proposed
2019-BEA-003 | R. Singh | Closed orbit feedback | announced
2019-BEA-004 | M. Witthaus | Test of Profile-Grid Electronics for FAIR and GSI upgrade | proposed
2019-BEA-005 | M. Witthaus | Test of Resonant Transformer for FAIR & GSI upgrade | proposed
2019-BEA-006 | P. Boutchakov | Rad.-hard Scintillators | announced
2019-BEA-007 | B. Walasek-Höhne | Rad.-hard camera | announced
2019-BEA-008 | P. Forck | Profile-Grid Electronics pLINAC | announced
1) re-commission the ESR capabilities and to complete the CRYRING commissioning with beam from ESR
2) re-establish heavy ion beams, such as Pb and uranium, in the UNILAC
3) benchmark most challenging operation/beam performance that are requested for the upcoming physics program. Examples are 1) operational setup for minimizing the micro-spill structure of slow extracted SIS18 beam, 2) stored and cooled beam in CRYRING, 3) intensity limit of Pb and uranium beam, etc.