## Slide 1: Operations - 28.05.2019
Overall shutdown is progressing well
  Cryring Bake-Out starts on 07.06. – 17.06. (HKR manned, VAC on call)
  Dry-Runs and Cryring beam time in Sept. + Oct. need re-scheduling (will be coordinated with DEC + ACO)
  HEST: BI-upgrade for Mini CBM progressing well, transfer measurement planned for June 25th  installation starts sub sequentially, critical: BIG for wall openings  need to be finished till 26. Aug. because installing of cables is scheduled fix
Preparation Engineering-Run 2019
  2nd iteration is attached (prolonged time for RF-commissioning)
  beam studies proposal template: desired beam- and machine parameter are missing