## Slide 1: machine status
CRYRING@ESR & HITRAP
CRYRING@ESR
  - electron cooler
  - the scheduled filling failed due to clogged filling nozzle.
      Go through another warmup cycle – new fill schedule for June-11
      install remote pressure monitor using temporary equipment to avoid another blockage
  dipole chamber YR08 removed, installed, leaks removed, pumping now
    bake out scheduled to start on June-7
  new (May-29) accel. operation plan has possible conflicts between CS release, ESR dryruns and Cryring@ESR September Run
HITRAP
  no activities

## Slide 2: engineering run 2019
CRYRING@ESR
PAC Experiments in 2020 expect:
  136Xe50+, 238U88+ and 238U91+ @ about 10 MeV/u, 107 (/ minute)
  cooled!
topic | Beam | measure | time/shifts
optimize transport ESR-CRYRING | Any @ 1.4 Tm | beam size and intensities along HEST | 2
optimize/match injecton into YR (0.8/ 1.4 Tm) | Any @ 1.4 and 0.8 Tm | beam intensity on YR02DC1, YR07DC3, YR07DC3 | 2
optimize stored beam at injection energy, incl. orbit (0.8/ 1.4 Tm) | Any @ 1.4 and 0.8 Tm | current on DC trafo, Schottky, AC trafo, BPM signal, IPM | 1
setup cooling at injection energy | Any @ 1.4 and 0.8 Tm | IPM, Schottky | 1
measure lifetime and intensity w/o cooling | Heavy ions, eventually U91+ | IPM, DC, Schottky | 1
setup deceleration from 1.4 Tm to 0.8 Tm | Any @ 1.4 and 0.8 Tm | DC, AC, Schottky, BPM | 2
setup cooling at low rgidity | Any @ 1.4 and 0.8 Tm | Schottky, AC, life time | 1
measure lifetime and intensity at low energy | Heavy ions, eventually U91+ | DC, AC, Schottky | 1
Beam size/ position at 0.8 Tm | Any @ 1.4 and 0.8 Tm | beam size with scrapers, IPMs, BPMs | 1
Tune Meas. to determine space charge limits | Any @ 1.4 and 0.8 Tm | Tune on BPMs with HF exciter kicks | 1
Test detector setups (move, scrape, measure) | Any @ 1.4 and 0.8 Tm | rate on detector for different conditions | 1
S 14 shifts (7 days!)
Task based schedule for engineering run