## Slide 1: Overview GSI / FAIR Status Collaboration Meeting: CERN – GSI/FAIR Darmstadt - 2nd July 2019
Jörg Blaurock
Technical Managing Director FAIR GmbH & GSI GmbH

## Slide 2: FAIR & GSI Darmstadt
Status: May 2019
Notes: Hintergrundbild: aktueller Bildausschnitt der GSI mit neuen Gebäuden

## Slide 3: Agenda
FAIR & GSI – Strategy
GSI GmbH & FAIR GmbH Organisation
GSI Operation
GSI Campus
FAIR Project
Collaboration CERN – GSI/FAIR

## Slide 4: FAIR & GSI – Strategy
Our 4 strategic priorities
Construction of FAIR
FAIR phase 0 research program
Upgrade of existing accelerators
Campus development

## Slide 5: Agenda
FAIR & GSI – Strategy
GSI GmbH & FAIR GmbH Organisation
GSI Operation
GSI Campus
FAIR Project
Collaboration CERN – GSI/FAIR

## Slide 6: GSI GmbH & FAIR GmbH Organisation

## Slide 7: Agenda
FAIR & GSI – Strategy
GSI GmbH & FAIR GmbH Organisation
GSI Operation
GSI Campus
FAIR Project
Collaboration CERN – GSI/FAIR

## Slide 8: GSI Operation - Beam time 2019 Q1

## Slide 9: GIS Operation Physics run: 10/02/2019 – 15/04/2019
Carry out scheduled Physics program from Feb. 28 to April 15
Continue the ESR and CRYRING commissioning
Physics run plan:
  A total of 17 experiments:
    9 UNILAC, 8 SIS18 fix target
    Requested ions: 12-C, Sn, Ag, 48-Ca, Au, 16-O, 56-Fe
  ESR commissioning as synchrotron
  CRYRING commissioning and user operation as stand alone mode
Status quo so far
  Done, all carried out with requested ion species. BeamOnTgt: ~80%!
    Highlight: HADES with significant improved spill quality by modulating quadrupoles
    Further improvement: R3B beam setup. Can benefit from steady operation
  Carried out with very limited time, a total of 15 shifts over the 2.5 month
    Achieved: deceleration Ag45+ from 260MeV/u to 110 MeV/u
    Decelerated Fe25+ was stored and cooled at 120MeV/u
  To be carried out: storage ring mode in the Fall of 2019
  Carried out with excellent stability w.o e-cooler, which has broken cryo system

## Slide 10: Agenda
FAIR & GSI – Strategy
GSI GmbH & FAIR GmbH Organisation
GSI Operation
GSI Campus
FAIR Project
Collaboration CERN – GSI/FAIR

## Slide 11: GSI Campus Development - Masterplan
FAIR & GSI Campus Development - 1st Phase
FAIR Control center (FCC)
Multi storey car park
Entrance building
Refurbishment of existing buildings
Car park
Entrance building
FCC
KBW

## Slide 12: Agenda
FAIR & GSI – Strategy
GSI GmbH & FAIR GmbH Organisation
GSI Operation
GSI Campus
FAIR Project
Collaboration CERN – GSI/FAIR

## Slide 13: FAIR Project - International Review 2019
International Project Review completed and conclusions presented to 26th Extraordinary FAIR Council on 29th April 2019

## Slide 14: FAIR Project - International Review 2019
Conclusions of the Review Panel
  Science case of FAIR MSV as world class science confirmed
  First experiments are expected end 2025
  FAIR project execution works are recognized as very good
  Full scope of civil works should be executed at once
  Solutions for providing the necessary additional funding should be implemented shortly to allow full continuation of project execution works
Next Steps
  Discussion in 27th (3.&4. July 2019) and 28th (5.&6. Dec. 2019) FAIR Council where proposed decisions need to be taken.

## Slide 15
FAIR Project – The Facility
Ring accelerator SIS100
Production of new atomic nuclei
Production of antiprotons
Collector ring
Antiproton ring
Linear accelerator
Ring accelerator
100 meters
Existing facility
Planned facility
Experiments

## Slide 16
FAIR Project - Master Time Schedule
New Baseline as February 2019
New Baseline Dates
Baseline Dates 2016
Early Science in second half of 2025
Completion of full FAIR MSV scheduled until mid 2026

## Slide 17
FAIR Project – ACC
  Integration of FOS quadrupole module started at BNG
  41 sc dipole modules delivered, 36 dipole modules successfully tested and accepted
  Contract for series testing of the integrated modules with INFN (Salerno, Italy) signed
  Series production released for thin wall dipole- and for thin wall quadrupole chambers with LHe cooling.
  Manufacturing of series of bunch compression cavities at Aurion completed
  Integration of series of bunch compressor power converters at OCEM almost completed
  Production of injection septum magnets and power converters completed
  Series production of cryo-adsorption pumps completed by ILK.
  Tender launched for main dipole- and quadrupole power converters and for extraction kicker system.
  Decision taken for technical solution of quench detection system based on GSI-inhouse developments.
SIS100
sc dipole modules in GSI storage area
Bunch compression cavities at AURION
FOS QP module integration @ BNG

## Slide 18
FAIR Project – ACC
  Kick-off meeting at CERN of the testing facility for SC magnets performed
  Successful FAT of First-of-Series SC Multiplet; Multiplet shipped to CERN for testing
  SC branched dipoles specifications ready. Award of tender expected for Q4-19 / Q1-20
  Local cryogenics specification released in January 2019
  Contracts status with BINP:
      NC dipoles and diagnostic vacuum chambers signed
      Contract finalised for SC dipoles vacuum chambers
      Negotiation ongoing for NC multipoles, NC magnet chambers, other vacuum elements and BPM detectors
Super- FRS
Kick-off of testing facility at CERN
  Production contract for the special radiation hard cable as supplementary material (MIC cable) for NC dipoles signed in January 2019
  In-kind contract with Sweden for SEM-grid detectors signed in February 2019. Kick-off done on 04/04/2019
  India expressed interest to provide the laterally part of iron shield. Decision required soon.
Notes: Negotitation ongoing streichen?

## Slide 19
FAIR Project – ACC
  Commissioning of ion source at CEA in progress. Beam shape improved
  Ladder-RFQ (fig. 1) opened and machined to final geometry after first low level RF tests and succeeding simulations. Very good agreement with expected resonace frequency, quality factor and flatness
  Copper Plating tests for first CCH cavity started. Promising results with dummy cavity (see fig. 2 and 3)
pLinac/ pbar Target

## Slide 20
FAIR Project – ACC
  Series production of RF – debunchers has been finished. SAT is under preparation at GSI
  Series production of Power amplifiers for Stochastic Cooling is in progress
  2nd BINP - FAIR Coordination Workshop performed covering aspects of all subprojects in Darmstadt at GSI from 20th – 24th May 2019
Collector Ring
RF-debuncher
Power amplifiers for Stochastic Cooling
FAIR-BINP Coordination Workshop May 2019

## Slide 21
FAIR Project – ACC
  All Dipoles are produced and are in Jülich, 78% are delivered to FAIR
  All Quadrupoles are produced and are in Jülich
  Sextupoles, steerers and their power converters are in production (Romania), magnets arriving continuously in Jülich
  Nearly all other power converters are produced and are in Jülich.
  RF equipment mechanical design is finished, production has started.
  Stochastic cooling equipment, beam diagnostics and injection kickers are in production
HESR

## Slide 22
FAIR Project – ACC
  Installation of first beam dump in HEBT transfer building in April 2019
  HEBT Power Converter:
      Detailed Specifications of all HEBT Power Converter types released
      FAT of main series (67 pcs.) HEBT Quadrupole Power Converter completed at ECIL, India in June 2019
  HEBT Beam Instrumentation:
      Beam tests of FAIR-type Beam-Loss Monitors successfully tested with beam at HADES
      Acceptance tests of LIBERA readout system performed
Installation of HEBT beam dump
HEBT PC during FAT at ECIL
Inspection of prototype HEBT Steerer PC at ECIL
New Beam-Loss Monitor
designed & produced by GSI
COMMONS

## Slide 23
FAIR Project - Civil Construction
FAIR Site & Buildings

## Slide 24
Groundbreaking ceremony
on 3rd July 2017
FAIR Project - Civil Construction
1st SIS100 tunnel segment
concreting completed in April 2019

## Slide 25
Complex design of very large transfer building
FAIR Project - Civil Construction
Ground slab of transfer building under execution in April 2019

## Slide 26
FAIR Project - Civil Construction
- Contracting strategy for Technical building Installations

## Slide 27
FAIR Project - Civil Construction
- Next Steps
Continuation civil detailed design process and civil work in the field
Awarding of construction area south in full in Q4 2019
Continue tendering for technical building installation (MEP) and award in 2020

## Slide 28
FAIR Project - Experiments
Day 1 configurations vetted technically and scientifically by Expert Committee Experiments and Joint Scientific Council.
Experiments utilizing beams from SIS18 within the FAIR Phase-0 program have started.
First test experiments of the NUSTAR-R3B collaboration were performed with the fully operational GLAD magnet, a large German-French contribution to the experiments.
Main Achievements

## Slide 29: Agenda
FAIR & GSI – Strategy
GSI GmbH & FAIR GmbH Organisation
GSI Operation
GSI Campus
FAIR Project
Collaboration CERN – GSI/FAIR

## Slide 30: Collaboration CERN – GSI/FAIR
CERN and GSI/FAIR have an excellent and longlasting collaboration over many decades.
We appreciate very much that you are visiting GSI/FAIR Campus.
We are looking forward to fruitful discussions to intensify collaboration activities on proposed selected topics with special focus on FAIR.

## Slide 31
Thank you for your attention !