## Slide 1
Machine meeting 25.06.19 - UNILAC
  LEBT QQ beam pipe:
    assembly of A-pipe: welding and annealing (partly) finished, mounting of cooling jacket pending
    next step on-site: test with backup pipe & unloaded magnet
  HSI RFQ:
    All sections new electrodes implemented, cleanded & checked
    Waiting for setup for LLRF measurements
  HSI IH 1:
    Electrical short fixed, drift tube and all other components inside tank in place
    Ready for mounting of end plate

## Slide 2
Machine meeting 25.06.19 - UNILAC
  Vacuum controls upgrade:
    LSB2: on schedule
      Equipping and connecting of new racks in progress
      connecting of contactor controllers continued
    LSB4: on schedule
      New racks in place
      Mounting of contactor controllers continued
  FoS:
    FoS FAT at VA-TEC last week (mantle and endplates):
      dimensions ok
      surfaces better than expected, however small defects spotted which will be fixed easily
      FAT w.r.t. UHV within next days
      some flange-welding proc. to be re-defined
    Cu cathode supports production proceeds well
    drift tubes with stems ready for transport to bunker
    drift tube with quadrupole to be ordered soon