## Slide 1: NUSTAR financial and project status 11th meeting of the ECE / 2nd meeting of ECSG FAIR/GSI, Darmstadt, Germany
Alexander Herlert
NUSTAR Resource Coordinator
FAIR
France
India
Finland
Germany
Poland
Sweden
Romania
Russia
Slovenia
UK

## Slide 2
 | Super-FRS | RIB production, separation, and identification
PSP | Experiment | Description
1.2.2 | HISPEC/ DESPEC | In-beam -spectroscopy at low and intermediate energy, n-decay, high-resolution -, -, -, p-, spectroscopy
1.2.3 | MATS | In-trap mass measurements and decay studies
1.2.4 | LaSpec | Laser spectroscopy
1.2.5 | R3B | Kinematically complete reactions with relativistic radioactive beams
1.2.6 | ILIMA | Large-scale scans of mass and lifetimes of nuclei in ground and isomeric states
1.2.10 | Super-FRS Exp | High-resolution spectrometer experiments
1.2.11 | SHE | Synthesis and study of super-heavy elements
1.2.8 | ELISe(*) | Elastic, inelastic, and quasi-free e--A scattering
1.2.9 | EXL(*) | Light-ion scattering reactions in inverse kinematics
(*) NESR required – alternative/intermediate “operation” within MSV under discussion.
Super-FRS Experiment Day-one configuration defined
NUSTAR – The project structure
Notes: 2

## Slide 3: NUSTAR MSV – funding status 2019
Chart: 
| secured/expected FAIR | secured external | EoI | to be assigned
Spalte1 | 0.48 | 0.24 | 0.18 | 0.1
funding (secured and expected) from:
(FAIR members/associates in bold face)
Status: February 2019
  Israel
  Netherlands
  Poland
  Romania
  Russia
  Spain
  Sweden
  Turkey
  United Kingdom
  Australia
  Belgium
  Bulgaria
  Canada
  Finland
  France
  Germany
  Hungary
  India
44.0 MEUR

## Slide 4: Evolution of NUSTAR project funding (MSV)
Chart: Cost (MEUR 2005)
| RRB 1 | RRB 2 | RRB 3 | RRB 4 | RRB 5 | RRB 6 | RRB 7 | RRB 8
secured external | 5.0704 | 7.275 | 7.163 | 7.1276 | 8.811 | 8.9075 | 9.8169 | 10.4239
secured/expected FAIR | 18.3556 | 22.7468 | 23.011 | 21.5824 | 20.4 | 20.6264 | 21.1011 | 21.1011
EoI | 15.5584 | 10.496 | 10.433 | 12.79 | 11.859 | 9.8496 | 7.9499 | 8.139
to be assigned | 8.2528 | 6.728 | 6.728 | 4.719 | 4.914 | 6.2457 | 6.7361 | 4.3723
Note:
GLAD with final cost
UK included in FAIR

## Slide 5: Phases of construction and operation
Phase 0
  R&D and experiments to be carried out with present facilities and FAIR/NUSTAR equipment
Phase 1 (starting with Day-one)
  Core detectors and subsystems completed (Day-one configurations)
  First measurements with FAIR/Super-FRS beams
    Carry out Day-one experiments with highest visibility as part of the core program and within the FAIR MSV
Phase 2
  FAIR evolving towards full power
  Completion of experiments within MSV
    Essentially the full program of MSV can be performed
Phase 3
  Moderate projects, which have been initiated on the way (outside MSV) can be included (e.g. experiments related to return line for rings or R3B spectrometer)
Phase 4
  Major new investments and upgrades for all experiments
MSV

## Slide 6: Day-one configuration (ECE meeting 2018)
Chart: 
| secured/expected FAIR | secured external | EoI | to be assigned
Spalte1 | 0.59 | 0.24 | 0.04 | 0.13
Chart: 
| secured/expected FAIR | secured external | EoI | to be assigned | Infrastructure Common Fund | R3B multiplet
Spalte1 | 0.59 | 0.24 | 0.04 | 0.02 | 0.07 | 0.04
Status: February 2018
35.8 MEUR

## Slide 7: Day-one configuration (2019)
Chart: 
| secured/expected FAIR | secured external | EoI | to be assigned
Spalte1 | 0.65 | 0.29 | 0.05 | 0.01
funding (secured and expected) from:
(FAIR members/associates in bold face)
  Israel
  Netherlands
  Poland
  Romania
  Russia
  Spain
  Sweden
  United Kingdom
  Bulgaria
  Canada
  Finland
  France
  Germany
  Hungary
  India
32.5 MEUR
Status: February 2019

## Slide 8: Day-one configuration – funding status
Chart: 
| secured/expected FAIR | secured external | EoI | Common Fund | to be assigned
Spalte1 | 0.65 | 0.29 | 0.02 | 0.03 | 0.01
funding (secured and expected) from:
(FAIR members/associates in bold face)
  Israel
  Netherlands
  Poland
  Romania
  Russia
  Spain
  Sweden
  United Kingdom
  Bulgaria
  Canada
  Finland
  France
  Germany
  Hungary
  India
32.5 MEUR
Status: February 2019
Common Fund to be shared equally among NUSTAR members (with PhD)
to be defined

## Slide 9: Infrastructure items for Common Fund (RRB 8)
PSP | Name | cost (2005) [k€]
1.2.1.2.4 | Detectors and slit system in front CSC | 135.7
1.2.1.2.5 | Beam line to MATS-LaSpec hall | 154.0
1.2.1.7 | Beam line to MATS RFQ | 200.0
1.2.2.2.1 | HISPEC/DESPEC Beamline | 127.1
1.2.2.5.1 | Safety measures | 132.1
1.2.5.1.1.3.3 | Valve box GLAD | 128.1
1.2.5.1.1.3.4 | Infrastructure magnets | 200.0
NUSTAR Common Fund |  | 1,077.0
  Several components required for the Day-one configurations have been identified by the NUSTAR Collaboration as common infrastructure items.
  These items cannot be taken over by partner institutes.
  The costs for some items is given as defined in the respective TDRs, which are presently under evaluation by the ECE

## Slide 10: Cryogenic Stopping Cell
PSP | Name | cost (2005) [k€]
1.2.1.2.4 | Detectors and slit system in front CSC | 135.7
1.2.1.2.5 | Beam line to MATS-LaSpec hall | 154.0
1.2.1.7 | Beam line to MATS RFQ | 200.0
1.2.2.2.1 | HISPEC/DESPEC Beamline | 127.1
1.2.2.5.1 | Safety measures | 132.1
1.2.5.1.1.3.3 | Valve box GLAD | 128.1
1.2.5.1.1.3.4 | Infrastructure magnets | 200.0
NUSTAR Common Fund |  | 1,077.0
  TDR with ECE
  Components to be covered by Common Fund are standard systems (e.g. beam diagnostics)

## Slide 11: Beam line between CSC and MATS RFQ
PSP | Name | cost (2005) [k€]
1.2.1.2.4 | Detectors and slit system in front CSC | 135.7
1.2.1.2.5 | Beam line to MATS-LaSpec hall | 154.0
1.2.1.7 | Beam line to MATS RFQ | 200.0
1.2.2.2.1 | HISPEC/DESPEC Beamline | 127.1
1.2.2.5.1 | Safety measures | 132.1
1.2.5.1.1.3.3 | Valve box GLAD | 128.1
1.2.5.1.1.3.4 | Infrastructure magnets | 200.0
NUSTAR Common Fund |  | 1,077.0
  Defined in CSC TDR
  Standard beamline and vacuum components (incl. support structures)

## Slide 12: HISPEC/DESPEC infrastructure
PSP | Name | cost (2005) [k€]
1.2.1.2.4 | Detectors and slit system in front CSC | 135.7
1.2.1.2.5 | Beam line to MATS-LaSpec hall | 154.0
1.2.1.7 | Beam line to MATS RFQ | 200.0
1.2.2.2.1 | HISPEC/DESPEC Beamline | 127.1
1.2.2.5.1 | Safety measures | 132.1
1.2.5.1.1.3.3 | Valve box GLAD | 128.1
1.2.5.1.1.3.4 | Infrastructure magnets | 200.0
NUSTAR Common Fund |  | 1,077.0
  TDR with ECE (total cost about 2 MEUR, Day one: 1.6 MEUR)
  Cost sharing under discussion: more than 10 institutes involved
  Common Fund contribution below 200 kEUR and further reduction possible
  Day-one configuration: 82% of funding secured (survey in progress)

## Slide 13: R3B magnet infrastructure
PSP | Name | cost (2005) [k€]
1.2.1.2.4 | Detectors and slit system in front CSC | 135.7
1.2.1.2.5 | Beam line to MATS-LaSpec hall | 154.0
1.2.1.7 | Beam line to MATS RFQ | 200.0
1.2.2.2.1 | HISPEC/DESPEC Beamline | 127.1
1.2.2.5.1 | Safety measures | 132.1
1.2.5.1.1.3.3 | Valve box GLAD | 128.1
1.2.5.1.1.3.4 | Infrastructure magnets | 200.0
NUSTAR Common Fund |  | 1,077.0
  R3B multiplet moved to accelerator (Super-FRS sub-project)
  Part of magnet infrastructure (incl. GLAD) to be covered by experiment
  “Infrastructure magnets” (200 kEUR) (cryo components) possibly not needed – to be checked

## Slide 14: Latest news on MoU (2019)
General Conditions for Experiments at FAIR
  Endorsed by FAIR AFC
MoU
  CBM Collaboration presented its MoU at the 8th FAIR-RRB meeting
  NUSTAR MoU adapted to the one from CBM:
    Slightly re-structured the document (new ordering of articles)
    NUSTAR specific annexes
  Update NUSTAR organizational structures
  Discuss new version with NUSTAR Boards
  NUSTAR Common Fund still not clarified

## Slide 15: Check list NUSTAR MoU
NUSTAR member list updated?
In progress (new database operational)
All TDRs for “Day one” at least submitted?
Still some TDRs needed (R3B) – expected until spring 2020
All work packages relevant for “Day one” assigned to partner institute?
Need to establish “Common Fund”
Contributions of new partners under discussion
Interfaces clarified (connections to accelerator and civil construction)?
In progress (as part of building planning) ...
General conditions for experiments available?
Endorsed by FAIR AFC ...

## Slide 16: WP defined by TDR
Work package
Funding
Schedule
Components
Teams
TDR
M3

## Slide 17: TDR Status (2019)
TDR # | title | submission | date | approval | date
 |  | status |  | status | 
2_01 | LEB infrastructure | expected | Nov 19 |  | 
2_02 | Cryogenic Stopping cell | submitted | Aug 18 |  | 
2_03 | Beam tracking/identification | obsolete |  |  | 
2_04 | HISPEC/DESPEC infrastructure | submitted | Nov 18 |  | 
2_05 | NUSTAR DAQ | submitted | Nov 16 | approved | Jun 18
2_06 | MINOS | obsolete |  |  | 
2_07 | Active target (India) | expected | Nov 22 |  | 
2_08 | HYDE | expected | Nov 22 |  | 
2_09 | LYCCA | submitted | Jun 08 | approved | Sep 08
2_10 | Plunger | submitted | Apr 14 | approved | Jun 14
2_11 | AIDA | submitted | Aug 08 | approved | Mrz 13
2_12 | DEGAS | submitted | Aug 14 | approved | Jul 15
2_13 | FATIMA | submitted | Mrz 15 | approved | Jul 15
2_14 | BELEN | submitted | Jan 14 | approved | Aug 14
2_15 | MONSTER | submitted | Feb 13 | approved | Aug 14
2_16 | NEDA | submitted | Sep 14 | approved | Jan 16
2_17 | DTAS | submitted | Apr 12 | approved | Jan 13
2_18 | Isomeric moments | expected | Nov 19 |  | 
2_19 | MATS/LaSpec | submitted | Sep 09 | approved | Mai 10
2_20 | R3B multiplet | obsolete |  |  | 
2_21 | GLAD | submitted | Jun 06 | approved | Jul 08
2_22 | R3B tracking | submitted | Nov 14 | approved | Jul 15
2_23 | Large Area ToF Wall | obsolete |  |  | 
2_24 | CALIFA barrel | submitted | Nov 11 | approved | Jan 13
2_25 | CALIFA fwd endcap | submitted | Nov 14 | approved | Jul 15
2_26 | Si tracker | expected | Mrz 20 |  | 
2_27 | NeuLAND | submitted | Nov 11 | approved | Jan 13
2_28 | R3B vacuum | expected | Sep 19 |  | 
2_29 | R3B infrastructure | expected | Nov 19 |  | 
2_30 | R3B spectrometer | expected | Nov 21 |  | 
2_31 | R3B spectrom tracking | obsolete |  |  | 
2_32 | ACTAF | submitted | Sep 15 | approved | Jun 17
2_33 | ILIMA Schottky | submitted | Dez 17 | approved | Dez 18
2_34 | ILIMA TOF detectors | submitted | Dez 17 | approved | Okt 18
2_35 | ILIMA Heavy ion detector | submitted | Nov 17 | approved | Okt 18
2_36 | AGATA | obsolete |  |  | 
2_37 | Slowed down beam setup | expected | Nov 21 |  | 
2_38 | EXPERT | submitted | Sep 16 | approved | Jul 17
2_39 | Super-FRS Exp infrastructure | submitted | Mai 19 |  | 
2_40 | Liquid hydrogen target | expected | Jul 21 |  | 
2_41 | (Ice target and tensor force) | expected | Jul 21 |  | 
2_42 | (future WASA) | expected | Jul 24 |  | 
3 under evaluation by ECE
4 needed for Day-one and are still expected in the next months
8 more expected, but not time critical
21 approved

## Slide 18: TDR Status (2019) – Day-one configuration
TDR # | title | submission | date | approval | date
 |  | status |  | status | 
2_01 | LEB infrastructure | expected | Nov 19 |  | 
2_02 | Cryogenic Stopping cell | submitted | Aug 18 |  | 
2_04 | HISPEC/DESPEC infrastructure | submitted | Nov 18 |  | 
2_05 | NUSTAR DAQ | submitted | Nov 16 | approved | Jun 18
2_09 | LYCCA | submitted | Jun 08 | approved | Sep 08
2_10 | Plunger | submitted | Apr 14 | approved | Jun 14
2_11 | AIDA | submitted | Aug 08 | approved | Mrz 13
2_12 | DEGAS | submitted | Aug 14 | approved | Jul 15
2_13 | FATIMA | submitted | Mrz 15 | approved | Jul 15
2_14 | BELEN | submitted | Jan 14 | approved | Aug 14
2_15 | MONSTER | submitted | Feb 13 | approved | Aug 14
2_16 | NEDA | submitted | Sep 14 | approved | Jan 16
2_17 | DTAS | submitted | Apr 12 | approved | Jan 13
2_19 | MATS/LaSpec | submitted | Sep 09 | approved | Mai 10
2_21 | GLAD | submitted | Jun 06 | approved | Jul 08
2_22 | R3B tracking | submitted | Nov 14 | approved | Jul 15
2_24 | CALIFA barrel | submitted | Nov 11 | approved | Jan 13
2_25 | CALIFA fwd endcap | submitted | Nov 14 | approved | Jul 15
2_26 | Si tracker | expected | Mrz 20 |  | 
2_27 | NeuLAND | submitted | Nov 11 | approved | Jan 13
2_28 | R3B vacuum | expected | Sep 19 |  | 
2_29 | R3B infrastructure | expected | Nov 19 |  | 
2_32 | ACTAF | submitted | Sep 15 | approved | Jun 17
2_33 | ILIMA Schottky | submitted | Dez 17 | approved | Dez 18
2_34 | ILIMA TOF detectors | submitted | Dez 17 | approved | Okt 18
2_35 | ILIMA Heavy ion detector | submitted | Nov 17 | approved | Okt 18
2_38 | EXPERT | submitted | Sep 16 | approved | Jul 17
2_39 | Super-FRS Exp infrastructure | submitted | Mai 19 |  | 
2_40 | Liquid hydrogen target | expected | Jul 21 |  | 
2_41 | (Ice target and tensor force) | expected | Jul 21 |  | 
2_42 | (future WASA) | expected | Jul 24 |  | 
3 under evaluation by ECE
4 needed for Day-one and are still expected in the next months
3 more expected (Super-FRS experiment, but not time critical)
21 approved

## Slide 19: Keep track of funding status
Work package
Funding
Schedule
Components
Teams
external
FAIR
ME1 = funding established
M4 = in-kind contract signed
cost-matrix
M4
ME1
TO DO:
report on funding status
preparation of contracts
writing detailed specifications

## Slide 20: In-kind and Collaboration Contracts
Country | Experiment | Description | in-kind value | requested? | specs? | contract? | signed?
Finland | HISPEC/DESPEC | DEGAS stage 2 | 268 | yes | no | no | no
 | HISPEC/DESPEC | MONSTER | 119.9 | yes | yes | yes | yes
 | MATS | RFQ | 215.2 | yes | Draft | no | no
 | LaSpec | Laser-based beam preparation | 106.4 | yes | Draft | no | no
France | R3B | GLAD | 2530 | yes | Draft | Draft | no
Germany | HISPEC/DESPEC | DEGAS stage 1 | 390 | yes | no | no | no
 | HISPEC/DESPEC | DEGAS stage 2 | 100 | yes | no | no | no
 | R3B | GLAD | 2530 | yes | Draft | Draft | no
 | R3B | NeuLAND stage 1 | 390 | yes | no | no | no
 | ILIMA | Heavy Ion Detector | 65.7 | yes | no | no | no
 | ILIMA | Schottky pick-ups | 341.3 | yes | no | no | no
 | ILIMA | Time-of-flight detectors | 333 | yes | yes | Draft | no
India | HISPEC/DESPEC | DEGAS | 1410 | yes | yes | yes | no
 | HISPEC/DESPEC | MONSTER | 560 | yes | yes | yes | no
 | MATS | Preparation Penning Trap | 40 | yes | Draft | no | no
Romania | HISPEC/DESPEC | FATIMA | 100 | yes | no | no | no
 | HISPEC/DESPEC | Plunger | 122.5 | yes | no | no | no
Russia | R3B | ACTAF – Small chamber ACTAF 2 | 174.7 | yes | yes | yes | yes
 | R3B | NeuLAND - HV distribution system | 415 | yes | yes | yes | yes
 | R3B | CALIFA endcap – iPhos detection modules | 300 | yes | yes | yes | yes
 | R3B | Proton arm spectrometer | 489.3 | yes | yes | yes | yes
Sweden | HISPEC/DESPEC | DEGAS stage 2 | 450 | yes | no | no | no
 | HISPEC/DESPEC | LYCCA | 150 | yes | yes | yes | no
 | R3B | CALIFA barrel stage 1 | 399.2 | yes | yes | yes | yes
 | R3B | CALIFA forward endcap | 575.8 | yes | no | no | no
United Kingdom | HISPEC/DESPEC | AIDA | 975 | yes | no | no | no
 | HISPEC/DESPEC | DTAS | 84 | yes | no | no | no
 | HISPEC/DESPEC | FATIMA | 464.6 | yes | no | no | no
 | HISPEC/DESPEC | LYCCA | 705.4 | yes | no | no | no

## Slide 21: From construction to operation
Work package
Funding
Schedule
Components
Teams
construction
M91
M10
FAT
shipment
assembly
installation
commissioning
test with beam
A92
A10
A12
A112
A119
M11
M9
M92
M12
ready for installation (SAT A)
factory acceptance test (FAT)
ready for beam (SAT Ba)
ready for operation (SAT Bb)

## Slide 22: NUSTAR score card (Sep. 2019)

## Slide 23: HISPEC/DESPEC status report (Sep. 2019)
TDR approval expected Nov. 2019

## Slide 24: Define and keep track of components
Work package
Funding
Schedule
Components
Teams
definition
location
documentation
logistics
AID and CID
SID
safety, manuals, etc.
central organization
TO DO:
Define components
Link components to beamline
Define required documents
Which items require logistics (GSI local transport services)?

## Slide 25: Define and keep track of teams
Work package
Funding
Schedule
Components
Teams
TO DO:
register all NUSTAR members (membership in sub-collaborations)
define team leaders
add team members
also reflect contributions without „investment“

## Slide 26: NUSTAR database – work in progress
NUSTAR
member DB
NUSTAR
web page
EDMS
GSI email
server
ECE
PLM (+CDB)
RRB
MS Project
WP leaders + providers
NUSTAR DB
milestones
TDRs
component list
work packages
funding
in-kind contracts

## Slide 27: NUSTAR project key objectives for 2020
Finalize remaining TDRs for Day-one
Establish Common Fund in order to complete Day-one configuration (infrastructure items)
Conclude NUSTAR member list update
Complete NUSTAR Construction MoU
AND:
More in-kind contracts
Follow-up of component construction
Further refine installation planning